## Data
Upgrade Id | Region | Description | Project Type | Voltage | Cost Estimate | Required Date | Transmission Owner | Proposal IDs | Schedule12 Location | (Non-Load Ratio Share) Cost Allocation Percent | (Load Ratio Share) Cost Allocation Percent | State | Location | Equipment | Task | Status | TEAC Cost | Driver | Projected In Service Date | Actual In Service Date | Immediate Need | Initial TEAC Date | Latest TEAC Date | Percent Complete | ISA In-Service Date | Revised In-Service Date | TEAC Materials
b3124 | PJM WEST | Separate metering, station power, and communication at Bruce Mansfield 345 kV station | Baseline | 345 | 0.93 | 12/31/2020 | ATSI |  | Appendix A | ATSI:100 |  | PA | Bruce Mansfield | Substation | Modify | EP | 0.4 | Generator Deactivation | 12/30/2025 |  | Yes | 7/11/2019 | 7/11/2019 | 39
b3144.1 | PJM MA | Upgrade line relaying and substation conductor on the 46 kV Nanty Glo line exit at Jackson Road substation | Baseline | 46 | 0 | 6/1/2024 | PENELEC |  | Appendix A | PENELEC:100 |  | PA | Jackson | Relay | Upgrade | EP |  | TO Criteria Violation | 6/30/2025 |  | No | 9/24/2019 | 11/18/2019 | 1
b3232 | PJM MA | Replace the existing Williamsburg, ALH (Hollidaysburg) and bus section breaker at the Altoona substation with a new breaker with higher interrupting capability. | Baseline | 46 | 1.7 | 6/1/2025 | PENELEC |  | Appendix A | PENELEC:100 |  | PA |  | Circuit Breaker | Replace | EP | 1.7 | TO Criteria Violation | 6/1/2025 |  | No | 11/18/2020 | 11/18/2020 | 0
b3233 | PJM MA | Install one 34 MVAR 115 kV shunt reactor and breaker. Install one 115 kV circuit breaker to expand the substation to a 4 breaker ring bus. | Baseline | 115 | 4.9 | 6/1/2025 | PENELEC |  | Appendix A | PENELEC:100 |  | PA |  | Reactive Device | Install | EP | 4.9 | Baseline Load Growth Deliverability & Reliability | 12/31/2027 |  | No | 11/18/2020 | 11/18/2020 | 3
b3234 | PJM WEST | Extend both the east and west 138 kV buses at Pine substation, and install one 138 kV breaker, associated disconnect switches, and one 100 MVAR reactor. | Baseline | 138 | 3.8 | 6/1/2025 | ATSI |  | Appendix A | ATSI:100 |  | PA |  | Reactive Device | Install | EP | 3.8 | TO Criteria Violation | 3/22/2028 |  | No | 10/16/2020 | 11/20/2020 | 2
b3306 | PJM MA | Install a second 125 MVAR 345 kV shunt reactor and associated equipment at Pierce Brook Substation. Install a 345 kV breaker on the high side of the #1 345/230 kV transformer | Baseline | 345 | 8.08 | 6/1/2025 | PENELEC | 2020_W1-855 | Appendix A | PENELEC:100 |  | PA | Pierce Brook | Reactive Device | Install | EP | 8.08 | Baseline Load Growth Deliverability & Reliability | 12/31/2026 |  | No | 12/1/2020 | 12/1/2020 | 0
b3666 | PJM MA | Marshall 230 kV Substation: Install dual reactors and expand existing ring bus | Baseline | 230 | 5.83 | 6/1/2026 | PENELEC | 2021_1-745 | Appendix A | PENELEC:100 |  | PA | Marshall | Reactive Device | Install | EP | 5.83 | Baseline Load Growth Deliverability & Reliability | 12/31/2027 |  | No | 11/2/2021 | 11/2/2021 | 3
b3667 | PJM MA | Pierce Brook Substation: Install second 230/115 kV transformer | Baseline | 230/115 | 5.07 | 6/1/2026 | PENELEC | 2021_1-101 | Appendix A | PENELEC:100 |  | PA | Pierce Brook | Transformer | Install | EP | 5.07 | Baseline Load Growth Deliverability & Reliability | 12/1/2027 |  | No | 11/2/2021 | 11/2/2021 | 10
b3673 | PJM MA | Replace the relay panels at Bethlehem 33 46 kV substation on the Cambria Prison line. | Baseline | 46 | 0.3 | 6/1/2026 | PENELEC |  | Appendix A | PENELEC:100 |  | PA | Bethlehem 33 | Relay | Replace | EP | 0.3 | TO Criteria Violation | 6/1/2026 |  | No | 11/18/2021 | 11/18/2021 | 0
b3681 | PJM WEST | Upgrade the Shingletown #82 230-46 kV transformer circuit by installing a 230 kV breaker and disconnect switches, removing existing 230 kV switches, replacing 46 kV disconnect switches, replacing limiting substation conductor, and installing/replacing relays. | Baseline | 230 | 1.66 | 6/1/2026 | APS | 2021_1-919 | Appendix A | APS:100 |  | PA | Shingletown 230 kV substation | Circuit Breaker | Install | EP | 1.66 | Baseline Load Growth Deliverability & Reliability | 10/31/2025 |  | No | 11/30/2021 | 11/30/2021 | 30
b3708 | Not Specified | Replace the Shawville 230/115/17.2 kV transformer with a new Shawville 230/115 kV transformer and associated facilities. Replace the plant’s No. 2B 115/17.2 kV transformer with a larger 230/17.2 kV transformer. | Baseline | 230/115/17.2 | 8.78 | 6/1/2026 | PENELEC | 2021_1-100 | Appendix A | PENELEC:100 |  | PA | Shawville | Transformer | Replace | EP | 8.78 | Baseline Load Growth Deliverability & Reliability | 12/31/2026 |  | No | 3/8/2022 | 3/8/2022 | 15
b3715.3 | PJM MA | Install a new Allen four breaker ring bus within the existing MetEd Allen substation. Terminate the Round Top-Allen and the Allen-PPGI (PPG Industries) 115 kV lines into the new switchyard. | Baseline | 115 | 11.73 | 6/1/2026 | ME | 2021_1-99 | Appendix A | ME:100 |  | PA | Allen | Ring Bus | Modify | EP | 6.41 | Baseline Load Growth Deliverability & Reliability | 6/1/2026 |  | No | 5/10/2022 | 5/10/2022 | 39
b3717.1 | PJM WEST | Install a series reactor on Cheswick-Springdale 138 kV line | Baseline | 138 | 9 | 12/31/2024 | APS |  | Appendix A | APS:23.19,DL:76.81 |  | PA | Springdale | Series Reactor | Install | EP | 7.36 | Generator Deactivation | 3/17/2026 |  | Yes | 9/6/2022 | 9/5/2023 | 5
b3717.3 | PJM WEST | Relay work at Springdale 138 kV | Baseline | 138 | 1 | 12/31/2024 | APS |  | Appendix A | APS:100 |  | PA | Cheswick | Relay | Modify | EP | 1 | Generator Deactivation | 1/24/2025 |  | No | 4/11/2023 | 4/11/2023 | 39
b3737.47 | PJM MA | Build New North Delta 500 kV substation (four bay breaker and half configuration ) - the substation will include 12 - 500kV breakers and one 500/230 kV transformer, will allow the termination of six - 500 kV lines | Baseline | 500/230 | 104.1 | 6/1/2027 | Transource | 2021_SAA-63 | Appendix C | Reliability driver (26.73%): PECO:100 PublicPolicy driver (73.27%): AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA | North Delta | Substation | Build | EP | 104.1 | Public Policy,Baseline Load Growth Deliverability & Reliability | 10/15/2027 |  | No | 11/4/2022 | 12/5/2023 | 15
b3737.50 | PJM MA | Bring the Peach Bottom-Delta York 500 ‘5034’ kV line “in and out” of Bramah substation by partially demolishing the 5034 line to construct a new Peach Bottom-Bramah-Delta York 500 kV line, with 0.87 miles of cut-in and cut-out lines. | Baseline | 500 | 12 | 6/1/2029 | PECO | 2021_SAA-63 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | PA | Peach Bottom-Delta Power Plant | Transmission Line | Modify | EP | 12 | Public Policy | 6/1/2029 |  | No | 11/4/2022 | 5/6/2025 | 4
b3738 | PJM WEST | Charleroi - Dry Run 138 kV Line: Replace Limiting Terminal Equipment | Baseline | 138 | 0.38 | 6/1/2027 | APS |  | Appendix A | APS:100 |  | PA | Charleroi - Dry Run 138 kV | Substation | Replace | EP | 0.38 | Baseline Load Growth Deliverability & Reliability | 6/1/2027 |  | No | 11/18/2022 | 11/18/2022 | 4
b3739 | PJM WEST | Dry Run - Mitchell 138 kV Line: Replace Limiting Terminal Equipment | Baseline | 138 | 0.4 | 6/1/2027 | APS |  | Appendix A | APS:100 |  | PA | Dry Run - Mitchell 138 kV | Substation | Replace | EP | 0.4 | Baseline Load Growth Deliverability & Reliability | 6/1/2027 |  | No | 11/18/2022 | 11/18/2022 | 2
b3740 | PJM WEST | Glen Falls - Bridgeport 138 kV Line: Replace Limiting Terminal Equipment | Baseline | 138 | 1.88 | 6/1/2027 | APS |  | Appendix A | APS:100 |  | PA | Glen Falls - Bridgeport 138 kV | Substation | Replace | EP | 1.88 | Baseline Load Growth Deliverability & Reliability | 5/29/2026 |  | No | 11/18/2022 | 11/18/2022 | 24
b3741 | PJM WEST | Yukon - Charleroi No.1 138 kV Line: Replace Limiting Terminal Equipment | Baseline | 138 | 0.7 | 6/1/2027 | APS |  | Appendix A | APS:100 |  | PA | Yukon - Charleroi No.1 138 kV | Substation | Replace | EP | 0.7 | Baseline Load Growth Deliverability & Reliability | 6/1/2026 |  | No | 11/18/2022 | 11/18/2022 | 3
b3745 | PJM WEST | Carbon Center Substation - Install Redundant Relaying | Baseline | 230 | 0.57 | 6/1/2027 | APS |  | Appendix A | APS:100 |  | PA | Carbon Center 230 kVSubstation | Substation | Replace | EP | 0.57 | Baseline Load Growth Deliverability & Reliability | 6/1/2026 |  | No | 11/18/2022 | 11/18/2022 | 2
b3750 | PJM MA | Upgrade Seward Terminal Equipment of the Seward-Blairsville 115 kV Line to increase the line rating such that the Transmission Line conductor is the limiting component. | Baseline | 115 | 0.43 | 6/1/2027 | PENELEC |  | Appendix A | PENELEC:100 |  | PA | Seward | Disconnect Switch | Upgrade | EP | 0.43 | Baseline Load Growth Deliverability & Reliability | 5/1/2026 |  | No | 10/13/2022 | 11/17/2022 | 20
b3751 | PJM MA | Rebuild 6.4 miles of the Roxbury - Shade Gap 115 kV line from Roxbury to the AE1-071 115 kV ring bus with single circuit 115 kV construction | Baseline | 115 | 15.03 | 6/1/2027 | PENELEC |  | Appendix A | PENELEC:100 |  | PA | Roxbury to the AE1-071 | Transmission Line | Rebuild | EP | 15.03 | Baseline Load Growth Deliverability & Reliability | 6/29/2027 |  | No | 10/13/2022 | 11/17/2022 | 5
b3752 | PJM MA | Rebuild 7.2 miles of the Shade Gap - AE1-071 115 kV line section of the Roxbury - Shade Gap 115 kV line | Baseline | 115 | 17.43 | 6/1/2027 | PENELEC |  | Appendix A | PENELEC:100 |  | PA | Shade Gap - AE1-071 115 | Transmission Line | Rebuild | EP | 17.43 | Baseline Load Growth Deliverability & Reliability | 12/10/2026 |  | No | 10/13/2022 | 11/17/2022 | 5
b3753 | PJM MA | Replace the Tyrone North 115 /46 kV transformer with a new standard 75 MVA top rated bank and upgrade the entire terminal to minimum 100 MVA capability for both SN and SE rating | Baseline | 115/46 | 2.82 | 6/1/2027 | PENELEC |  | Appendix A | PENELEC:100 |  | PA | Tyrone North | Transformer | Replace | EP | 2.82 | TO Criteria Violation | 6/1/2027 |  | No | 10/13/2022 | 11/17/2022 | 2
b3754 | PJM MA | At Maclane tap: Construct a new three breaker ring bus to tie into the Warrior Ridge - Belleville 46 kV D line and the 1LK line | Baseline | 46 | 10.09 | 6/1/2027 | PENELEC |  | Appendix A | PENELEC:100 |  | PA | Maclane | Bus | Modify | EP | 10.09 | TO Criteria Violation | 9/9/2028 |  | No | 10/13/2022 | 11/17/2022 | 2
b3761 | PJM WEST | Install 138 kV Breaker on the Ridgway 138/46 kV #2 Transformer | Baseline | 138 | 1.1 | 6/1/2027 | APS |  | Appendix A | APS:100 |  | PA | Ridgway 138/46 kV | Circuit Breaker | Install | EP | 1.1 | Baseline Load Growth Deliverability & Reliability | 6/1/2027 |  | No | 12/16/2022 | 12/16/2022 | 0
b3769 | PJM MA | Install second TMI 500/230kV Transformer with additional 500 and 230 bus expansions | Baseline | 500/230 | 30.19 | 6/1/2027 | ME | 2022-W1-880 | Appendix A | ME:45.74,PPL:54.26 |  | PA | TMI | Transformer | Install | EP | 30.19 | Baseline Load Growth Deliverability & Reliability | 6/1/2027 |  | No | 12/6/2022 | 1/6/2023 | 4
b3770 | PJM MA | Rebuild 1.4 miles of existing single circuit 230 kV tower line between BGE's Graceton substation to the Brunner Island PPL tie-line at the MD/PA state line to double circuit steel pole line with one (1) circuit installed to uprate 2303 circuit | Baseline | 230 | 10.17 | 6/1/2027 | BGE | 2022-W1-912 | Appendix A | BGE:99.98,ME:0.01,PPL:0.01 |  | PA | Graceton - Brunner Island | Transmission Structures | Rebuild | EP | 8.4 | Baseline Load Growth Deliverability & Reliability | 6/1/2027 |  | No | 12/6/2022 | 1/6/2023 | 25
b3773 | PJM WEST | Install (1) 31.7 MVAR switched capacitor, 138 kV breaker, and associated relaying at Warfordsburg Substation | Baseline | 138 | 3.05 | 6/1/2027 | APS |  | Appendix A | APS:100 |  | PA | McConnellsburg | Reactive Device | Install | EP | 3.05 | Baseline Load Growth Deliverability & Reliability | 6/1/2027 |  | No | 12/6/2022 | 4/11/2025 | 4
b3774 | PJM MA | Upgrade terminal equipment at Brunner Island (on the Brunner Island - Yorkana 230 kV circuit) | Baseline | 230 | 2.5 | 6/1/2027 | PPL |  | Appendix A | PPL:100 |  | PA | Brunner Island | Conductor | Replace | EP | 2.5 | Baseline Load Growth Deliverability & Reliability | 6/1/2027 |  | No | 12/6/2022 | 1/6/2023 | 10
b3780.1 | PJM MA | Peach Bottom North upgrades – substation work Add 3x 500 kV breakers to form a breaker-and-a-half bay. | Baseline | 500 | 76.63 | 6/1/2025 | PECO |  | Appendix A | ATSI:0.02,BGE:28.40,Dominion:33.36,DPL:0.02,JCPL:6.36,Neptune:0.73,PECO:0.01,PEPCO:17.90,PSEG:12.69,RE:0.51 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA | Peach Bottom | Substation | Build | EP | 76.63 | Generator Deactivation | 12/31/2028 |  | Yes | 6/6/2023 | 6/6/2023 | 9
b3780.14 | PJM MA | Reconfigure Cooper transmission feeds by establishing new Cooper-North Delta 230 kV line and rerouting existing transmissions lines by Cooper. | Baseline | 500 | 6.73 | 6/1/2025 | PECO | 2022-W3 | Appendix A | DPL:38.25,PECO:61.75 |  | PA | Cooper | Transmission Line | Build | EP | 6.73 | Generator Deactivation | 12/31/2028 |  | Yes | 12/5/2023 | 1/9/2024 | 19
b3780.2 | PJM MA | Peach Bottom to Graceton (PECO) – New 500 kV transmission line New rating: 4503 MVA SN/ 5022 MVA SE | Baseline | 500 | 63.74 | 6/1/2025 | PECO |  | Appendix A | ATSI:0.02,BGE:28.40,Dominion:33.36,DPL:0.02,JCPL:6.36,Neptune:0.73,PECO:0.01,PEPCO:17.90,PSEG:12.69,RE:0.51 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA | Peach Botton - Graceton | Transmission Line | Install | EP | 63.74 | Generator Deactivation | 12/31/2028 |  | Yes | 6/6/2023 | 6/6/2023 | 7
b3800.1 | PJM MA | Build New Otter Creek 500 kV (Collinsville) - (switching station -Two bay three breaker configuration). | Baseline | 500 | 32.76 | 6/1/2027 | PPL | 2022-W3-374 | Appendix A | APS:13.16,BGE:0.71,Dominion:74.28,DPL:0.36,PECO:0.68,PEPCO:10.59,PPL:0.22 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  | Circuit Switcher | Build | EP | 32.76 | Baseline Load Growth Deliverability & Reliability | 4/23/2027 |  | No | 12/5/2023 | 12/5/2023 | 5
b3800.10 | PJM MA | Rebuild the Germantown-Lincoln 115 kV line for 230 kV double circuit construction. | Baseline | 115 | 30.1 | 6/1/2027 | ME | 2022-W3-837 | Appendix A | ME:100 |  | PA |  | Transmission Line | Rebuild | EP | 30.1 | Baseline Load Growth Deliverability & Reliability | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 0
b3800.101 | PJM WEST | 502 Junction substation two 500 kV circuit breaker expansion. | Baseline | 500 | 30.6 | 6/1/2027 | APS | 2022-W3-853 | Appendix A | APS:25.59,BGE:9.79,Dominion:51.94,PEPCO:12.68 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA | 502 Junction | Circuit Breaker | Upgrade | EP | 30.6 | Baseline Load Growth Deliverability & Reliability | 12/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 30
b3800.11 | PJM MA | Rebuild the Hunterstown-Lincoln 115 kV line for 230 kV double circuit construction. | Baseline | 115 | 11.48 | 6/1/2027 | ME | 2022-W3-837 | Appendix A | ME:100 |  | PA |  | Transmission Line | Rebuild | EP | 11.48 | Baseline Load Growth Deliverability & Reliability | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 0
b3800.12 | PJM MA | Rebuild the Germantown-Carroll 138 kV line for 230 kV double circuit construction (MAIT). | Baseline | 138 | 12.16 | 6/1/2027 | ME | 2022-W3-837 | Appendix A | ME:100 |  | PA |  | Transmission Line | Rebuild | EP | 12.16 | Baseline Load Growth Deliverability & Reliability | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 15
b3800.121 | PJM WEST | Kammer to 502 Junction 500 kV line: Conduct LIDAR Sag Study to assess SE rating and needed upgrades. | Baseline | 500 | 0.1 | 6/1/2027 | AEP | 2022-W3-853 | Appendix A | AEP:21.66,APS:0.01,BGE:7.14,DEOK:0.01,Dominion:62.25,PEPCO:8.93 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA | 502 Junction | Transmission Line | Sag Study | EP | 0.1 | Baseline Load Growth Deliverability & Reliability | 6/1/2027 |  | No | 12/5/2023 | 12/5/2023 | 0
b3800.14 | PJM MA | Construct New 230 kV Hunterstown-Carroll line (MAIT section). | Baseline | 230 | 17.37 | 6/1/2027 | ME | 2022-W3-837 | Appendix A | APS:99.86,ME:0.14 |  | PA |  | Transmission Line | Construct | EP | 17.37 | Baseline Load Growth Deliverability & Reliability | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 0
b3800.18 | PJM MA | Add a new 230 kV Breaker at the Hunterstown 230 kV substation for the new Hunterstown-Carroll 230 kV termination. | Baseline | 230 | 2.31 | 6/1/2027 | ME | 2022-W3-837 | Appendix A | APS:99.86,ME:0.14 |  | PA |  | Circuit Breaker | Build | EP | 2.31 | Baseline Load Growth Deliverability & Reliability | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 0
b3800.2 | PJM MA | Break the existing TMI-Peach Bottom line within the existing right-of-way and install new structures rerouting the line toward Chanceford switchyard taps being constructed by PPL. | Baseline | 500 | 7.43 | 6/1/2027 | ME | 2022-W3-374, DENL | Appendix A | APS:13.16,BGE:0.71,Dominion:74.28,DPL:0.36,PECO:0.68,PEPCO:10.59,PPL:0.22 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  | Transmission Line | Modify | EP | 7.43 | Baseline Load Growth Deliverability & Reliability | 6/1/2027 |  | No | 12/6/2023 | 5/1/2024 | 3
b3800.22 | PJM MA | Install DTT relaying at Straban substation. | Baseline | 115 | 0.67 | 6/1/2027 | ME | 2022-W3-837 | Appendix A | ME:100 |  | PA |  | Relay | Install | EP | 0.67 | Baseline Load Growth Deliverability & Reliability | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 0
b3800.23 | PJM MA | Revise Relay Settings at Lincoln substation. | Baseline | 115 | 0.31 | 6/1/2027 | ME | 2022-W3-837 | Appendix A | ME:100 |  | PA |  | Relay | Modify | EP | 0.31 | Baseline Load Growth Deliverability & Reliability | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 0
b3800.24 | PJM MA | Revise Relay Settings at Germantown substation. | Baseline | 115 | 0.47 | 6/1/2027 | ME | 2022-W3-837 | Appendix A | ME:100 |  | PA |  | Relay | Modify | EP | 0.47 | Baseline Load Growth Deliverability & Reliability | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 0
b3800.3 | PJM MA | Build New 500kV AC line from the new Otter Creek (Chanceford) 500 kV switchyard – towards PA/MD border ~12.5 miles Ø Rebuild the existing Otter Creek - Conastone 230 kV line to become a double-circuit 500 kV line, operate Conastone circuit at 230 kV initially | Baseline | 500 | 102.8 | 6/1/2027 | PPL | 2022-W3-374 | Appendix A | APS:13.16,BGE:0.71,Dominion:74.28,DPL:0.36,PECO:0.68,PEPCO:10.59,PPL:0.22 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  | Transmission Line | Build | EP | 102.8 | Baseline Load Growth Deliverability & Reliability | 4/30/2027 |  | No | 12/6/2023 | 5/1/2024 | 5
b3800.31 | PJM MA | Build new North Delta-High Ridge 500 kV line. | Baseline | 500 | 42.06 | 6/1/2027 | PECO | 2022-W3-344 | Appendix A | Dominion:60.85,DPL:0.01,PECO:0.01,PEPCO:29.24,PSEG:9.48,RE:0.41 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  | Transmission Line | Build | EP | 13.36 | Baseline Load Growth Deliverability & Reliability | 12/1/2030 |  | No | 12/5/2023 | 12/5/2023 | 6
b3800.35 | PJM MA | Rebuild 5012 (existing Peach Bottom-Conastone) (new North Delta-Graceton PECO) 500 kV line on single circuit structures within existing ROW and cut into North Delta 500 kV and Gracetone 500 kV stations. | Baseline | 500 | 43.78 | 6/1/2027 | PECO | 2022-W3-344 | Appendix A | BGE:49.42,Dominion:31.22,DPL:0.01,JCPL:0.01,PECO:3.75,PEPCO:15.57,PSEG:0.02 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  | Transmission Line | Rebuild | EP | 29.86 | Baseline Load Growth Deliverability & Reliability | 12/1/2030 |  | No | 12/5/2023 | 12/5/2023 | 6
b3800.42 | PJM MA | Peach Bottom North bus upgrade - Replace 11 – Instances of strain bus conductor used for breaker drops or CT drops, 7 – 500 kV disconnect switches, 7 – Free Standing CTs, 1 – 500 kV breaker, 2 – Breaker relays or meters. | Baseline | 500 | 7.27 | 6/1/2027 | PECO | 2022-W3-344 | Appendix A | BGE:62.82,DPL:7.25,JCPL:0.09,Neptune:0.01,PECO:0.01,PEPCO:29.63,PSEG:0.18,RE:0.01 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  | Transmission Line | Upgrade | EP | 2.7 | Baseline Load Growth Deliverability & Reliability | 12/1/2030 |  | No | 12/5/2023 | 12/5/2023 | 15
b3800.44 | Not Specified | North Delta termination for the North Delta-High Ridge 500 line (PECO work). | Baseline | 500 | 4.76 | 6/1/2027 | PECO | 2022-W3-344 | Appendix A | Dominion:60.85,DPL:0.01,PECO:0.01,PEPCO:29.24,PSEG:9.48,RE:0.41 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  | Transmission Line | Construct | EP | 3.4 | Baseline Load Growth Deliverability & Reliability | 12/1/2030 |  | No | 10/31/2023 | 12/5/2023 | 13
b3800.45 | PJM MA | North Delta 500 kV termination for the Rock Springs 500 kV line (5034/5014 line) (PECO work). | Baseline | 500 | 1.45 | 6/1/2027 | PECO | 2022-W3-344, DENL | Appendix A | AEC:17.65,BGE:4.43,Dominion:9.87,DPL:22.25,JCPL:3.16,Neptune:0.36,PECO:2.98,PENELEC:0.44,PEPCO:3.80,PPL:5.99,PSEG:27.86,RE:1.21 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  | Transmission Line | Construct | EP | 0.8 | Baseline Load Growth Deliverability & Reliability | 12/1/2030 |  | No | 10/31/2023 | 1/9/2024 | 15
b3800.46 | Not Specified | North Delta 500 kV termination for the new Peach Bottom-North Delta 500 kV line (PECO work). | Baseline | 500 | 2.7 | 6/1/2027 | PECO | 2022-W3-344 | Appendix A | AEC:11.03,BGE:37.40,DPL:22.91,PEPCO:28.66 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  | Transmission Line | Construct | EP | 2.6 | Baseline Load Growth Deliverability & Reliability | 12/1/2030 |  | No | 10/31/2023 | 12/5/2023 | 27
b3800.47 | Not Specified | Build new Peach Bottom South-North Delta 500 kV line – cut in to Peach Bottom tie No. 1 and extending line to North Delta (~1.25 miles new ROW). | Baseline | 500 | 8.4 | 6/1/2027 | PECO | 2022-W3-344 | Appendix A | AEC:11.03,BGE:37.40,DPL:22.91,PEPCO:28.66 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  | Transmission Line | Construct | EP | 5.5 | Baseline Load Growth Deliverability & Reliability | 12/1/2030 |  | No | 10/31/2023 | 12/5/2023 | 12
b3800.48 | Not Specified | North Delta termination for the North Delta-High Ridge 500 line (Transource work). | Baseline | 500 | 4.38 | 6/1/2027 | Transource | 2022-W3-344 | Appendix A | Dominion:60.85,DPL:0.01,PECO:0.01,PEPCO:29.24,PSEG:9.48,RE:0.41 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  | Transmission Line | Construct | EP | 0.96 | Baseline Load Growth Deliverability & Reliability | 12/15/2030 |  | No | 10/31/2023 | 12/5/2023 | 15
b3800.49 | Not Specified | North Delta 500 kV termination for the Calpine generator (Calpine/Transource work). | Baseline | 500 | 4.05 | 6/1/2027 | Transource | 2022-W3-344 | Appendix A | PECO:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  | Transmission Line | Construct | EP | 4.05 | Baseline Load Growth Deliverability & Reliability | 10/6/2027 |  | No | 10/31/2023 | 12/5/2023 | 15
b3800.5 | PJM MA | Peach Bottom-TMI 500 kV – Replace terminal equipment at Peach Bottom (install new line terminal relays and communication infrastructure within Peach Bottom and along the 5007) | Baseline | 500 | 6.11 | 6/1/2027 | PECO | 2022-W3-374 | Appendix A | AEC:6.40,BGE:20.32,DPL:9.76,JCPL:17.57,Neptune:1.73,PECO:6.33,PEPCO:7.48,PSEG:29.15,RE:1.26 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  | Substation | Replace | EP | 2.5 | Baseline Load Growth Deliverability & Reliability | 6/1/2027 |  | No | 12/7/2023 | 5/1/2024 | 3
b3800.50 | Not Specified | North Delta 500 kV termination for the Rock Springs 500 kV line (5034/5014 line) (Transource work). | Baseline | 500 | 3.55 | 6/1/2027 | Transource | 2022-W3-344 | Appendix A | AEC:17.65,BGE:4.43,Dominion:9.87,DPL:22.25,JCPL:3.16,Neptune:0.36,PECO:2.98,PENELEC:0.44,PEPCO:3.80,PPL:5.99,PSEG:27.86,RE:1.21 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  | Transmission Line | Construct | EP | 0.49 | Baseline Load Growth Deliverability & Reliability | 1/23/2028 |  | No | 10/31/2023 | 12/5/2023 | 15
b3800.51 | Not Specified | North Delta 500 kV termination for the new Peach Bottom-North Delta 500 kV line (Transource work). | Baseline | 500 | 3.68 | 6/1/2027 | Transource | 2022-W3-344 | Appendix A | AEC:11.03,BGE:37.40,DPL:22.91,PEPCO:28.66 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  | Transmission Line | Construct | EP | 0.29 | Baseline Load Growth Deliverability & Reliability | 5/31/2028 |  | No | 10/31/2023 | 12/5/2023 | 15
b3800.52 | PJM MA | Reconfigure Peach Bottom North and South yards to allow for termination of 500 kV lines from Peach Bottom to North Delta. North Delta 500 kV termination for the new Peach Bottom-North Delta 500 kV line. | Baseline | 500 | 14.25 | 6/1/2027 | PECO | 2022-W3-344/660 | Appendix A | AEC:11.03,BGE:37.40,DPL:22.90,PEPCO:28.67 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA | Peach Bottom | Transmission Line | Modify | EP | 7.86 | Baseline Load Growth Deliverability & Reliability | 12/1/2030 |  | No | 10/31/2023 | 1/9/2024 | 11
b3800.53 | PJM MA | Construct a double circuit 500 kV line from the existing TMI-Peach Bottom 500 kV right-of-way to the proposed Chanceford switchyard ~1.0 miles in length. | Baseline | 500 | 12.59 | 6/1/2027 | PPL | 2022-W3-374 | Appendix A | APS:13.37,Dominion:75.27,PEPCO:11.36 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA | Voltage |  |  | EP | 12.59 | Baseline Load Growth Deliverability & Reliability | 4/30/2027 |  | No | 5/1/2024 | 5/1/2024 | 0
b3858.1 | PJM MA | Rebuild the Windsor Substation 115 kV yard to convert from a straight bus configuration into a six-breaker ring bus configuration. Install two (2) 21.62 MVAR, 115 kV capacitor banks. | Baseline | 115 | 12.36 | 6/1/2028 | ME |  | Appendix A | ME:100 |  | PA | Windsor | Substation | Rebuild | EP | 12.36 | Baseline Load Growth Deliverability & Reliability | 6/1/2029 |  | No | 11/14/2024 | 11/14/2024 | 1
b3858.2 | PJM MA | Rebuild the Yorkana Substation 115 kV yard converting from a straight bus configuration to a (9) breaker, breaker-and-a-half configuration. | Baseline | 115 | 20.8 | 6/1/2028 | ME |  | Appendix A | ME:100 |  | PA | Yorkana | Substation | Rebuild | EP | 20.8 | Baseline Load Growth Deliverability & Reliability | 6/1/2029 |  | No | 11/14/2024 | 11/14/2024 | 1
b3862.1 | PJM MA | Upgrade two (2) 500kV free standing CTs, one (1) disconnect switch, and four (4) sections of tube bus at Elroy 500kV Substation. | Baseline | 500 | 1.5 | 6/1/2029 | PECO |  | Appendix A | PECO:100 |  | PA | Elroy | Substation equipment | Upgrade | EP | 1.5 | Baseline Load Growth Deliverability & Reliability | 12/31/2028 |  | No | 12/3/2024 | 12/3/2024 | 15
b3863.1 | PJM MA | Change tap ratios on two (2) CTs at Schuylkill 230kV Substation | Baseline | 230 | 0.1 | 12/1/2029 | PECO |  | Appendix A | PECO:100 |  | PA | Schuylkill | Substation equipment | Modify | EP | 0.1 | TO Criteria Violation | 12/1/2029 |  | No | 11/14/2024 | 11/14/2024 | 0
b3864.1 | PJM MA | Replace station cable at Tacony 69kv Station | Baseline | 69 | 0.18 | 6/1/2029 | PECO |  | Appendix A | PECO:100 |  | PA | Tacony | Substation equipment | Upgrade | EP | 0.18 | Baseline Load Growth Deliverability & Reliability | 6/1/2029 |  | No | 11/14/2024 | 11/14/2024 | 0
b3864.2 | PJM MA | Replace station cable at Richmond 230kV Station | Baseline | 69 | 0.18 | 6/1/2029 | PECO |  | Appendix A | PECO:100 |  | PA | Richmond | Substation equipment | Upgrade | EP | 0.18 | Baseline Load Growth Deliverability & Reliability | 6/1/2029 |  | No | 11/14/2024 | 11/14/2024 | 0
b3870.1 | PJM WEST | At Federal Street Substation: - Install (3) 138 kV CCVTs on the 138 kV bus. - Remove the Transformer 1 CO-6 138 kV Phase relay Overcurrent Relays. - Install (1) SEL-421 relay on the high side of Transformer 1. - Install foundations, conduit, and grounding for new CCVTs. - Install cables between CCVTs and relay. | Baseline | 138 | 0.69 | 6/1/2028 | APS |  | Appendix A | APS:100 |  | PA | Federal St. | Relay | Replace | EP | 0.69 | Baseline Load Growth Deliverability & Reliability | 6/1/2029 |  | No | 11/15/2024 | 11/15/2024 | 0
b3907.1 | PJM MA | Reconductor entire 2.5 miles of North Philadelphia to Master 230 kV line | Baseline | 230 | 6.49 | 6/1/2029 | PECO | 2024-W1-12 | Appendix A | AEC:0.76,JCPL:1.45,PECO:94.22,PSEG:3.29,RE:0.13,Neptune:0.15 |  | PA | North Philadelphia | Transmission Line | Rebuild | EP | 6.49 | Baseline Load Growth Deliverability & Reliability | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 3
b3907.2 | PJM MA | Richmond to Waneeta 230kV Line: Rebuild entire 0.95 miles of existing UGT, and rebuild entire 2.23 miles of existing OHT | Baseline | 230 | 29.4 | 6/1/2028 | PECO | 2024-W1-12 | Appendix A | AEC:9.99,JCPL:8.34,PECO:55.62,PSEG:24.31,RE:0.94,Neptune:0.80 |  | PA | Richmond | Transmission Line | Rebuild | EP | 29.4 | Baseline Load Growth Deliverability & Reliability | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 3
b3907.3 | PJM MA | Reconductor 2.12 miles of North Philadelphia to Waneeta 230 kV line | Baseline | 230 | 7.33 | 6/1/2028 | PECO | 2024-W1-12 | Appendix A | AEC:10.75,JCPL:14.26,PECO:38.58,PSEG:33.62,RE:1.31,Neptune:1.48 |  | PA | Waneeta | Transmission Line | Rebuild | EP | 7.33 | Baseline Load Growth Deliverability & Reliability | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 3
b3908.1 | PJM MA | Install one 80 MVAr 230 kV capacitor bank at Pocono 230kV Substation | Baseline | 230 | 4.97 | 6/1/2029 | PPL | 2024-W1-850 | Appendix A | PPL:100 |  | PA | Pocono | Capacitor | Install | EP | 4.93 | Baseline Load Growth Deliverability & Reliability | 4/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 0
b3909.1 | PJM MA | Juniata 500 kV yard expansion/reconfiguration to include one new bay and eliminate the line fault stuck breaker | Baseline | 500 | 23.73 | 6/1/2028 | PPL | 2024-W1-935 | Appendix A | PPL:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA | Juniata | Substation | Expand | EP | 22.2 | Baseline Load Growth Deliverability & Reliability | 6/1/2028 |  | No | 12/3/2024 | 12/3/2024 | 0
b3910.1 | PJM MA | Susquehanna T10 230 kV Station Reconfiguration. Break the existing Susquehanna - Glen Brook 230 kV line and loop it 0.2 miles in and out of the Susquehanna T10 230 kV Station. | Baseline | 230 | 10.07 | 6/1/2029 | PPL | 2024-W1-549 | Appendix A | PPL:100 |  | PA | Susquehanna | Substation | Reconfigure | EP | 9.5 | Baseline Load Growth Deliverability & Reliability | 12/31/2028 |  | No | 12/3/2024 | 12/3/2024 | 0
n4287 | PJM MA | Install 34.5kV tap, radio controlled switch and associated equipment at North Meshoppen 34.5kV and Tunkahannock 34.5kV substations | Network | 34.5 | 0.1 | 12/31/2015 | PENELEC |  |  |  |  | PA | North Meshoppen 34.5kV, Tunkahannock 34.5kV | Distribution Structure | Install | EP | 0.1 | Z1-038 |  |  | No | 10/8/2024 | 10/8/2024 | 0 | 12/31/2015
n4997 | Not Specified | Replace the disconnect switch at the Sabinsville 115 kV substation. | Network | 69 | 0.09 | 6/1/2017 | PENELEC |  |  |  |  | PA | Niles Valley – Sabinsville 115 kV line | Disconnect Switch | Replace | EP | 0.09 | AA2-081 |  |  | No | 10/8/2024 | 10/8/2024 | 0 | 6/1/2017
n6026 | Not Specified | Install one span of Attachment Facility line from the Point of Interconnection (POI) to the tap point at the Hokes – Grantley 69 kV Line. | Network | 69 | 0.2 | 4/1/2020 | ME |  |  |  |  | PA | Tap between Hokes and Grantley substations | Conductor | Install | EP | 0.2 | AD2-116 | 8/25/2022 |  | No | 11/1/2022 | 11/1/2022 | 15 | 4/1/2020 | 10/31/2020
n6027 | Not Specified | Install two switches at the tap point at the Hokes – Grantley 69kV Line. | Network | 69 | 0.4 | 4/1/2020 | ME |  |  |  |  | PA | Tap between Hokes and Grantley substations | Disconnect Switch | Install | EP | 0.4 | AD2-116 | 8/25/2022 |  | No | 11/1/2022 | 11/1/2022 | 15 | 4/1/2020 | 10/31/2020
n6028 | Not Specified | Estimated installation of 700 MHz radio system (70% penetration of FE territory) to support the SCADA switch replacements. Assumed SCADA work is included in this cost. | Network | 69 | 0.05 | 4/1/2020 | ME |  |  |  |  | PA | Tap between Hokes and Grantley substations | Communication Equipment | Install | EP | 0.05 | AD2-116 | 8/25/2022 |  | No | 11/1/2022 | 11/1/2022 | 15 | 4/1/2020 | 10/31/2020
n6107 | Not Specified | Keystone Substation: Revise relay settings on South Bend Terminal. | Network | 138 | 0.03 | 5/31/2022 | APS |  |  |  |  | PA | Keystone | Relay | Modify | EP | 0.03 | AD2-114 | 6/1/2023 |  | No | 9/28/2020 | 9/28/2020 | 0 | 5/31/2022 | 5/31/2022
n6726 | Not Specified | Dubois 34.5kV SS. Adjust Remote Relay and Metering Settings. | Network | 34.5 | 0.04 | 6/1/2022 | PENELEC |  |  |  |  | PA | Dubois 34.5 kV | Relay | Modify | EP | 0.04 | AE2-126 |  |  | No | 11/1/2022 | 11/1/2022 | 0 | 6/1/2022
n6727 | Not Specified | Curwensville 34.5kV SS. Adjust Remote Relay and Metering Settings. | Network | 34.5 | 0.04 | 6/1/2022 | PENELEC |  |  |  |  | PA | Curwensville 34.5 kV | Relay | Modify | EP | 0.04 | AE2-126 |  |  | No | 11/1/2022 | 11/1/2022 | 0 | 6/1/2022
n6890 | Not Specified | Tap the South Troy- Athens 34.5 kV line (distribution circuit 00517-63) near pole STS-17961 and install a span of 34.5 kV line to the Point of Interconnection with the Interconnection Customer including a new Supervisory Control and Data Acquisition (SCADA) recloser. | Network | 34.5 | 0.1 | 11/30/2021 | PENELEC |  |  |  |  | PA | South Troy-Athens 34.5 kV | Transmission Line | Install | EP | 0.1 | AF2-265 |  |  | No | 11/1/2022 | 11/1/2022 | 0 | 11/30/2021 | 9/1/2022
n6891 | Not Specified | South Troy 34.5 kV Substation: Adjust remote relay and metering settings on the Athens 34.5 kV terminal. | Network | 34.5 | 0.01 | 11/30/2021 | PENELEC |  |  |  |  | PA | South Troy 34.5 kV Substation | Relay | Modify | EP | 0.01 | AF2-265 |  |  | No | 11/1/2022 | 11/1/2022 | 0 | 11/30/2021 | 9/1/2022
n6983 | Not Specified | SCADA/Fiber Communication: Estimated installation of (2) 700 MHz radio systems (70% penetration of FE territory) to support SCADA Switches. Assumed SCADA work is included in this cost. | Network | 69 | 0.1 | 12/8/2020 | ATSI |  |  |  |  | PA |  | Communication Equipment | Install | EP | 0.1 | AE1-183 |  |  | No |  |  | 0 | 12/8/2020
n7001 | Not Specified | At new AE1-129 115 kV Switchyard: Install line exit take-off structure, foundations, disconnect switch and associated equipment at ring bus substation | Network | 115 | 0.69 | 9/30/2021 | ME |  |  |  |  | PA | New AE1-129 115 kV Switchyard | Disconnect Switch | Install | EP | 0.69 | AE1-129 | 12/7/2026 |  | No | 11/1/2022 | 11/1/2022 | 2 | 1/7/2027 | 9/30/2021
n7002 | Not Specified | Construct a new three-breaker ring bus on the 115kV line (977) between Middletown Junction Substation and Zions View Substation. Perform related project management, and Supervisory Control and Data Acquisition (SCADA) and fiber communication work. | Network | 115 | 9.7 | 9/15/2029 | ME |  |  |  |  | PA | New AE1-129 115 kV Switchyard | Substation | Install | EP | 9.7 | AE1-129 | 12/7/2026 |  | No | 11/1/2022 | 10/8/2025 | 2 | 1/7/2027 | 9/30/2021
n7003 | Not Specified | Cut the existing Middletown Junction – Smith Street (977) 115kV line between existing structure 65 and structure 66 to create a loop to the proposed ring | Network | 115 | 2.68 | 9/15/2029 | ME |  |  |  |  | PA | New AE1-129 115 kV Switchyard | Transmission Line | Loop | EP | 2.68 | AE1-129 | 12/7/2026 |  | No | 11/1/2022 | 10/8/2025 | 2 | 1/7/2026 | 9/30/2021
n7004 | Not Specified | Replace existing line relaying with (1) standard line relaying panel with (1) SEL421 and (1) SEL411L.Install (1) standard breaker control panel with (1) SEL451 BFT and (1) SATEC Meter at Middletown Junction Substation | Network | 115 | 0.69 | 9/15/2029 | ME |  |  |  |  | PA | Middletown Junction | Relay | Modify | EP | 0.69 | AE1-129 | 12/7/2026 |  | No | 11/1/2022 | 10/8/2025 | 2 | 1/7/2027 | 9/30/2021
n7005 | Not Specified | Replace (1) 115 kV OCB due to single CT condition with 145 kV 3000A 40kAIC breaker. Replace existing line relaying with (1) standard line relaying panel with (1) SEL421 and (1) SEL411L. Install (1) standard breaker control panel with (1) SEL451 BFT and (1) SATEC Meter at Smith Street Substation | Network | 115 | 1.53 | 9/15/2029 | ME |  |  |  |  | PA | Smith Street | Relay | Modify | EP | 1.53 | AE1-129 | 12/7/2026 |  | No | 11/1/2022 | 10/8/2025 | 2 | 1/7/2027 | 9/30/2021
n7312 | Not Specified | Maysville: Extend the Maysville 69 kV bus. Install one 69 kV circuit breaker. | Network | 69 | 0.82 | 6/30/2022 | ATSI |  |  |  |  | PA | Maysville | Bus | Modify | EP | 0.82 | AE2-285 |  |  | No | 11/1/2022 | 11/1/2022 | 0 | 6/30/2022
n7313 | Not Specified | Estimated SCADA work at Maysville substation to support breaker and relay installations. Estimated in-sub fiber run from Maysville control house to developer ran fiber build for communications and control to AE2-285 Generation Interconnection. | Network | 69 | 0.06 | 6/30/2022 | ATSI |  |  |  |  | PA | AE2-285/Maysville | Communication Equipment | Build | EP | 0.06 | AE2-285 |  |  | No | 11/1/2022 | 11/1/2022 | 0 | 6/30/2022
n7314 | Not Specified | Sharon: Modify relay settings. | Network | 69 | 0.1 | 6/30/2022 | ATSI |  |  |  |  | PA | Sharon | Relay | Modify | EP | 0.1 | AE2-285 |  |  | No | 11/1/2022 | 11/1/2022 | 0 | 6/30/2022
n7315 | Not Specified | Dilworth: Modify relay settings. | Network | 69 | 0.1 | 6/30/2022 | ATSI |  |  |  |  | PA | Dilworth | Relay | Modify | EP | 0.1 | AE2-285 |  |  | No | 11/1/2022 | 11/1/2022 | 0 | 6/30/2022
n7316 | Not Specified | McDowell: Modify relay settings. | Network | 69 | 0.1 | 6/30/2022 | ATSI |  |  |  |  | PA | McDowell | Relay | Modify | EP | 0.1 | AE2-285 |  |  | No | 11/1/2022 | 11/1/2022 | 0 | 6/30/2022
n7317 | Not Specified | Masury: Modify relay settings. | Network | 69 | 0.1 | 6/30/2022 | ATSI |  |  |  |  | PA | Masury | Relay | Modify | EP | 0.1 | AE2-285 |  |  | No | 11/1/2022 | 11/1/2022 | 0 | 6/30/2022
n7333 | Not Specified | AE1-196 Supervisory Control and Data Acquisition (SCADA)/Fiber Communication Estimated installation of (2) 700 MHz radio system (70% penetration of FE territory) to support the SCADA switch installations. SCADA work included. | Network | 69 | 0.1 | 4/1/2021 | ME |  |  |  |  | PA | AE1-196 Tap | Communication Equipment | Install | EP | 0.1 | AE1-196 | 12/31/2022 |  | No | 11/1/2022 | 11/1/2022 | 0 | 4/1/2021 | 12/31/2022
n7334 | Not Specified | Hokes-Jackson 69 kV Line Switches: At Hokes-Jackson (79) 69 kV line structure 79-142, install two (2) SCADA controlled disconnect switches, one each on either side of the tap. Includes Project Management, Commissioning, Environmental, Forestry, Real Estate, and Right of Way. | Network | 69 | 0.73 | 4/1/2021 | ME |  |  |  |  | PA | AE1-196 Tap | Transmission Line | Install | EP | 0.73 | AE1-196 | 12/31/2022 |  | No | 11/1/2022 | 11/1/2022 | 0 | 4/1/2021 | 12/31/2022
n7335 | Not Specified | Hokes 69 kV Substation: Update Relay Settings. | Network | 69 | 0.09 | 4/1/2021 | ME |  |  |  |  | PA | Hokes | Relay | Modify | EP | 0.09 | AE1-196 | 12/31/2022 |  | No | 11/1/2022 | 11/1/2022 | 0 | 4/1/2021 | 12/31/2022
n7336 | Not Specified | Jackson 69 kV Substation: Update Relay Settings. | Network | 69 | 0.09 | 4/1/2021 | ME |  |  |  |  | PA | Jackson | Relay | Modify | EP | 0.09 | AE1-196 | 12/31/2022 |  | No | 11/1/2022 | 11/1/2022 | 0 | 4/1/2021 | 12/31/2022
n7356 | Not Specified | Construct a new 3-breaker ring bus substation on the 230 kV line between Jackson Substation and Three Mile Island Substation. | Network | 230 | 1.08 | 6/30/2022 | ME |  |  |  |  | PA | New AE2-211 230 kV Switchyard | Substation | Modify | EP |  | AE2-211 |  |  | No |  |  | 0 | 6/30/2022 | 6/30/2022
n7357 | Not Specified | Design, install, and test/commission MPLS Equipment for SCADA transport | Network | 230 | 0.21 | 6/30/2022 | ME |  |  |  |  | PA | New AE2-211 230 kV Switchyard | Substation | Modify | EP |  | AE2-211 |  |  | No |  |  | 0 | 6/30/2022 | 6/30/2022
n7358 | Not Specified | Install fiber from AE2-211 Interconnect to Dover for MPLS transport | Network | 230 | 0.57 | 6/30/2022 | ME |  |  |  |  | PA | New AE2-211 230 kV Switchyard | Substation | Modify | EP |  | AE2-211 |  |  | No |  |  | 0 | 6/30/2022 | 6/30/2022
n7454 | Not Specified | Estimated installation of 700 MHz radio systems (70% penetration of FE territory) to support SCADA Switches. Assumed SCADA work is included in this cost. | Network | 69 | 0.12 | 6/30/2023 | ATSI |  |  |  |  | PA | Andover (Maysville) 69 kV Line | Communication Equipment | Install | EP | 0.12 | AE2-343 | 8/16/2023 |  | No | 11/1/2022 | 11/1/2022 | 0 | 6/30/2023 | 6/30/2023
n7455 | Not Specified | Tap the Andover (Maysville) 69kV line at or near structure 137. Install two 69kV line switches with SCADA. @ Dilworth-Maysville 69kV Tap | Network | 69 | 0.92 | 6/30/2023 | ATSI |  |  |  |  | PA | Andover (Maysville) 69 kV Line | Transmission Line | Build | EP | 0.92 | AE2-343 | 8/16/2023 |  | No | 11/1/2022 | 11/1/2022 | 0 | 6/30/2023 | 6/30/2023
n7457 | Not Specified | Update relay settings at Maysville | Network | 69 | 0.1 | 6/30/2023 | ATSI |  |  |  |  | PA | Maysville | Relay | Modify | EP | 0.1 | AE2-343 | 8/16/2023 |  | No | 11/1/2022 | 11/1/2022 | 0 | 6/30/2023 | 6/30/2023
n7458 | Not Specified | Update relay settings at Sharon | Network | 69 | 0.1 | 6/30/2023 | ATSI |  |  |  |  | PA | Sharon | Relay | Modify | EP | 0.1 | AE2-343 | 8/16/2023 |  | No | 11/1/2022 | 11/1/2022 | 0 | 6/30/2023 | 6/30/2023
n7888 | Not Specified | 69 kV Tap line, MOLBAB Switch, Poles, structure, and foundations. | Network | 69 | 0.72 | 3/5/2021 | PPL |  |  |  |  | PA | AE2-084 Line Tap (Milton-Millville 69 kV) | Substation | Install | EP |  | AE2-084 |  |  | No |  |  | 0 | 3/5/2021 | 12/15/2022
n7889 | Not Specified | Complete MILT-MVIL line modifications to tie in the new AE2-084 Attachment Facilities. This includes connecting the conductors and OPGW from the MILT-MVIL line to the new tap structure. | Network | 69 | 0.08 | 3/5/2021 | PPL |  |  |  |  | PA | AE2-084 Line Tap (Milton-Millville 69 kV) | Transmission Structures | Modify | EP |  | AE2-084 |  |  | No |  |  | 0 | 3/5/2021 | 12/15/2022
n7890 | Not Specified | Short Circuit Study, Review IC Engineering Package, and Remote End Work at the Milton 69 kV Substation | Network | 69 | 0.12 | 3/5/2021 | PPL |  |  |  |  | PA | Milton 69 kV Substation | Relay | Modify | EP |  | AE2-084 |  |  | No |  |  | 0 | 3/5/2021 | 12/15/2022
n8052.2 | Not Specified | Install new primary, backup, and control relay and protection equipment for the new terminal. | Network | 138 | 0.53 | 12/31/2019 | ComEd |  |  |  |  | IL,PA | TSS 86 Davis Creek | Relay | Install | EP | 0.53 | AC2-154 |  |  | No | 10/8/2025 | 10/8/2025 | 0 | 12/31/2019 | 12/31/2026
n8087.1 | Not Specified | McDowell 69 kV: Replace Maysville Y- 80/107 line relay & control panel with a standard line relaying panel. | Network | 69 | 0.72 |  | ATSI |  |  |  |  | PA | McDowell | Relay | Modify | EP | 0.72 | AF1-093 |  |  | No | 10/8/2024 | 10/8/2024 | 0
n8087.2 | Not Specified | Masury 69 kV: Relay settings will be revised. | Network | 69 | 0.04 |  | ATSI |  |  |  |  | PA | Masury | Relay | Modify | EP | 0.04 | AF1-093 |  |  | No | 10/8/2024 | 10/8/2024 | 0
n8087.3 | Not Specified | AF1-093: Tap the Maysville- McDowell 69kV line roughly 8.2 miles from McDowell substation, near structure 108. Install two 69kV line switches with SCADA. Install one span of 795 ACSR Drake toward the customer substation. | Network | 69 | 0.77 |  | ATSI |  |  |  |  | PA | Maysville - McDowell | Switching | Install | EP | 0.77 | AF1-093 |  |  | No | 10/8/2024 | 10/8/2024 | 0
n8087.4 | Not Specified | Maysville 69 kV: Relay settings will be revised. | Network | 69 | 0.04 |  | ATSI |  |  |  |  | PA | Maysville | Relay | Modify | EP | 0.04 | AF1-093 |  |  | No | 10/8/2024 | 10/8/2024 | 0
n8087.5 | Not Specified | Cedar Street 69 kV: Relay settings will be revised. | Network | 69 | 0.04 |  | ATSI |  |  |  |  | PA | Cedar Street | Relay | Modify | EP | 0.04 | AF1-093 |  |  | No | 10/8/2024 | 10/8/2024 | 0
n8087.6 | Not Specified | Sharon 69 kV: Relay settings will be revised. | Network | 69 | 0.04 |  | ATSI |  |  |  |  | PA | Sharon | Relay | Modify | EP | 0.04 | AF1-093 |  |  | No | 10/8/2024 | 10/8/2024 | 0
n8087.7 | Not Specified | Campbell 69 kV: Relay settings will be revised. | Network | 69 | 0.04 |  | ATSI |  |  |  |  | PA | Campbell | Relay | Modify | EP | 0.04 | AF1-093 |  |  | No | 10/8/2024 | 10/8/2024 | 0
n8121.1 | Not Specified | North Longview: Estimated SCADA work at North Longview to support breaker, MOAB, and relay installations. Estimated in-sub fiber run from North Longview control house to developer ran OPGW outside substation. | Network | 500 | 0.07 | 6/1/2022 | APS |  |  |  |  | PA | North Longview | Communication Equipment | Install | EP |  | AE1-105 |  |  | No |  |  | 0 | 6/1/2022
n8139.1 | Not Specified | three breaker ring switching station between transmission structures 2197/137 and 2197/138 | Network | 230 | 6.3 | 12/31/2020 | Dominion |  |  |  |  | PA | AD1-151 | Ring Bus | Construct | EP |  | AD1-151 |  |  | No |  |  | 0 | 12/31/2020 | 12/1/2027
n8139.2 | Not Specified | Re-arrange line #2197 to loop into and out of the new three breaker AD1-151 230 kV switching station | Network | 230 | 0.14 | 12/31/2020 | Dominion |  |  |  |  | PA | AD1-151 | Transmission Line | Modify | EP |  | AD1-151 |  |  | No |  |  | 0 | 12/31/2020 | 12/1/2027
n8139.3 | Not Specified | Colonial Trail and Hopewell 230 kV substations | Network | 230 | 0.01 | 12/31/2020 | Dominion |  |  |  |  | PA | Cotton Trail, Hopewell | Relay | Modify | EP |  | AD1-151 |  |  | No |  |  | 0 | 12/31/2020 | 12/1/2027
n8168.1 | Not Specified | Cut the existing Hoytdale-McClelland 345kV line 5.2 miles from the McClelland substation, near structure #81, and loop the circuit into the new AF1-146 Substation. Install (2) spans to loop the line in and out of the substation. | Network | 345 | 3.25 | 12/31/2021 | ATSI |  |  |  |  | PA | Hoytdale – McClelland | Transmission Line | Construct | EP |  | AF1-146 |  |  | No |  |  | 0 | 12/31/2021 | 12/31/2025
n8168.10 | Not Specified | Review and update relay settings. | Network | 345 | 0.37 | 12/31/2021 | ATSI |  |  |  |  | PA | Hoytdale | Relay | Modify | EP |  | AF1-146 |  |  | No |  |  | 0 | 12/31/2021 | 12/31/2025
n8168.11 | Not Specified | Construct three breaker ring bus interconnection facility | Network | 345 | 0.98 | 12/31/2021 | ATSI |  |  |  |  | PA | Hoytdale-McClelland | Circuit Breaker | Construct | EP |  | AF1-146 |  |  | No |  |  | 0 | 12/31/2021 | 12/31/2025
n8168.12 | Not Specified | Backbone Fiber Installation: Install fiber from AF1-146 Interconnection to Monaca - Youngstown - Harmonville Fiber Backbone for communication transport | Network | 345 | 0.12 | 12/31/2021 | ATSI |  |  |  |  | PA | Monaca-Youngstown-Harmonville | Communication Equipment | Install | EP |  | AF1-146 |  |  | No |  |  | 0 | 12/31/2021 | 12/31/2025
n8168.13 | Not Specified | AF1-146 Interconnection to McClelland Fiber Installation: Install fiber from AF1-146 Interconnection to McClelland Substation for communication transport | Network | 345 | 0.17 | 12/31/2021 | ATSI |  |  |  |  | PA | McClelland | Communication Equipment | Install | EP |  | AF1-146 |  |  | No |  |  | 0 | 12/31/2021 | 12/31/2025
n8168.14 | Not Specified | Install fiber from AF1-146 Interconnection to Hoytdale Substation for communication transport | Network | 345 | 0.2 | 12/31/2021 | ATSI |  |  |  |  | PA | Hoytdale | Communication Equipment | Install | EP |  | AF1-146 |  |  | No |  |  | 0 | 12/31/2021 | 12/31/2025
n8168.2 | Not Specified | Review and update relay settings. | Network | 345 | 0.11 | 12/31/2021 | ATSI |  |  |  |  | PA | New Castle | Relay | Modify | EP |  | AF1-146 |  |  | No |  |  | 0 | 12/31/2021 | 12/31/2025
n8168.3 | Not Specified | Review and update relay settings. | Network | 345 | 0.05 | 12/31/2021 | ATSI |  |  |  |  | PA | Niles | Relay | Modify | EP |  | AF1-146 |  |  | No |  |  | 0 | 12/31/2021 | 12/31/2025
n8168.4 | Not Specified | Review and update relay settings. | Network | 345 | 0.05 | 12/31/2021 | ATSI |  |  |  |  | PA | Maple | Wave Trap | Replace | EP |  | AF1-146 |  |  | No |  |  | 0 | 12/31/2021 | 12/31/2025
n8168.5 | Not Specified | Relay setting changes. | Network | 345 | 0.05 | 12/31/2021 | ATSI |  |  |  |  | PA | Shenango | Relay | Modify | EP |  | AF1-146 |  |  | No |  |  | 0 | 12/31/2021 | 12/31/2025
n8168.6 | Not Specified | Review and update relay settings. | Network | 345 | 0.05 | 12/31/2021 | ATSI |  |  |  |  | PA | Bruce | Relay | Modify | EP |  | AF1-146 |  |  | No |  |  | 0 | 12/31/2021 | 12/31/2025
n8168.7 | Not Specified | Review and update relay settings. | Network | 345 | 0.05 | 12/31/2021 | ATSI |  |  |  |  | PA | Hickory | Relay | Modify | EP |  | AF1-146 |  |  | No |  |  | 0 | 12/31/2021 | 12/31/2025
n8168.8 | Not Specified | Review and update relay settings. | Network | 345 | 0.05 | 12/31/2021 | ATSI |  |  |  |  | PA | Cranberry | Relay | Modify | EP |  | AF1-146 |  |  | No |  |  | 0 | 12/31/2021 | 12/31/2025
n8168.9 | Not Specified | Review and update relay settings. | Network | 345 | 0.37 | 12/31/2021 | ATSI |  |  |  |  | PA | McClelland | Relay | Modify | EP |  | AF1-146 |  |  | No |  |  | 0 | 12/31/2021 | 12/31/2025
n8188.1 | Not Specified | Brookville-Squab Hollow 138 kV Line: Loop the Brookville-Squab Hollow 138kV line into the new AE2-316 interconnection sub. | Network | 138 | 1.58 | 12/31/2020 | PENELEC |  |  |  |  | PA | Brookeville - Squab Hollow | Transmission Line | Modify | EP | 1.58 | AE2-316 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 12/31/2020 | 12/31/2025
n8188.2 | Not Specified | Brookville: Install new relays and modify relay settings. | Network | 138 | 0.24 | 12/31/2020 | PENELEC |  |  |  |  | PA | Brookville | Relay | Install | EP | 0.24 | AE2-316 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 12/31/2020 | 12/31/2025
n8188.3 | Not Specified | Armstrong: Install anti-islanding transmitter. | Network | 138 | 0.19 | 12/31/2020 | PENELEC |  |  |  |  | PA | Armstrong | Relay | Install | EP | 0.19 | AE2-316 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 12/31/2020 | 12/31/2025
n8188.4 | Not Specified | Squab Hollow: Install anti-islanding transmitter. | Network | 138 | 0.21 | 12/31/2020 | PENELEC |  |  |  |  | PA | Squab Hollow | Relay | Install | EP | 0.21 | AE2-316 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 12/31/2020 | 12/31/2025
n8188.5 | Not Specified | Install fiber from AE2-316 to Backbone for communication transport. @ AE2-316 Direct Connect – Squab Solar | Network | 138 | 1.11 | 12/31/2020 | PENELEC |  |  |  |  | PA | AE2-316 | Communication Equipment | Install | EP | 1.11 | AE2-316 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 12/31/2020 | 12/31/2025
n8188.6 | Not Specified | SCADA/Fiber Communication: Design, install, and test/commission MPLS Equipment for SCADA transport. | Network | 138 | 0.29 | 12/31/2020 | PENELEC |  |  |  |  | PA | AE2-316 | Communication Equipment | Install | EP | 0.29 | AE2-316 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 12/31/2020 | 12/31/2025
n8220.1 | Not Specified | Complete FRAC-FISH 69 kV line modifications to tie in the new AF2-445A Attachment Facilities. Intersperse a new custom foundation steel tap structure at the POI. Reframe/modify existing structures on each side of the new tap structure if required. | Network | 69 | 0.1 | 6/1/2021 | PPL |  |  |  |  | PA | Fish 69 kV | Transmission Line | Modify | EP |  | AF2-445A |  |  | No |  |  | 0 | 6/1/2021 | 7/25/2024
n8220.2 | Not Specified | Relay Modifications Scope of Work at Frackville Substation | Network | 69 | 0.14 | 6/1/2021 | PPL |  |  |  |  | PA | Frackville | Relay | Modify | EP |  | AF2-445A |  |  | No |  |  | 0 | 6/1/2021 | 7/25/2024
n8228 | Not Specified | Construct one new bay with double bus, single breaker arrangement at the Buxmont Substation spare Bay #12. | Network | 69 | 0.66 | 3/5/2018 | PPL |  |  |  |  | PA | Buxmont | Bus and circuit breakers | Construct | EP |  | AD2-077 |  |  | No |  |  | 0 | 3/5/2018 | 12/1/2027
n8341.1 | Not Specified | Modifications to the Mifflintown Tap 69 kV line to tie in the AF2-361 Attachment Facilities | Network | 69 | 0.1 | 12/31/2022 | PPL |  |  |  |  | PA | Mifflintown | Transmission Line | Modify | EP | 0.1 | AF2-361 | 9/19/2026 |  | No | 1/9/2024 | 1/9/2024 | 0 | 12/31/2022 | 12/31/2025
n8341.2 | Not Specified | Relay Modifications Scope of Work at Juniata Substation | Network | 69 | 0.24 | 12/31/2022 | PPL |  |  |  |  | PA | Juniata | Relay | Modify | EP | 0.24 | AF2-361 | 9/19/2026 |  | No | 1/9/2024 | 1/9/2024 | 0 | 12/31/2022 | 12/31/2025
n8341.3 | Not Specified | Relay Modifications Scope of Work at Dauphin Substation | Network | 69 | 0.24 | 12/31/2022 | PPL |  |  |  |  | PA | Dauphin | Relay | Modify | EP | 0.24 | AF2-361 | 9/19/2026 |  | No | 1/9/2024 | 1/9/2024 | 0 | 12/31/2022 | 12/31/2025
n8370.1 | Not Specified | Tap Cambridge Springs-Corry Central 34.5kV line and convert approximately ¾ of a mile of 12kv to 35kv | Network | 34.5 | 0.42 | 1/1/2023 | PENELEC |  |  |  |  | PA | Tap | Distribution Line | Modify | EP | 0.42 | AF1-094 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 1/1/2023 | 9/15/2026
n8370.2 | Not Specified | Update relay settings on 34.5kV Cambridge Springs line | Network | 34.5 | 0.05 | 1/1/2023 | PENELEC |  |  |  |  | PA | Union City | Relay | Modify | EP | 0.05 | AF1-094 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 1/1/2023 | 9/15/2026
n8370.3 | Not Specified | Installation of (1) 700 MHz radio system to support SCADA Switch | Network | 34.5 | 0.06 | 1/1/2023 | PENELEC |  |  |  |  | PA | Tap | Motor Operated Disconnect Switch | Construct | EP | 0.06 | AF1-094 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 1/1/2023 | 9/15/2026
n8374.1 | Not Specified | Warfordsburg Substation: Replace existing McConnellsburg line relaying with (1) standard line relaying panel with (2) SEL-421 and (1) SEL-501 BFT. | Network | 34.5 | 0.19 | 3/28/2019 | APS |  |  |  |  | PA | Warfordsburg | Relay | Replace | EP | 0.19 | AF1-136 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 3/28/2019 | 8/1/2026
n8374.2 | Not Specified | Warfordsburg – Purcell Jct 34.5 kV Line: Install two main line switches on the existing Warfordsburg – Purcell Jct 34.5 kV line | Network | 34.5 | 0.12 | 3/28/2019 | APS |  |  |  |  | PA | Warfordsburg - Purcell Jct | Distribution Line | Install | EP | 0.12 | AF1-136 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 3/28/2019 | 8/1/2026
n8374.3 | Not Specified | Mercersburg – AD1-061 34.5 kV Tap: Reconductor ~1.6 mi from Mercersburg – AD1-061 (Elk Hill 1) Tap 34.5 kV Line from Mercersburg Substation to Pole PA406-WP47 with 795 ACSR conductor. | Network | 34.5 | 1.32 | 3/28/2019 | APS |  |  |  |  | PA | Mercersburg - AD1-061 Tap | Distribution Line | Reconductor | EP | 1.32 | AF1-136 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 3/28/2019 | 8/1/2026
n8374.4 | Not Specified | Mercersburg Substation: Replace limiting conductors and revise relay settings. | Network | 34.5 | 0.23 | 3/28/2019 | APS |  |  |  |  | PA | Mercersburg | Line and Terminal Equipment | Replace | EP | 0.23 | AF1-136 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 3/28/2019 | 8/1/2026
n8374.5 | Not Specified | McConnellsburg Substation: Revise relay settings. | Network | 34.5 | 0.13 | 3/28/2019 | APS |  |  |  |  | PA | McConnellsburg | Relay | Modify | EP | 0.13 | AF1-136 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 3/28/2019 | 8/1/2026
n8406.1 | Not Specified | Install fiber on Shickshinny-Lackawanna 500 kV line | Network | 500 | 0.08 | 12/15/2022 | PPL |  |  |  |  | PA | Shickshinny and Lackawanna | Communication Equipment | Install | EP |  | AE1-059 |  |  | No |  |  | 0 | 12/15/2022 | 12/15/2023
n8406.2 | Not Specified | Relay modifications at remote end substations Stanton 230 kV and Summit 230 Kv | Network | 230 | 0.12 | 12/15/2022 | PPL |  |  |  |  | PA | Stanton and Summit | Relay | Modify | EP |  | AE1-059 |  |  | No |  |  | 0 | 12/15/2022 | 12/15/2023
n8406.3 | Not Specified | Modifications to existing Summit – Stanton 230 kV line to tie in new AE1-059 interconnection switching station | Network | 230 | 4.58 | 12/15/2022 | PPL |  |  |  |  | PA | Stanton and Summit | Transmission Line | Modify | EP |  | AE1-059 |  |  | No |  |  | 0 | 12/15/2022 | 12/15/2023
n8406.4 | Not Specified | New Interconnection Switching Station on the Stanton – Summit #4 230 kV line | Network | 230 | 18 | 12/15/2022 | PPL |  |  |  |  | PA | Stanton and Summit | Switching | Build | EP |  | AE1-059 |  |  | No |  |  | 0 | 12/15/2022 | 12/15/2023
n8457.1 | Not Specified | AE2-262/AE2-263 Interconnection Sub: Construct a new 230 kV three breaker ring bus looping in the Moshannon-Milesburg 230 kV line to provide interconnection facilities for AE2-262-AE2-263 | Network | 230 | 11.43 | 6/30/2022 | APS |  |  |  |  | PA | AE2-262/AE2-263 Interconnection Sub | Substation | Construct | EP | 11.43 | AE2-262 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 6/30/2022 | 12/31/2026
n8457.2 | Not Specified | AE2-262-AE2-263 Interconnection Sub: Design, install and test/commission MPLS Equipment for SCADA transport at new Interconnection Sub | Network | 230 | 0.24 | 6/30/2022 | APS |  |  |  |  | PA | AE2-262/AE2-263 Interconnection Sub | Communication Equipment | Install | EP | 0.24 | AE2-262 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 6/30/2022 | 12/31/2026
n8457.3 | Not Specified | AE2-262-AE2-263 Interconnection Sub: Install fiber from AE2-262/AE2-263 New Interconnection Substation to fiber backbone for communication transport | Network | 230 | 0.15 | 6/30/2022 | APS |  |  |  |  | PA | AE2-262/AE2-263 Interconnection Sub | Communication Equipment | Install | EP | 0.15 | AE2-262 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 6/30/2022 | 12/31/2026
n8457.4 | Not Specified | Moshannon-Milesburg 230 kV Line:The Moshannon-Milesburg 230 kV line will be cut and looped into the new 230 kV interconnect substation. This cut will take place at a location that is approximately 16.3 miles from the Moshannon substation. | Network | 230 | 1.72 | 6/30/2022 | APS |  |  |  |  | PA | AE2-262/AE2-263 Interconnection Sub | Transmission Line | Modify | EP | 1.72 | AE2-262 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 6/30/2022 | 12/31/2026
n8457.5 | Not Specified | Moshannon: Anti-islanding and carrier equipment will be installed in existing relay panels. Existing Milesburg line relaying will be replaced. | Network | 230 | 0.69 | 6/30/2022 | APS |  |  |  |  | PA | Moshannon | Transmission Line | Modify | EP | 0.69 | AE2-262 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 6/30/2022 | 12/31/2026
n8457.6 | Not Specified | Milesburg: One existing 230 kV CVT, wave trap, line tuner, and circuit breaker will be replaced. Anti-islanding will be installed. Existing Moshannon line relaying panel will be replaced. | Network | 230 | 1.82 | 6/30/2022 | APS |  |  |  |  | PA | Milesburg | Relay | Replace | EP | 1.82 | AE2-262 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 6/30/2022 | 12/31/2026
n8457.7 | Not Specified | Dale Summit: A new carrier relaying panel with anti-islanding will be installed for the Milesburg and Shingletown exits. | Network | 230 | 0.57 | 6/30/2022 | APS |  |  |  |  | PA | Dale Summit | Relay | Replace | EP | 0.57 | AE2-262 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 6/30/2022 | 12/31/2026
n8457.8 | Not Specified | Shingletown: A new carrier relaying panel with anti-islanding will be installed for the Dale Summit exit. | Network | 230 | 0.61 | 6/30/2022 | APS |  |  |  |  | PA | Shingletown | Relay | Replace | EP | 0.61 | AE2-262 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 6/30/2022 | 12/31/2026
n8486.1 | Not Specified | Install physical security devices and other construction work by FirstEnergy at new AE2-139 Interconnection Substation by developer. | Network | 230 | 1.14 |  | MAIT |  |  |  |  | PA | AE2-139 Interconnection Sub | Substation | Install | EP | 1.14 | AE2-139 |  |  | No | 10/8/2024 | 10/8/2024 | 0 |  | 5/31/2027
n8486.2 | Not Specified | Estimated design, installation, and testing/commissioning for MPLS equipment for SCADA transport at AE2-139 230 kV Interconnect Substation. | Network | 230 | 0.24 |  | MAIT |  |  |  |  | PA | AE2-139 Interconnection Sub | Communication Equipment | Install | EP | 0.24 | AE2-139 |  |  | No | 10/8/2024 | 10/8/2024 | 0 |  | 5/31/2027
n8486.3 | Not Specified | Install ADSS from East Towanda 230 kV substation to the new AE2-139 230 kV Interconnection substation. | Network | 230 | 0.44 |  | MAIT |  |  |  |  | PA | AE2-139 Interconnection Sub | Communication Equipment | Install | EP | 0.44 | AE2-139 |  |  | No | 10/8/2024 | 10/8/2024 | 0 |  | 5/31/2027
n8486.4 | Not Specified | East Towanda-Marshall 230 kV: Cut the existing East Towanda – Marshall 230kV line approximately 4 miles from the Scotch Hollow Tap to create a loop into the new 3 breaker ring bus for AE2-139 interconnection. | Network | 230 | 1.56 |  | MAIT |  |  |  |  | PA | AE2-139 Interconnection Sub | Transmission Line | Modify | EP | 1.56 | AE2-139 |  |  | No | 10/8/2024 | 10/8/2024 | 0 |  | 5/31/2027
n8486.5 | Not Specified | Marshall 230 kV Substation: Modify relay settings, drawings review and nameplate. | Network | 230 | 0.07 |  | MAIT |  |  |  |  | PA | Marshall Substation | Relay | Modify | EP | 0.07 | AE2-139 |  |  | No | 10/8/2024 | 10/8/2024 | 0 |  | 5/31/2027
n8486.6 | Not Specified | East Towanda 230 kV Substation: Modify relay settings, drawings review and nameplate. | Network | 230 | 0.07 |  | MAIT |  |  |  |  | PA | East Towanda | Relay | Modify | EP | 0.07 | AE2-139 |  |  | No | 10/8/2024 | 10/8/2024 | 0 |  | 5/31/2027
n8486.7 | Not Specified | Scotch Hollow 230 kV Substation: Modify relay settings, drawings review and nameplate. | Network | 230 | 0.07 |  | MAIT |  |  |  |  | PA | Scotch Hollow | Relay | Modify | EP | 0.07 | AE2-139 |  |  | No | 10/8/2024 | 10/8/2024 | 0 |  | 5/31/2027
n8486.8 | Not Specified | Grover 230 kV Substation: Relay settings, drawings review and nameplate. | Network | 230 | 0.07 |  | MAIT |  |  |  |  | PA | Grover | Relay | Modify | EP | 0.07 | AE2-139 |  |  | No | 10/8/2024 | 10/8/2024 | 0 |  | 5/31/2027
n8489.1 | Not Specified | Replace 34.5kV South Troy line relaying and controls and install (1) 34.5kV PT. | Network | 34.5 | 0.55 |  | PENELEC |  |  |  |  | PA | Mansfield Substation | Relay | Replace | EP | 0.55 | AF2-238 |  |  | No | 10/8/2024 | 10/8/2024 | 0 |  | 7/31/2027
n8489.2 | Not Specified | Revise relay settings at South Troy 34.5 kV substation | Network | 34.5 | 0.06 |  | PENELEC |  |  |  |  | PA | South Troy Substation | Relay | Modify | EP | 0.06 | AF2-238 |  |  | No | 10/8/2024 | 10/8/2024 | 0 |  | 7/31/2027
n8495.2 | Not Specified | Modify Sunbury-Lock Haven 69kV line to tine in the new interconnection facilities | Network | 69 | 0.28 | 1/1/2027 | PPL |  |  |  |  | PA | Sunbury-Lockhaven | Transmission Line | Modify | EP | 0.28 | AF1-333 | 9/30/2027 |  | No | 10/8/2025 | 10/8/2025 | 0 | 1/1/2027
n8495.3 | Not Specified | Modify relays at Lock Haven 69kV Substation | Network | 69 | 0.24 | 1/1/2027 | PPL |  |  |  |  | PA | Lockhaven | Relay | Modify | EP | 0.24 | AF1-333 | 9/30/2027 |  | No | 10/8/2025 | 10/8/2025 | 0 | 1/1/2027
n8495.4 | Not Specified | Modify relays at Sunbury 69kV Substation | Network | 69 | 0.24 | 1/1/2027 | PPL |  |  |  |  | PA | Sunbury | Relay | Modify | EP | 0.24 | AF1-333 | 9/30/2027 |  | No | 10/8/2025 | 10/8/2025 | 0 | 1/1/2027
n8496.1 | Not Specified | Lucerne 115 kV Substation: Convert Lucerne Substation to a four breaker (future six breaker) bus. | Network | 115 | 10.5 |  | MAIT |  |  |  |  | PA | Lucerne | Substation | Modify | EP | 10.5 | AF1-272 |  |  | No | 10/8/2024 | 10/8/2024 | 0 |  | 5/31/2027
n8496.2 | Not Specified | Lucerne-Shelocta 115kV Line: Re-terminate the Lucerne- Shelocta 115kV line to accommodate the new Lucerne 115 kV substation layout | Network | 115 | 0.64 |  | MAIT |  |  |  |  | PA | Lucerne - Shelocta 115 kV Line | Transmission Line | Modify | EP | 0.64 | AF1-272 |  |  | No | 10/8/2024 | 10/8/2024 | 0 |  | 5/31/2027
n8496.3 | Not Specified | East Pike-Lucerne 115 kV Line: Re-terminate the East Pike-Lucerne 115kV line to accommodate the new Lucerne 115 kV substation layout | Network | 115 | 1.03 |  | MAIT |  |  |  |  | PA | East Pike - Lucerne 115 kV line | Transmission Line | Modify | EP | 1.03 | AF1-272 |  |  | No | 10/8/2024 | 10/8/2024 | 0 |  | 5/31/2027
n8496.4 | Not Specified | East Pike 115 kV Substation: Replace (1) 115kV line trap and line tuner with (1) wideband line trap and line tuner for the Glory line terminal | Network | 115 | 0.63 |  | MAIT |  |  |  |  | PA | East Pike | Communication Equipment | Replace | EP | 0.63 | AF1-272 |  |  | No | 10/8/2024 | 10/8/2024 | 0 |  | 5/31/2027
n8496.5 | Not Specified | Glory 115 kV Substation: Replace (1) 115kV line trap and line tuner with (1) wideband line trap and tuner | Network | 115 | 0.64 |  | MAIT |  |  |  |  | PA | Glory | Communication Equipment | Replace | EP | 0.64 | AF1-272 |  |  | No | 10/8/2024 | 10/8/2024 | 0 |  | 5/31/2027
n8496.6 | Not Specified | Shelocta 115 kV: Install (1) PCM 5350 for the Lucerne 115kV line | Network | 115 | 0.46 |  | MAIT |  |  |  |  | PA | Shelocta | Communication Equipment | Install | EP | 0.46 | AF1-272 |  |  | No | 10/8/2024 | 10/8/2024 | 0 |  | 5/31/2027
n8497 | Not Specified | Revise relay settings as needed on 34.5 kV Turner St line. | Network | 34.5 | 0.08 |  | PENELEC |  |  |  |  | PA | Turner Street South | Relay | Modify | EP | 0.08 | AG1-100 | 7/31/2027 |  | No | 10/8/2024 | 10/8/2024 | 0 |  | 8/29/2027
n8502.1 | Not Specified | Review and revise relay settings as needed | Network | 115/34.5 | 0.06 |  | MAIT |  |  |  |  | PA | Rockwood | Relay | Modify | EP | 0.06 | AF1-143 |  |  | No | 10/8/2025 | 10/8/2025 | 0 |  | 12/31/2026
n8502.2 | Not Specified | Review and revise relay settings as needed | Network | 115/34.5 | 0.06 |  | MAIT |  |  |  |  | PA | Bigby | Relay | Modify | EP | 0.06 | AF1-143 |  |  | No | 10/8/2025 | 10/8/2025 | 0 |  | 12/31/2026
n8533.1 | Not Specified | Construct (2) line switches on the Claysburg-Hollidaysburg 46kV line approximately 0.1 miles from Claysburg Substation. | Network | 46 | 0.86 |  | MAIT |  |  |  |  | PA | Claysburg - Hollidaysburg 46 kV Tap | Switch | Construct | EP | 0.86 | AG1-281 |  |  | No | 10/8/2025 | 10/8/2025 | 0 |  | 12/31/2027
n8533.2 | Not Specified | Revise relay settings at Holidaysburg 46kV substation | Network | 46 | 0.05 |  | MAIT |  |  |  |  | PA | Holidaysburg 46 kV | Relays | Modify | EP | 0.05 | AG1-281 |  |  | No | 10/8/2025 | 10/8/2025 | 0 |  | 12/31/2027
n8533.3 | Not Specified | Revise relay settings at Claysburg 46kV substation | Network | 46 | 0.05 |  | MAIT |  |  |  |  | PA | Claysburg 46 kV | Relays | Modify | EP | 0.05 | AG1-281 |  |  | No | 10/8/2025 | 10/8/2025 | 0 |  | 12/31/2027
n8543 | Not Specified | Ronco Substation: Revise Relay Settings | Network | 500 | 0.06 | 10/1/2027 | APS |  |  |  |  | PA | Ronco | Relays | Revise | EP | 0.06 | AF2-029 | 10/1/2027 |  | No | 10/8/2025 | 10/8/2025 | 0 | 10/1/2027 | 10/1/2027
n8544 | Not Specified | Hatfield Substation: Revise Relay Settings | Network | 500 | 0.06 | 10/1/2027 | APS |  |  |  |  | PA | Hatfield | Relays | Revise | EP | 0.06 | AF2-029 | 10/1/2027 |  | No | 10/8/2025 | 10/8/2025 | 0 | 10/1/2027 | 10/1/2027
n8571 | Not Specified | Portland Substation: Relay Setting Changes | Network | 230 | 0.06 | 5/31/2028 | ME |  |  |  |  | PA | Portland | Relays | Revise | EP | 0.06 | AG1-511 | 5/31/2028 |  | No | 10/8/2025 | 10/8/2025 | 0 | 5/31/2028 | 5/31/2028
n8572 | Not Specified | Modify relays at Juniata 69 kV Substation (PJM Network Upgrade Number | Network | 69 | 0.14 | 10/31/2027 | PPL |  |  |  |  | PA | Sunbury-Middleburg | Relays | Modify | EP |  | AF2-233 | 9/30/2026 |  | No |  |  | 0 | 10/31/2027 | 10/31/2027
n8573 | Not Specified | Modify Sunbury-Middleburg #2 69 kV line to tie in the new Transmission Owner Interconnection Facility. | Network | 69 | 0.1 | 10/31/2027 | PPL |  |  |  |  | PA | Sunbury | Transmission Line | Modify | EP |  | AF2-233 | 9/30/2026 |  | No |  |  | 0 | 10/31/2027 | 10/31/2027
n8574 | Not Specified | Modify relays at Sunbury 69 kV Substation (PJM Network Upgrade Number | Network | 69 | 0.14 | 10/31/2027 | PPL |  |  |  |  | PA | Juniata | Relays | Modify | EP |  | AF2-233 | 9/30/2026 |  | No |  |  | 0 | 10/31/2027 | 10/31/2027
n8575 | Not Specified | Modify relays at Juniata 69 kV Substation (PJM Network Upgrade Number | Network | 69 | 0.14 | 11/2/2026 | PPL |  |  |  |  | PA | Sunbury-Middleburg | Relays | Modify | EP |  | AF2-234 | 9/30/2026 |  | No |  |  | 0 | 11/2/2026 | 11/2/2026
n8576 | Not Specified | Modify Sunbury-Middleburg #2 69 kV line to tie in the new Transmission Owner Interconnection Facility. | Network | 69 | 0.1 | 11/2/2026 | PPL |  |  |  |  | PA | Sunbury | Transmission Line | Modify | EP |  | AF2-234 | 9/30/2026 |  | No |  |  | 0 | 11/2/2026 | 11/2/2026
n8577 | Not Specified | Modify relays at Sunbury 69 kV Substation (PJM Network Upgrade Number | Network | 69 | 0.14 | 11/2/2026 | PPL |  |  |  |  | PA | Juniata | Relays | Modify | EP |  | AF2-234 | 9/30/2026 |  | No |  |  | 0 | 11/2/2026 | 11/2/2026
n8581 | Not Specified | Install two SCADA operated switches on the Miller REC - Warrior Ridge 46 kV Line | Network | 46 | 0.61 | 8/1/2027 | PENELEC |  |  |  |  | PA | Miller REC - Warrior Ridge | Switch | Install | EP | 0.61 | AG1-301 |  |  | No | 10/8/2025 | 10/8/2025 | 0 | 8/1/2027
n8582 | Not Specified | Replace line relaying panel at Warrior Ridge substation | Network | 46 | 0.47 | 8/1/2027 | PENELEC |  |  |  |  | PA | Warrior Ridge | Relays | Replace | EP | 0.47 | AG1-301 |  |  | No | 10/8/2025 | 10/8/2025 | 0 | 8/1/2027
n8586 | Not Specified | Roxbury Substation: Install new 23 kV PT on the Arco line. Revise relay settings for new customer tap. Replace existing 23kV KRB ARCO relays with SEL-0351S line panel | Network | 23 | 2.82 | 8/31/2027 | PENELEC |  |  |  |  | PA | Roxbury | Relays | Replace | EP | 2.82 | AF2-229 | 8/31/2027 |  | No | 10/8/2025 | 10/8/2025 | 0 | 8/31/2027 | 8/31/2027
n8615.0 | Not Specified | Modify Blooming Grove-West Damascus 69 kV line to tie in the new Transmission Owner Interconnection Facility. | Network |  | 0.61 |  | PPL |  |  |  |  | PA | Blooming Grove-West Damascus 69 kV | Transmission Line | Modify | EP | 0.61 |  | 12/31/2027 |  | No | 10/8/2025 | 10/8/2025 | 0
n8616.0 | Not Specified | Modify relays at Paupack 69 kV Substation | Network |  | 0.14 |  | PPL |  |  |  |  | PA | Paupack Substation | Relay | Modify | EP | 0.14 |  | 12/31/2027 |  | No | 10/8/2025 | 10/8/2025 | 0
n8617.0 | Not Specified | Modify relays at Blooming Grove 69 kV Substation | Network |  | 0.14 |  | PPL |  |  |  |  | PA | Blooming Grove Substation | Relay | Modify | EP | 0.14 |  | 12/31/2027 |  | No | 10/8/2025 | 10/8/2025 | 0
n8618.0 | Not Specified | Modify Harwood - East Hazelton 69 kV line to tie in the new Transmission Owner Interconnection Facility. | Network |  | 0.61 |  | PPL |  |  |  |  | PA | East Hazelton –Weatherly Tap 69 kV | Transmission Line | Modify | EP | 0.61 |  | 3/1/2027 |  | No | 10/8/2025 | 10/8/2025 | 0
n8619.0 | Not Specified | Modify relays at Harwood 69 kV Substation | Network |  | 0.14 |  | PPL |  |  |  |  | PA | Harwood | Relay | Modify | EP | 0.14 |  | 3/1/2027 |  | No | 10/8/2025 | 10/8/2025 | 0
n8634.0 | Not Specified | Modify Scott Tap - Bowmans Mill Tap 69 kV line to tie in the new Transmission Owner Interconnection Facility. | Network |  | 0.1 |  | PPL |  |  |  |  | PA | Scott Tap - Bowmans Mill Tap | Transmission Line | Modify | EP | 0.1 | AF2-086 | 12/31/2027 |  | No | 10/8/2025 | 10/8/2025 | 0
n8635.0 | Not Specified | Modify relays at Columbia 69 kV Substation | Network |  | 0.14 |  | PPL |  |  |  |  | PA | Columbia Substation | Relay | Modify | EP | 0.14 | AF2-086 | 12/31/2027 |  | No | 10/8/2025 | 10/8/2025 | 0
n8636.0 | Not Specified | Modify relays at Glen Brook 69 kV Substation | Network |  | 0.14 |  | PPL |  |  |  |  | PA | Glen Brook Substation | Relay | Modify | EP | 0.14 | AF2-086 | 12/31/2027 |  | No | 10/8/2025 | 10/8/2025 | 0
n8691.0 | Not Specified | Modify Sunbury – Columbia 69 kV line to tie in the new Transmission Owner Interconnection Facility. | Network | 69 | 0.8 | 5/1/2027 | PPL |  |  |  |  | PA | Sunbury - Columbia 69 kV | Line and Terminal Equipment | Install | EP | 0.8 | AF2-433 | 10/30/2026 |  | No | 10/8/2025 | 10/8/2025 | 0 | 12/31/2027
n8692.0 | Not Specified | Modify relays at Columbia 69 kV Substation | Network | 69 | 0.14 | 12/31/2027 | PPL |  |  |  |  | PA | Columbia 69 kV | Relay | Configure | EP | 0.14 | AF2-433 | 10/30/2026 |  | No | 10/8/2025 | 10/8/2025 | 0 | 12/31/2027
n8693.0 | Not Specified | Relay modifications at Sunbury 69 kV substation | Network | 69 | 0.14 | 12/31/2027 | PPL |  |  |  |  | PA | Sunbury 69 kV | Relay | Configure | EP | 0.14 | AF2-433 | 10/30/2026 |  | No | 10/8/2025 | 10/8/2025 | 0 | 12/31/2027
n8699.0 | Not Specified | Install security fence at AE2-316/AF1-302 interconnection substation. | Network | 138 | 1.16 | 2/28/2026 | PENELEC |  |  |  |  | PA | AE2-316/AF1-302 Interconnection Substation | Substation | Install | EP |  | AE2-316 | 2/28/2026 |  | No |  |  | 0 | 2/28/2026
n8700.0 | Not Specified | Revise relay settings at Brookvile substation for PJM Project Identifier AF1-302 | Network | 138 | 0.07 | 2/28/2026 | PENELEC |  |  |  |  | PA | Brookville | Relay | Revise | EP |  | AF1-302 | 2/28/2026 |  | No |  |  | 0 | 2/28/2026
n8701.0 | Not Specified | Revise relay settings at AE2-316/AF1-302 interconnection substation for PJM Project Identifier AF1-302 | Network | 138 | 0.07 | 2/28/2026 | PENELEC |  |  |  |  | PA | AE2-316/AF1-302 Interconnection Substation | Relay | Revise | EP |  | AF1-302 | 2/28/2026 |  | No |  |  | 0 | 2/28/2026
n8702.0 | Not Specified | Revise relay settings at Squab Hollow substation for PJM Project Identifier AF1-302 | Network | 138 | 0.07 | 2/28/2026 | APS |  |  |  |  | PA | Squab Hollow | Relay | Revise | EP |  | AF1-302 | 2/28/2026 |  | No |  |  | 0 | 2/28/2026
n8729.0 | Not Specified | TO construction scope of work at AG1-054 substation (includes security systems) | Network | 69 | 1.33 | 3/31/2026 | ATSI |  |  |  |  | PA | Volant | Substation | Install | EP | 1.33 | AG1-054 | 3/31/2026 |  | No | 10/8/2025 | 10/8/2025 | 0 | 3/31/2026
n8730.0 | Not Specified | Design, install, and test/commission Multi-Protocol Label Switching (MPLS) equipment for Supervisory Control and Data Acquisition (SCADA) transport at AG1-054 interconnection substation | Network | 69 | 0.31 | 3/31/2026 | ATSI |  |  |  |  | PA | Volant | Communication Equipment | Install | EP | 0.31 | AG1-054 | 3/31/2026 |  | No | 10/8/2025 | 10/8/2025 | 0 | 3/31/2026
n8731.0 | Not Specified | Install 3.44 miles of ADSS to nearest splice point of OPGW on existing Campbell – Cedar Street line. | Network | 69 | 1.33 | 3/31/2026 | ATSI |  |  |  |  | PA | Volant | Cable | Install | EP | 1.33 | AG1-054 | 3/31/2026 |  | No | 10/8/2025 | 10/8/2025 | 0 | 3/31/2026
n8732.0 | Not Specified | Loop the Campbell to Cedar Street 69 kV line into new interconnection substation approximately 10.2 miles from Campbell substation (between Potter and Harlan substations) | Network | 69 | 0.77 | 3/31/2026 | ATSI |  |  |  |  | PA | Volant | Transmission Line | Install | EP | 0.77 | AG1-054 | 3/31/2026 |  | No | 10/8/2025 | 10/8/2025 | 0 | 3/31/2026
n8733.0 | Not Specified | Frew Mill Substation – update drawings and nameplates for line name change | Network | 69 | 0.03 | 3/31/2026 | ATSI |  |  |  |  | PA | Volant | Substation | Install | EP | 0.03 | AG1-054 | 3/31/2026 |  | No | 10/8/2025 | 10/8/2025 | 0 | 3/31/2026
n8734.0 | Not Specified | Potter Substation – update drawings and nameplates for line name change | Network | 69 | 0.03 | 3/31/2026 | ATSI |  |  |  |  | PA | Volant | Substation | Install | EP | 0.03 | AG1-054 | 3/31/2026 |  | No | 10/8/2025 | 10/8/2025 | 0 | 3/31/2026
n8735.0 | Not Specified | Willowbrook Substation – update drawings and nameplates for line name change | Network | 69 | 0.03 | 3/31/2026 | ATSI |  |  |  |  | PA | Volant | Substation | Install | EP | 0.03 | AG1-054 | 3/31/2026 |  | No | 10/8/2025 | 10/8/2025 | 0 | 3/31/2026
n8736.0 | Not Specified | Harlan Substation - update drawings and nameplates for line name change | Network | 69 | 0.03 | 3/31/2026 | ATSI |  |  |  |  | PA | Volant | Substation | Install | EP | 0.03 | AG1-054 | 3/31/2026 |  | No | 10/8/2025 | 10/8/2025 | 0 | 3/31/2026
n8737.0 | Not Specified | Leesburg Substation - update drawings and nameplates for line name change | Network | 69 | 0.03 | 3/31/2026 | ATSI |  |  |  |  | PA | Volant | Substation | Install | EP | 0.03 | AG1-054 | 3/31/2026 |  | No | 10/8/2025 | 10/8/2025 | 0 | 3/31/2026
n8738.0 | Not Specified | Veterans Substation - update drawings and nameplates for line name change | Network | 69 | 0.03 | 3/31/2026 | ATSI |  |  |  |  | PA | Volant | Substation | Install | EP | 0.03 | AG1-054 | 3/31/2026 |  | No | 10/8/2025 | 10/8/2025 | 0 | 3/31/2026
n8739.0 | Not Specified | Frisco Substation – review and update relay settings | Network | 69 | 0.05 | 3/31/2026 | ATSI |  |  |  |  | PA | Volant | Relay | Install | EP | 0.05 | AG1-054 | 3/31/2026 |  | No | 10/8/2025 | 10/8/2025 | 0 | 3/31/2026
n8740.0 | Not Specified | McDowell Substation – review and update relay settings | Network | 69 | 0.05 | 3/31/2026 | ATSI |  |  |  |  | PA | Volant | Relay | Install | EP | 0.05 | AG1-054 | 3/31/2026 |  | No | 10/8/2025 | 10/8/2025 | 0 | 3/31/2026
n8741.0 | Not Specified | New Castle Substation – review and update relay settings | Network | 69 | 0.05 | 3/31/2026 | ATSI |  |  |  |  | PA | Volant | Relay | Install | EP | 0.05 | AG1-054 | 3/31/2026 |  | No | 10/8/2025 | 10/8/2025 | 0 | 3/31/2026
n8742.0 | Not Specified | Masury Substation – review and update relay settings | Network | 69 | 0.05 | 3/31/2026 | ATSI |  |  |  |  | PA | Volant | Relay | Install | EP | 0.05 | AG1-054 | 3/31/2026 |  | No | 10/8/2025 | 10/8/2025 | 0 | 3/31/2026
n8743.0 | Not Specified | Columbiana Substation – review and update relay settings | Network | 69 | 0.05 | 3/31/2026 | ATSI |  |  |  |  | PA | Volant | Relay | Install | EP | 0.05 | AG1-054 | 3/31/2026 |  | No | 10/8/2025 | 10/8/2025 | 0 | 3/31/2026
n8744.0 | Not Specified | Lowellville Substation – review and update relay settings | Network | 69 | 0.05 | 3/31/2026 | ATSI |  |  |  |  | PA | Volant | Relay | Install | EP | 0.05 | AG1-054 | 3/31/2026 |  | No | 10/8/2025 | 10/8/2025 | 0 | 3/31/2026
n8745.0 | Not Specified | Cedar Street Substation – Update drawings and nameplates for line name change. Review and update relay settings. Convert primary and back up relays to POTT over fiber with step distance | Network | 69 | 0.07 | 3/31/2026 | ATSI |  |  |  |  | PA | Volant | Relay | Install | EP | 0.07 | AG1-054 | 3/31/2026 |  | No | 10/8/2025 | 10/8/2025 | 0 | 3/31/2026
n8746.0 | Not Specified | Campbell Substation – Update drawings and nameplates for line name change. Review and update relay settings. Convert primary and back up relays to POTT over fiber with step distance. | Network | 69 | 0.07 | 3/31/2026 | ATSI |  |  |  |  | PA | Volant | Relay | Install | EP | 0.07 | AG1-054 | 3/31/2026 |  | No | 10/8/2025 | 10/8/2025 | 0 | 3/31/2026
n8747.0 | Not Specified | Keisters Substation – review and update relay settings | Network | 69 | 0.05 | 3/31/2026 | APS |  |  |  |  | PA | Volant | Relay | Install | EP | 0.05 | AG1-054 | 3/31/2026 |  | No | 10/8/2025 | 10/8/2025 | 0 | 3/31/2026
n8749.0 | Not Specified | Revise relay settings at Harwick Substation | Network | 138 | 0.06 | 6/1/2027 | APS |  |  |  |  | PA | Harwick Substation | Relay | Revise | EP | 0.06 | AG1-514 | 6/1/2027 |  | No | 10/8/2025 | 10/8/2025 | 0 | 6/1/2027
n8750.0 | Not Specified | Revise relay settings at Yukon Substation | Network | 138 | 0.06 | 6/1/2027 | APS |  |  |  |  | PA | Yukon Substation | Relay | Revise | EP | 0.06 | AG1-514 | 6/1/2027 |  | No | 10/8/2025 | 10/8/2025 | 0 | 6/1/2027
n8751.0 | Not Specified | Revise relay settings at Brackenridge Substation | Network | 138 | 0.06 | 6/1/2027 | APS |  |  |  |  | PA | Brackenridge Substation | Relay | Revise | EP | 0.06 | AG1-514 | 6/1/2027 |  | No | 10/8/2025 | 10/8/2025 | 0 | 6/1/2027
n8752.0 | Not Specified | Revise relay settings at Huntingdon Substation | Network | 138 | 0.06 | 6/1/2027 | APS |  |  |  |  | PA | Huntingdon Substation | Relay | Revise | EP | 0.06 | AG1-514 | 6/1/2027 |  | No | 10/8/2025 | 10/8/2025 | 0 | 6/1/2027
n8753.0 | Not Specified | Revise relay settings at Pittsburgh Mills Substation | Network | 138 | 0.06 | 6/1/2027 | APS |  |  |  |  | PA | Pittsburgh Mills Substation | Relay | Revise | EP | 0.06 | AG1-514 | 6/1/2027 |  | No | 10/8/2025 | 10/8/2025 | 0 | 6/1/2027
n8754.0 | Not Specified | Revise relay settings at White Valley Substation | Network | 138 | 0.06 | 6/1/2027 | APS |  |  |  |  | PA | White Valley Substation | Relay | Revise | EP | 0.06 | AG1-514 | 6/1/2027 |  | No | 10/8/2025 | 10/8/2025 | 0 | 6/1/2027
n8755.0 | Not Specified | Revise relay settings at All Dam 6 Substation | Network | 138 | 0.06 | 6/1/2027 | APS |  |  |  |  | PA | All Dam 6 Substation | Relay | Revise | EP | 0.06 | AG1-514 | 6/1/2027 |  | No | 10/8/2025 | 10/8/2025 | 0 | 6/1/2027
n8756.0 | Not Specified | Revise relay settings at Shaffers Corner Substation | Network | 138 | 0.06 | 6/1/2027 | APS |  |  |  |  | PA | Shaffers Corner Substation | Relay | Revise | EP | 0.06 | AG1-514 | 6/1/2027 |  | No | 10/8/2025 | 10/8/2025 | 0 | 6/1/2027
n8757.0 | Not Specified | Revise relay settings at Springdale Substation | Network | 138 | 0.06 | 6/1/2027 | APS |  |  |  |  | PA | Springdale Substation | Relay | Revise | EP | 0.06 | AG1-514 | 6/1/2027 |  | No | 10/8/2025 | 10/8/2025 | 0 | 6/1/2027
n8758.0 | Not Specified | Revise relay settings at Cheswick Substation | Network | 138 | 0.05 | 6/1/2027 | Duquesne Light (DL) |  |  |  |  | PA | Cheswick Substation | Relay | Revise | EP | 0.05 | AG1-514 | 6/1/2027 |  | No | 10/8/2025 | 10/8/2025 | 0 | 6/1/2027
n8759.0 | Not Specified | Revise relay settings at Plum Substation | Network | 138 | 0.05 | 6/1/2027 | Duquesne Light (DL) |  |  |  |  | PA | Plum Substation | Relay | Revise | EP | 0.05 | AG1-514 | 6/1/2027 |  | No | 10/8/2025 | 10/8/2025 | 0 | 6/1/2027
n8791.0 | Not Specified | Modify Blooming East Palmerton - Acahela 69 kV line to tie in the new Transmission Owner Interconnection Facility. | Network | 69 | 0.9 | 12/31/2027 | PPL |  |  |  |  | PA | East Palmerton - Acahela 69 kV | Transmission Line | Modify | EP | 0.9 | AG1-156 | 12/31/2027 |  | No | 10/8/2025 | 10/8/2025 | 0
n8792.0 | Not Specified | Modify relays at Acahela 69 kV Substation | Network | 69 | 0.14 | 12/31/2027 | PPL |  |  |  |  | PA | Acahela Substation | Relay | Modify | EP | 0.14 | AG1-156 | 12/31/2027 |  | No | 10/8/2025 | 10/8/2025 | 0
n8793.0 | Not Specified | Modify relays at East Palmerton 69 kV Substation | Network | 69 | 0.14 | 12/31/2027 | PPL |  |  |  |  | PA | East Palmerton Substation | Relay | Modify | EP | 0.14 | AG1-156 | 12/31/2027 |  | No | 10/8/2025 | 10/8/2025 | 0
n8870.0 | Not Specified | Review and update relay settings for Ontelaunee Substation | Network | 230 | 0.05 | 11/30/2027 | ME |  |  |  |  | PA | Ontelaunee | Relays | Update | EP | 0.05 | AF2-030 | 11/30/2027 |  | No | 10/8/2025 | 10/8/2025 | 0 | 11/30/2027
n8912.0 | Not Specified | Modify Reed Tap#1 line to tie in the new Transmission Owner Interconnection Facility. | Network |  | 0.07 | 12/31/2027 | PPL |  |  |  |  | PA | Reed Tap #1 | Transmission Line | Modify | EP |  | AF2-424 | 11/2/2026 |  | No |  |  | 0
n8913.0 | Not Specified | Modify relays at Eldred 69 kV Substation | Network |  | 0.14 | 12/31/2027 | PPL |  |  |  |  | PA | Eldred | Relay | Modify | EP |  | AF2-424 | 11/2/2026 |  | No |  |  | 0
n8914.0 | Not Specified | Modify relays at Sunbury 69 kV Substation | Network |  | 0.14 | 12/31/2027 | PPL |  |  |  |  | PA | Sunbury | Relay | Modify | EP |  | AF2-424 | 11/2/2026 |  | No |  |  | 0
n8915.0 | Not Specified | Modify Sunbury-Dauphin 69 kV line to tie in the new Transmission Owner Interconnection Facility. | Network |  | 0.9 | 12/31/2027 | PPL |  |  |  |  | PA | Sunbury-Dauphin 69 kV | Transmission Line | Modify | EP | 0.9 | AG1-259 | 12/31/2027 |  | No | 10/8/2025 | 10/8/2025 | 0
n8916.0 | Not Specified | Modify relays at Sunbury 69 kV Substation | Network |  | 0.14 | 12/31/2027 | PPL |  |  |  |  | PA | Sunbury | Relay | Modify | EP | 0.14 | AG1-259 | 12/31/2027 |  | No | 10/8/2025 | 10/8/2025 | 0
n8917.0 | Not Specified | Modify relays at Dauphin 69 kV Substation | Network |  | 0.14 | 12/31/2027 | PPL |  |  |  |  | PA | Dauphin | Relay | Modify | EP | 0.14 | AG1-259 | 12/31/2027 |  | No | 10/8/2025 | 10/8/2025 | 0
n8962.0 | Not Specified | Review and revise relay settings as required | Network | 115 | 0.06 | 12/31/2027 | MAIT |  |  |  |  | PA | Orrtanna 115 kV Substation | Relays | Revise | EP | 0.06 | AG1-486 | 12/31/2027 |  | No | 10/8/2025 | 10/8/2025 | 0 | 12/31/2027
n9316.0 | Not Specified | Change relay settings at the Maysville Substation | Network |  | 0.06 |  | ATSI |  |  |  |  | PA | Maysville 69kV Substation | Relay | Modify | EP | 0.06 | AE1-183 | 12/8/2020 |  | No | 10/8/2025 | 10/8/2025 | 0
n9317.0 | Not Specified | Change relay settings at the McDowell Substation | Network |  | 0.05 |  | ATSI |  |  |  |  | PA | McDowell 69kV Substation | Relay | Modify | EP | 0.05 | AE1-183 | 12/8/2020 |  | No | 10/8/2025 | 10/8/2025 | 0
n9318.0 | Not Specified | Change relay setting at the Cedar Street Substation | Network |  | 0.05 |  | ATSI |  |  |  |  | PA | Cedar Street 69kV Substation | Relay | Modify | EP | 0.05 | AE1-183 | 12/8/2020 |  | No | 10/8/2025 | 10/8/2025 | 0
n9319.0 | Not Specified | Change relay settings at the Campbell Substation | Network |  | 0.05 |  | ATSI |  |  |  |  | PA | Campbell 69kV Substation | Relay | Modify | EP | 0.05 | AE1-183 | 12/8/2020 |  | No | 10/8/2025 | 10/8/2025 | 0
n9320.0 | Not Specified | Change relay settings at the Sharon Substation | Network |  | 0.05 |  | ATSI |  |  |  |  | PA | Sharon 69kV Substation | Relay | Modify | EP | 0.05 | AE1-183 | 12/8/2020 |  | No | 10/8/2025 | 10/8/2025 | 0
n9321.0 | Not Specified | Change relay settings at the Dillworth Substation | Network |  | 0.05 |  | ATSI |  |  |  |  | PA | Dillworth 69kV Substation | Relay | Modify | EP | 0.05 | AE1-183 | 12/8/2020 |  | No | 10/8/2025 | 10/8/2025 | 0
s0275 | PJM MA | Rebuild Whitpain – Buxmont 230 kV line | Supplemental | 230 | 12.53 |  | PPL |  |  |  |  | PA | Whitpain/Buxmont | Transmission Line | Rebuild | EP | 15 | Equipment Material Condition, Performance and Risk | 12/31/2027 |  | No | 3/10/2011 | 3/10/2011 | 10
s0337 | PJM MA | East Tannersville Substation: new 138 kV tap to new substation | Supplemental | 138 | 2.4 |  | PPL |  |  |  |  | PA | East Tannersville | Transmission Line | Build | EP | 0.7 | Customer Service | 12/15/2030 |  | No | 10/27/2011 | 10/27/2011 | 0
s0527 | PJM MA | Build a new Good Hope 69/12 kV substation by tapping the Cumberland - West Shore #1 69 kV line | Supplemental | 69/12 | 0.45 |  | PPL |  |  |  |  | PA | Good Hope | Substation | Build | EP | 0.45 | Customer Service | 12/15/2033 |  | No | 3/1/2013 | 3/1/2013 | 0
s0866 | PJM MA | Build a new 230 kV circuit from Martins Creek to Monroe using existing Martins Creek-Stroudsburg 69 kV decommissioned line, and reconfigure Martins Creek and Monroe substations | Supplemental | 230 | 44.86 |  | PPL |  |  |  |  | PA | Martins Creek - Monroe | Transmission Line | Build | EP | 44.86 | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 12/15/2028 |  | No | 1/7/2015 | 1/7/2015 | 10
s0867 | PJM MA | Rebuild existing Dauphin 230-69 kV to new design standard | Supplemental | 230/69 | 33 |  | PPL |  |  |  |  | PA | Dauphin | Substation | Rebuild | EP | 33 | Equipment Material Condition, Performance and Risk | 6/30/2027 |  | No | 12/8/2014 | 12/8/2014 | 10
s0867.1 | PJM MA | Replace structure 1087-3 with new steel pole dead-end structure outside PPL Dauphin Substation | Supplemental | 230 | 1.1 |  | ME |  |  |  |  | PA | Dauphin | Substation | Replace | EP | 1.1 | Equipment Material Condition, Performance and Risk | 12/31/2026 |  | No | 2/4/2025 | 2/4/2025 | 0
s0945.7 | PJM MA | Rebuild the Cumberland - West Shore 3 & 4 69 kV (5 mi) | Supplemental | 69 | 1.2 |  | PPL |  |  |  |  | PA | Cumberland - West Shore | Transmission Line | Rebuild | EP | 1.2 | Equipment Material Condition, Performance and Risk,Infrastructure Resilience | 12/15/2034 |  | No | 7/29/2015 | 7/29/2015 | 10
s0945.8 | PJM MA | Rebuild the Juniata - Cumberland 230 kV Line (14.2 mi) | Supplemental | 230 | 30.6 |  | PPL |  |  |  |  | PA | Juniata - Cumberland | Transmission Line | Rebuild | EP | 30.6 | Equipment Material Condition, Performance and Risk,Infrastructure Resilience | 12/15/2034 |  | No | 8/13/2015 | 8/13/2015 | 10
s0946 | PJM MA | Rebuild the Dauphin-Copperstone 1 & 2 69 kV lines (6.2 mi) | Supplemental | 69 | 8.5 |  | PPL |  |  |  |  | PA | Dauphin - Copperstone | Transmission Line | Rebuild | EP | 8.5 | Equipment Material Condition, Performance and Risk | 12/2/2030 |  | No | 7/29/2015 | 7/29/2015 | 25
s0947.2 | PJM MA | Rebuild Harrisburg - Capital Park 1 & 2 69 kV lines (1 mi) | Supplemental | 69 | 1.5 |  | PPL |  |  |  |  | PA | Harrisburg - Capital Park | Transmission Line | Rebuild | EP | 1.5 | Equipment Material Condition, Performance and Risk,Infrastructure Resilience | 12/31/2026 |  | No | 7/29/2015 | 7/29/2015 | 25
s0948.1 | PJM MA | Rebuild Hummelstown - Middletown Junction #1 230 kV line (7 mi) | Supplemental | 230 | 19 |  | PPL |  |  |  |  | PA | Hummelstown - Middletown Junction | Transmission Line | Rebuild | EP | 19 | Equipment Material Condition, Performance and Risk | 12/15/2033 |  | No | 8/13/2015 | 8/13/2015 | 10
s0948.2 | PJM MA | Rebuild Hummelstown - Steelton 230 kV line (6.8 mi) | Supplemental | 230 | 18 |  | PPL |  |  |  |  | PA | Hummelstown - Steelton | Transmission Line | Rebuild | EP | 18 | Equipment Material Condition, Performance and Risk,Infrastructure Resilience | 12/31/2033 |  | No | 8/13/2015 | 8/13/2015 | 0
s0949.4 | PJM MA | Build new Lauschtown - Wyomissing 69 kV line (14 mi) | Supplemental | 69 | 30 |  | PPL |  |  |  |  | PA | Lauschtown - Wyomissing | Transmission Line | Build | EP | 30 | Infrastructure Resilience | 12/15/2033 |  | No | 7/29/2015 | 7/29/2015 | 0
s0949.5 | PJM MA | Rebuild Berks 230/69 kV Substation | Supplemental | 230/69 | 30 |  | PPL |  |  |  |  | PA | Berks | Substation | Rebuild | EP | 30 | Infrastructure Resilience | 12/1/2029 |  | No | 7/29/2015 | 7/29/2015 | 10
s0951.2 | PJM MA | Rebuild Brunner Island - South Manheim 230 kV (17.8 mi) | Supplemental | 230 | 31 |  | PPL |  |  |  |  | PA | Brunner Island - South Manheim | Transmission Line | Rebuild | EP | 31 | Equipment Material Condition, Performance and Risk,Infrastructure Resilience | 12/15/2033 |  | No | 8/13/2015 | 8/13/2015 | 0
s0951.4 | PJM MA | Rebuild South Manheim 230 kV yard | Supplemental | 230 | 19 |  | PPL |  |  |  |  | PA | South Manheim | Substation | Rebuild | EP | 19 | Infrastructure Resilience | 12/31/2030 |  | No | 8/13/2015 | 8/13/2015 | 25
s0952.2 | PJM MA | Rebuild South Manheim 69 kV Yard | Supplemental | 69 | 8 |  | PPL |  |  |  |  | PA | South Manheim | Substation | Rebuild | EP | 8 | Infrastructure Resilience | 6/15/2027 |  | No | 7/29/2015 | 7/29/2015 | 20
s0953.1 | PJM MA | Rebuild McGovernville 69 kV Tap (1.2 mi) | Supplemental | 69 | 2.7 |  | PPL |  |  |  |  | PA | McGovernville | Substation | Rebuild | EP | 2.7 | Equipment Material Condition, Performance and Risk,Infrastructure Resilience | 3/2/2029 |  | No | 7/29/2015 | 7/29/2015 | 20
s0953.2 | PJM MA | Rebuild West Hempfield - South Manheim 69 kV Line between McGovernville and Silver Springs (4.4 mi) | Supplemental | 69 | 10.9 |  | PPL |  |  |  |  | PA | West Hempfield - South Manheim | Transmission Line | Rebuild | EP | 10.9 | Equipment Material Condition, Performance and Risk,Infrastructure Resilience | 9/2/2030 |  | No | 7/29/2015 | 7/29/2015 | 10
s0953.3 | PJM MA | Rebuild West Hempfield - South Manheim 69 kV Line between West Hempfield and Silver Springs (4.9 mi) | Supplemental | 69 | 10.9 |  | PPL |  |  |  |  | PA | West Hempfield - South Manheim | Transmission Line | Rebuild | EP | 10.9 | Equipment Material Condition, Performance and Risk,Infrastructure Resilience | 11/2/2030 |  | No | 7/29/2015 | 7/29/2015 | 10
s0953.4 | PJM MA | Rebuild Donegal 1 & 2 – Landisville 69 kV Tap (4.9 mi) | Supplemental | 69 | 10.9 |  | PPL |  |  |  |  | PA | Donegal - Landisville | Transmission Line | Rebuild | EP | 10.9 | Equipment Material Condition, Performance and Risk,Infrastructure Resilience | 9/1/2033 |  | No | 7/29/2015 | 7/29/2015 | 10
s0954.1 | PJM MA | Rebuild South Akron - Morgantown 1 69 kV line (1.2 mi) | Supplemental | 69 | 2.7 |  | PPL |  |  |  |  | PA | South Akron - Morgantown | Transmission Line | Rebuild | EP | 2.7 | Infrastructure Resilience | 2/2/2029 |  | No | 7/29/2015 | 7/29/2015 | 10
s0954.2 | PJM MA | Rebuild South Akron - Morgantown 3 69 kV line (7.5 mi) | Supplemental | 69 | 14.9 |  | PPL |  |  |  |  | PA | South Akron - Morgantown | Transmission Line | Rebuild | EP | 14.9 | Infrastructure Resilience | 12/1/2029 |  | No | 7/29/2015 | 7/29/2015 | 10
s0954.3 | PJM MA | Rebuild Ephrata 69 kV Tap (1.9 mi) | Supplemental | 69 | 4.4 |  | PPL |  |  |  |  | PA | Ephrata | Substation | Rebuild | EP | 4.4 | Infrastructure Resilience | 12/15/2029 |  | No | 7/29/2015 | 7/29/2015 | 20
s0954.4 | PJM MA | Rebuild South Akron 230/69 kV Substation | Supplemental | 230/69 | 32.5 |  | PPL |  |  |  |  | PA | South Akron | Substation | Rebuild | EP | 32.5 | Infrastructure Resilience | 12/31/2028 |  | No | 7/29/2015 | 7/29/2015 | 10
s0954.5 | PJM MA | Rebuild South Akron - South Manheim 3 69 kV line(9.5 mi) | Supplemental | 69 | 23 |  | PPL |  |  |  |  | PA | South Akron - South Manheim | Transmission Line | Rebuild | EP | 23 | Infrastructure Resilience | 11/30/2026 |  | No | 7/29/2015 | 7/29/2015 | 10
s0955.5 | PJM MA | Rebuild West Hempfield - Manor 2 230 kV line (9.1 mi) | Supplemental | 230 | 22.7 |  | PPL |  |  |  |  | PA | West Hempfield - Manor | Transmission Line | Rebuild | EP | 22.7 | Equipment Material Condition, Performance and Risk,Infrastructure Resilience | 12/15/2033 |  | No | 8/13/2015 | 8/13/2015 | 0
s0955.6 | PJM MA | Rebuild Manor - Otter Creek 230 kV line (5.9 mi) | Supplemental | 230 | 5.4 |  | PPL |  |  |  |  | PA | Manor - Otter Creek | Transmission Line | Rebuild | EP | 5.4 | Equipment Material Condition, Performance and Risk,Infrastructure Resilience | 12/15/2034 |  | No | 8/13/2015 | 8/13/2015 | 0
s0956.2 | PJM MA | Rebuild Engleside - Greenland 1 & 2 69 kV line (1.7 mi) | Supplemental | 69 | 4.1 |  | PPL |  |  |  |  | PA | Engleside - Greenland | Transmission Line | Rebuild | EP | 4.1 | Equipment Material Condition, Performance and Risk | 12/31/2027 |  | No | 7/29/2015 | 7/29/2015 | 15
s0958.2 | PJM MA | Rebuild the Siegfried - Nazareth #1 and #2 69 kV lines (11 mi) | Supplemental | 69 | 25 |  | PPL |  |  |  |  | PA | Siegfried - Nazareth | Transmission Line | Rebuild | EP | 25 | Equipment Material Condition, Performance and Risk | 11/6/2026 |  | No | 7/29/2015 | 7/29/2015 | 10
s0965.7 | PJM MA | Rebuild the Eldred 230 kV Yard | Supplemental | 230 | 9.1 |  | PPL |  |  |  |  | PA | Eldred | Substation | Rebuild | EP | 9.1 | Infrastructure Resilience | 10/31/2028 |  | No | 8/13/2015 | 8/13/2015 | 0
s0966.2 | PJM MA | Build a new Humboldt Loop 69 kV (2.5 mi) | Supplemental | 69 | 6.3 |  | PPL |  |  |  |  | PA | Humboldt Loop | Conductor | Build | EP | 6.3 | Infrastructure Resilience | 1/1/2030 |  | No | 7/29/2015 | 7/29/2015 | 10
s0968.5 | PJM MA | Rebuild the Sunbury - Lewisburg 69kV Line (8.8 mi) | Supplemental | 69 | 15.6 |  | PPL |  |  |  |  | PA | Sunbury - Lewisburg | Transmission Line | Rebuild | EP | 15.6 | Operational Flexibility and Efficiency | 10/15/2026 |  | No | 7/29/2015 | 7/29/2015 | 25
s0974.4 | PJM MA | Extend Keyser Avenue tap line (2 mi) | Supplemental | 69 | 7.8 |  | PPL |  |  |  |  | PA | Keyser Avenue Tap | Transmission Line | Extend | EP | 7.8 | Operational Flexibility and Efficiency,Infrastructure Resilience | 10/31/2033 |  | No | 7/29/2015 | 7/29/2015 | 25
s0975 | PJM MA | Rebuild Stanton 230/69 kV substation | Supplemental | 230/69 | 52.2 |  | PPL |  |  |  |  | PA | Stanton | Substation | Rebuild | EP | 52.2 | Equipment Material Condition, Performance and Risk,Infrastructure Resilience | 10/25/2034 |  | No | 7/29/2015 | 7/29/2015 | 10
s1030 | PJM MA | Build new D/C tap to Shillington from the new Lauschtown -Wyomissing #1 & #2 69kV lines (Approximately 2 Miles) | Supplemental | 69 | 4.9 |  | PPL |  |  |  |  | PA | Shillington, Lauschtown - Wyomissing | Transmission Line | Build | EP | 4.9 | Infrastructure Resilience | 12/15/2033 |  | No | 12/8/2015 | 12/8/2015 | 10
s1098.1 | PJM MA | Montour - Build Bay 5 and 6 to standard breaker and a half configuration and Re-terminate the MONT-SU10 230kV Line into Bay 5 and the MONT-SUSQ 230kV Line into Bay 6. | Supplemental | 230 | 6.49 |  | PPL |  |  |  |  | PA | Montour | Substation | Build | EP | 6.49 | Operational Flexibility and Efficiency,Infrastructure Resilience | 12/31/2033 |  | No | 1/7/2016 | 1/7/2016 | 0
s1098.3 | PJM MA | Remove two (2) Montour 230kV circuits breakers in Bay 1 and Bay 2. | Supplemental | 230 | 0 |  | PPL |  |  |  |  | PA | Montour | Circuit Breaker | Remove | EP | 0 | Operational Flexibility and Efficiency,Infrastructure Resilience | 11/30/2030 |  | No | 1/7/2016 | 1/7/2016 | 0
s1100 | PJM MA | Rebuild the existing Foxhill-Shawnee 230 kV line (Approximately 8.25 Miles). | Supplemental | 230 | 24.8 |  | PPL |  |  |  |  | PA | Foxhill - Shawnee | Transmission Line | Rebuild | EP | 24.8 | Equipment Material Condition, Performance and Risk | 6/11/2027 |  | No | 1/7/2016 | 1/7/2016 | 10
s1105.1 | PJM MA | Build new 230 kV Line from Dauphin to New Harrisburg kV Substation. | Supplemental | 230 | 63 |  | PPL |  |  |  |  | PA | Dauphin - New Harrisburg | Transmission Line | Build | EP | 63 | Operational Flexibility and Efficiency,Infrastructure Resilience | 12/15/2033 |  | No | 1/7/2016 | 1/7/2016 | 0
s1105.2 | PJM MA | Build new UG 230 kV Line from West Shore to New Harrisburg Substation. | Supplemental | 230 | 25 |  | PPL |  |  |  |  | PA | West Shore - New Harrisburg | Transmission Line (Underground) | Build | EP | 25 | Operational Flexibility and Efficiency,Infrastructure Resilience | 11/30/2033 |  | No | 1/7/2016 | 1/7/2016 | 0
s1672 | PJM MA | Rebuild Seward-Glory-Piney 115 kV line: rebuild ~66 miles of 115 kV line using double circuit 230 kV construction, install 1033 ACSR conductor (six-wired) energized at 115 kV. | Supplemental | 115 | 200 |  | PENELEC |  |  |  |  | PA | Seward, Glory, Piney | Transmission Line | Rebuild | EP | 200 | Equipment Material Condition, Performance and Risk | 12/31/2028 |  | No | 5/25/2018 | 7/20/2018 | 4
s1712 | PJM WEST | At Masury: Replace Y-188 (B17) 69 kV line relaying and control with standard relay panel At Sharon: Replace Y-188/Y-303 (B6) 69 kV line relaying and control with standard relay panel. Replace the limiting disconnect switch At Shenango: Replace 138 kV breaker (B48) and line relaying. Replace two 138 kV breaker disconnect switches (D37 & D43). Upgrade the terminal equipment (line drops) to exceed the TL rating At McDowell: Upgrade the terminal equipment (substation conductor) to exceed the TL rating | Supplemental | 69 | 45 |  | ATSI |  |  |  |  | PA | Shenango | Substation | Build | EP | 45 | Operational Flexibility and Efficiency | 4/1/2026 |  | No | 8/31/2018 | 4/21/2023 | 30 |  | 12/1/2025
s1713 | PJM WEST | Build new Pine-Cranberry #3 138 kV Line | Supplemental | 138 | 27 |  | ATSI |  |  |  |  | PA | Pine, Cranberry | Transmission Line | Build | EP | 27 | Operational Flexibility and Efficiency | 12/15/2028 |  | No | 8/31/2018 | 9/28/2018 | 2
s1756 | PJM WEST | Replace New Castle #7 138/69 kV Transformer. Replace existing New Castle #7 138/69/4.2 kV transformer (125 MVA) with new 138/69 kV transformer (134 MVA). Replace existing 69 kV breaker (B32). Install new 69/4.2 kV transformer (15 MVA) and a 69 kV circuit breaker in existing 69 kV transformer position for generation station service. | Supplemental | 138/69 | 3.9 |  | ATSI |  |  |  |  | PA | New Castle | Transformer | Replace | EP | 3.9 | Equipment Material Condition, Performance and Risk | 6/14/2026 |  | No | 10/26/2018 | 10/26/2018 | 10
s1761.1 | PJM MA | Construct new Van Reed 69 kV Ring Bus Substation | Supplemental | 69 | 8.26 |  | ME |  |  |  |  | PA | Van Reed | Substation | Build | EP | 3.6 | Customer Service | 11/30/2026 |  | No | 10/29/2018 | 10/29/2018 | 20
s1761.2 | PJM MA | Loop the Northkill - North Temple 69 kV line into Van Reed | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | Northkill, North Templ, Van Reed | Transmission Line | Modify | EP |  | Customer Service | 6/30/2026 |  | No | 10/29/2018 | 10/29/2018 | 4
s1761.3 | PJM MA | Provide new 69 kV delivery point for customer from Van Reed 69 kV | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | Van Reed | Transmission Line | Build | EP |  | Customer Service | 6/30/2026 |  | No | 10/29/2018 | 10/29/2018 | 4
s1769.1 | PJM MA | Dubois – Harvey Run – Whetstone 115 kV Line, Rehab approximately 14.25 miles of wood pole construction | Supplemental | 115 | 5.3 |  | PENELEC |  |  |  |  | PA | Dubois, Harvey Run, Whetstone | Transmission Line | Upgrade | EP | 5.3 | Equipment Material Condition, Performance and Risk | 12/31/2027 |  | No | 10/29/2018 | 10/29/2018 | 3
s1769.2 | PJM MA | Dubois 115 kV substation - Replace Line relaying, line trap, substation conductor, line tuner, CCVT, circuit breaker and breaker disconnects (on Dubois – Harvey Run – Whetstone 115 kV Line) | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA | Dubois | Relay | Replace | EP |  | Equipment Material Condition, Performance and Risk | 12/31/2026 |  | No | 10/29/2018 | 10/29/2018 | 1
s1769.3 | PJM MA | Harvey Run 115 kV substation - Replace Substation conductor, disconnect switches and CVTs (on Dubois – Harvey Run – Whetstone 115 kV Line) | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA | Harvey Run | Relay | Replace | EP |  | Equipment Material Condition, Performance and Risk | 12/31/2026 |  | No | 10/29/2018 | 10/29/2018 | 1
s1769.4 | PJM MA | Whetstone 115 kV substation - Replace Line relaying, line trap, substation conductor, line tuner, CCVT, circuit breaker and breaker disconnects (on Dubois – Harvey Run – Whetstone 115 kV Line) | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA | Whetstone | Relay | Replace | EP |  | Equipment Material Condition, Performance and Risk | 12/31/2026 |  | No | 10/29/2018 | 10/29/2018 | 1
s1774.1 | PJM MA | Seward 230 kV substation - Expand 230 kV ring bus to a six breaker ring bus | Supplemental | 230 | 15.7 |  | PENELEC |  |  |  |  | PA | Seward | Bus | Modify | EP | 15.7 | Operational Flexibility and Efficiency | 3/24/2026 |  | No | 10/29/2018 | 10/29/2018 | 10
s1774.2 | PJM MA | Relocate the Homer City – Seward 230 kV and Johnstown – Seward 230 kV line terminals | Supplemental | 230 | 0 |  | PENELEC |  |  |  |  | PA | Seward | Transmission Line | Modify | EP |  | Operational Flexibility and Efficiency | 3/24/2026 |  | No | 10/29/2018 | 10/29/2018 | 10
s1774.4 | PJM MA | Install a 115 kV reactor on the low side of the Seward #11 230/115 kV transformer | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA | Seward | Reactive Device | Install | EP |  | Operational Flexibility and Efficiency | 3/24/2026 |  | No | 10/29/2018 | 10/29/2018 | 10
s1779.2 | PJM MA | East Altoona 46 kV Substation - Replace Disconnect switches | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | East Altoona | Relay | Replace | EP |  | Operational Flexibility and Efficiency | 5/13/2025 |  | No | 10/29/2018 | 10/29/2018 | 15
s1795 | PJM WEST | NLMK 138/69 kV Substation Rebuild Project; Retire existing NLMK 1M and 2M substations and network the existing NLMK 69 kV system with the Masury-Sharon 69 kV line. Install a loop structure at the Masury tap and rebuild the segment of line from the tap to the 2M substation as double circuit 336 ACSR (0.8 miles) * Replace existing NLMK 138/69 kV 1M substation with new a 138/69 kV substation - 3-138 kV breakers in a straight bus configuration (1-Line and 2-transformer breakers) - 2-138/69 kV transformers (134 MVA) - Six (6) breaker 69 kV ring bus - New control building * Re-configure existing 69 kV lines around NLMK - Masury-NLMK 69 kV Line: 57 MVA SN / 73 MVA SE - Sharon-NLMK 69 kV Line: 57 MVA SN / 73 MVA SE * Install revenue metering * Add a 138 kV breaker at Crossland for the Crossland-NLMK 138 kV Line * Upgrade 69 kV relays at Masury and Sharon substations | Supplemental | 69 | 30 |  | ATSI |  |  |  |  | PA | NLMK | Substation | Rebuild | EP | 30 | Equipment Material Condition, Performance and Risk | 3/25/2031 |  | No | 9/28/2018 | 10/26/2018 | 12
s1811.1 | PJM MA | Pleasureville 115 kV Substation - replace Line relaying, line trap, CCVT, line tuner, coax, substation conductor, and breaker disconnect switches | Supplemental | 115 | 0 |  | ME |  |  |  |  | PA | Pleasureville | Conductor | Replace | EP |  | Equipment Material Condition, Performance and Risk | 10/17/2025 |  | No |  |  | 4
s1811.2 | PJM MA | York Incinerator 115 kV Substation - replace Line relaying, line trap, CCVT, line tuner, coax, substation conductor, circuit breaker, and disconnect switches | Supplemental | 115 | 0 |  | ME |  |  |  |  | PA | York Incinerator | Conductor | Replace | EP |  | Equipment Material Condition, Performance and Risk | 10/8/2026 |  | No |  |  | 4
s1818 | PJM MA | Jackson – Westgate 115 kV replace relays prone to misoperation | Supplemental | 115 | 1.86 |  | ME |  |  |  |  | PA | Jackson, Westgate | Relay | Replace | EP |  | Equipment Material Condition, Performance and Risk | 12/31/2025 |  | No | 11/28/2018 | 11/28/2018 | 20
s1818.1 | PJM MA | Jackson – Taxville 115 kV Line section - replace Line disconnect switches (JE Baker Tap) | Supplemental | 115 | 0 |  | ME |  |  |  |  | PA | Jackson, Taxville | Circuit Switcher | Replace | EP |  | Equipment Material Condition, Performance and Risk | 12/12/2025 |  | No |  |  | 30
s1818.2 | PJM MA | Jackson 115 kV Substation - replace Line relaying, line drops, CCVT, line trap, line tuner, coax, substation conductor, and breaker disconnect switches | Supplemental | 115 | 0 |  | ME |  |  |  |  | PA | Jackson | Communication Equipment | Replace | EP |  | Equipment Material Condition, Performance and Risk | 12/31/2025 |  | No |  |  | 30
s1818.3 | PJM MA | Westgate 115 kV Substation - replace Line relaying, CCVT, line trap, line tuner, and arresters | Supplemental | 115 | 0 |  | ME |  |  |  |  | PA | Westgate | Communication Equipment | Replace | EP |  | Equipment Material Condition, Performance and Risk | 12/31/2025 |  | No |  |  | 30
s1819 | PJM MA | Gardners – Hunterstown 115 kV replace relays prone to misoperation | Supplemental | 115 | 3.9 |  | ME |  |  |  |  | PA | Gardners, Hunterstown | Relay | Replace | EP |  | Equipment Material Condition, Performance and Risk | 5/13/2027 |  | No | 11/28/2018 | 11/28/2018 | 25
s1819.1 | PJM MA | Gardners 115 kV Substation - replace Line relaying, CCVT, line trap, line tuner, coax, arresters, substation conductor, circuit breaker and disconnect switches | Supplemental | 115 | 0 |  | ME |  |  |  |  | PA | Gardners | Circuit Breaker | Replace | EP |  | Equipment Material Condition, Performance and Risk | 10/31/2025 |  | No |  |  | 30
s1819.2 | PJM MA | Hunterstown 115 kV Substation - replace Line relaying, CCVT, line trap, line tuner, coax, and arresters | Supplemental | 115 | 0 |  | ME |  |  |  |  | PA | Hunterstown | Circuit Breaker | Replace | EP |  | Equipment Material Condition, Performance and Risk | 10/31/2025 |  | No |  |  | 30
s1826 | PJM WEST | Tap the existing Pursley - Franklin 138 kV line. Install one 138 kV line switch (Franklin side). Install 138 kV switch on line to customer. Construct single span of 138 kV line to customer substation. | Supplemental | 138 | 0.14 |  | APS |  |  |  |  | PA | Franklin | Circuit Switcher | Install | EP | 0.14 | Customer Service | 12/31/2022 |  | No | 2/22/2019 | 2/22/2019 | 1
s1827 | PJM WEST | Tap the existing Fawn - Lawson Jct 138 kV line. Install two 138 kV line switches. Install 138 kV switch on line to customer. Construct 1.5 miles of 138 kV line to customer substation. | Supplemental | 138 | 0.14 |  | APS |  |  |  |  | PA | Fawn | Circuit Switcher | Install | EP | 0.14 | Equipment Material Condition, Performance and Risk,Customer Service | 6/30/2024 |  | No | 4/26/2019 | 4/26/2019 | 1
s1880 | PJM MA | Construct a new 69 kV transmission line from Shawnee to Walker substations (approximately 31.1 miles) | Supplemental | 69 | 75 |  | ME |  |  |  |  | PA | Shawnee | Transmission Line | Build | EP | 60 | Customer Service | 12/31/2028 |  | No | 1/25/2019 | 11/19/2019 | 3
s1880.1 | PJM MA | Expand Shawnee 230 kV bus into a six breaker ring bus | Supplemental | 230 | 0 |  | ME |  |  |  |  | PA | Shawnee | Bus | Modify | EP |  | Customer Service | 12/31/2026 |  | No | 1/25/2019 | 11/19/2019 | 3
s1880.2 | PJM MA | Install a new 230/69 kV 100/134/168 MVA transformer and associated equipment at Shawnee station | Supplemental | 230/69 | 0 |  | ME |  |  |  |  | PA | Shawnee | Transformer | Install | EP |  | Customer Service | 12/31/2026 |  | No | 1/25/2019 | 11/19/2019 | 3
s1880.3 | PJM MA | Build new 69 kV delivery point at Birchwood Lakes | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | Birchwood Lakes | Substation | Build | EP |  | Customer Service | 12/31/2026 |  | No | 1/25/2019 | 11/19/2019 | 3
s1880.4 | PJM MA | Install a new 69 kV 9.6 MVAR capacitor at Birchwood Lakes | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | Birchwood Lakes | Capacitor | Install | EP |  | Customer Service | 12/31/2026 |  | No | 1/25/2019 | 11/19/2019 | 3
s1880.5 | PJM MA | Build new 69 kV delivery point at Bushkill Falls | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | Bushkill Falls | Substation | Build | EP |  | Customer Service | 12/31/2026 |  | No | 1/25/2019 | 11/19/2019 | 3
s1880.6 | PJM MA | Install a new 69 kV 9.6 MVAR capacitor Bushkill Falls | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | Bushkill Falls | Capacitor | Install | EP |  | Customer Service | 12/31/2026 |  | No | 1/25/2019 | 11/19/2019 | 3
s1880.7 | PJM MA | Expand Walker 69 kV bus into a three breaker ring bus | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | Walker | Bus | Modify | EP |  | Customer Service | 6/1/2027 |  | No | 1/25/2019 | 11/19/2019 | 3
s1883 | PJM MA | Remove the Westfall No.3 and No.4 115/46 kV transformers and install a new Westfall No.3 115/46 kV 45/60/75 MVA transformer | Supplemental | 115/46 | 3.9 |  | PENELEC |  |  |  |  | PA | Westfall | Transformer | Upgrade | EP | 3.9 | Equipment Material Condition, Performance and Risk | 6/30/2027 |  | No | 3/25/2019 | 11/19/2019 | 20
s1890.2 | PJM MA | Replace line relaying, line trap, and substation conductor on the Erie South 115 kV Line exit at the Union City 115 kV Substation | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA | Union City | Conductor | Upgrade | EP |  | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 3/31/2025 |  | No | 3/25/2019 | 11/19/2019 | 25
s1891.1 | PJM MA | Build a 115 kV four breaker ring bus at Titusville station. | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA | Titusville | Bus | Build | EP |  | Operational Flexibility and Efficiency | 6/15/2026 |  | No | 3/25/2019 | 11/19/2019 | 2
s1891.2 | PJM MA | Replace substation conductor on the Titusville 115 kV Line exit at the Union City station | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA | Union City | Conductor | Upgrade | EP |  | Operational Flexibility and Efficiency | 6/15/2026 |  | No | 3/25/2019 | 11/19/2019 | 2
s1891.3 | PJM MA | Replace substation conductor on the Titusville 115 kV line exit at Grandview 115 kV substation. | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA | Grandview | Conductor | Upgrade | EP |  | Operational Flexibility and Efficiency | 6/15/2026 |  | No | 3/25/2019 | 11/19/2019 | 2
s1898.1 | PJM MA | Reconductor Bernville - State Street 69 kV line section | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | Bernville, State Street | Transmission Line | Reconductor | EP |  | Equipment Material Condition, Performance and Risk | 12/23/2025 |  | No | 4/26/2019 | 11/19/2019 | 10
s1898.2 | PJM MA | Replace substation conductor and relays on the State Street 69 kV Line exit at South Hamburg substation. | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | South Hamburg | Conductor | Upgrade | EP |  | Equipment Material Condition, Performance and Risk | 4/4/2025 |  | No | 4/26/2019 | 11/19/2019 | 35
s1899 | PJM MA | Rehab/Rebuild the Middletown Junction - Smith Street 69 kV Line. | Supplemental | 69 | 2.1 |  | ME |  |  |  |  | PA | Middletown Junction, Smith Street | Transmission Line | Rebuild | EP | 2.1 | Equipment Material Condition, Performance and Risk | 12/31/2022 |  | No | 4/26/2019 | 11/19/2019 | 0
s1899.1 | PJM MA | Rehab/Rebuild Middletown Junction - York Haven Tap - Zions view - Smith Street 69 kV Line | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | Middletown Junction, York Haven Tap, Zions view, S | Transmission Line | Rebuild | EP |  | Equipment Material Condition, Performance and Risk | 12/31/2022 |  | No | 4/26/2019 | 11/19/2019 | 0
s1899.2 | PJM MA | Replace substation conductor on the Zions View 69 kV line exit at the Smith Street substation. | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | Smith Street | Conductor | Upgrade | EP |  | Equipment Material Condition, Performance and Risk | 12/31/2022 |  | No | 4/26/2019 | 11/19/2019 | 0
s1900 | PJM MA | Rehab/Rebuild Allentown - Lyons - South Hamburg 69 kV line | Supplemental | 69 | 15.7 |  | ME |  |  |  |  | PA | Allentown, Lyons, South Hamburg | Transmission Line | Rebuild | EP | 15.7 | Equipment Material Condition, Performance and Risk | 6/1/2027 |  | No | 4/26/2019 | 11/19/2019 | 30
s1900.1 | PJM MA | Rehab/Rebuild Allentown - Lyons - South Hamburg 69 kV line. Reconductor 15.2 miles of the circuit | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | Allentown, Lyons, South Hamburg | Transmission Line | Rebuild | EP |  | Equipment Material Condition, Performance and Risk | 6/1/2027 |  | No | 4/26/2019 | 11/19/2019 | 10
s1900.2 | PJM MA | Replace substation conductor at South Hamburg 69 kV station | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | South Hamburg | Conductor | Upgrade | EP |  | Equipment Material Condition, Performance and Risk | 6/1/2027 |  | No | 4/26/2019 | 11/19/2019 | 10
s1900.3 | PJM MA | Replace substation conductor at Moselem 69 kV station | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | Moselem | Conductor | Upgrade | EP |  | Equipment Material Condition, Performance and Risk | 6/1/2026 |  | No | 4/26/2019 | 11/19/2019 | 10
s1900.4 | PJM MA | Replace substation conductor at Lyons 69 kV station | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | Lyons | Conductor | Upgrade | EP |  | Equipment Material Condition, Performance and Risk | 12/31/2025 |  | No | 4/26/2019 | 11/19/2019 | 10
s1905.3 | PJM MA | Replace substation conductor on the Middle Creek 69 kV line exit at County Line substation. | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | County Line | Conductor | Upgrade | EP |  | Equipment Material Condition, Performance and Risk | 4/1/2025 |  | No | 4/26/2019 | 11/19/2019 | 30
s1905.4 | PJM MA | Replace relay and disconnect switch on the Middle Creek 69 kV line exit at Ringing Rocks substation. | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | Ringing Rocks | Conductor | Upgrade | EP |  | Equipment Material Condition, Performance and Risk | 6/15/2025 |  | No | 4/26/2019 | 11/19/2019 | 30
s1907 | PJM MA | Replacement 230/69 kV transformers No.1 and No.2 and 230 kV ring bus at South Lebanon substation. | Supplemental | 69 | 13.9 |  | ME |  |  |  |  | PA | South Lebanon | Substation | Modify | EP | 13.9 | Equipment Material Condition, Performance and Risk | 12/31/2021 |  | No | 4/26/2019 | 11/19/2019 | 0
s1907.2 | PJM MA | Replace the South Lebanon 230/69 kV 60/80/100 MVA transformer No.2 and associated equipment with a new 230/69 kV 100/134/168 MVA transformer. | Supplemental | 230/69 | 0 |  | ME |  |  |  |  | PA | South Lebanon | Transformer | Upgrade | EP |  | Equipment Material Condition, Performance and Risk | 12/31/2025 |  | No | 4/26/2019 | 11/19/2019 | 1
s1919 | PJM MA | Construct a 115 kV ring bus at the Philipsburg substation. | Supplemental | 115 | 4.5 |  | PENELEC |  |  |  |  | PA | Philipsburg | Bus | Build | EP | 4.5 | Operational Flexibility and Efficiency | 6/18/2027 |  | No | 5/31/2019 | 11/19/2019 | 4
s1919.1 | PJM MA | Build a four breaker 115 kV ring bus at the Philipsburg substation. | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA | Philipsburg | Bus | Build | EP |  | Operational Flexibility and Efficiency | 12/31/2026 |  | No | 5/31/2019 | 11/19/2019 | 4
s1919.3 | PJM MA | Replace limiting CTs, substation conductor / drop, and circuit breakers on Eagle Valley 115 kV line exit at the Philipsburg substation. | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA | Philipsburg | Conductor | Upgrade | EP |  | Operational Flexibility and Efficiency | 12/31/2026 |  | No | 5/31/2019 | 11/19/2019 | 4
s1919.4 | PJM MA | Replace line trap on Philipsburg 115 kV line exit at the Shawville substation and adjust line relaying as necessary. | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA | Shawville | Conductor | Upgrade | EP |  | Operational Flexibility and Efficiency | 12/31/2026 |  | No | 5/31/2019 | 11/19/2019 | 4
s1920 | PJM MA | Build 115 kV ring bus at the Clark Summit substation. | Supplemental | 115 | 3.9 |  | PENELEC |  |  |  |  | PA | Clark Summit | Bus | Build | EP | 3.9 | Operational Flexibility and Efficiency | 6/1/2027 |  | No | 5/31/2019 | 11/19/2019 | 3
s1920.1 | PJM MA | Build a new 115 kV four breaker ring bus at the Clark Summit substation. | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA | Clark Summit | Bus | Build | EP |  | Operational Flexibility and Efficiency | 12/31/2025 |  | No | 5/31/2019 | 11/19/2019 | 2
s1920.2 | PJM MA | Replace substation conductor on the Clark Summit 115 kV line exit at the Grandview substation. | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA | Grandview | Conductor | Upgrade | EP |  | Operational Flexibility and Efficiency | 12/31/2025 |  | No | 5/31/2019 | 11/19/2019 | 2
s1921 | PJM MA | Build 46 kV ring bus at the Lilly substation. | Supplemental | 46 | 4.4 |  | PENELEC |  |  |  |  | PA | Lilly | Bus | Build | EP | 4.4 | Operational Flexibility and Efficiency | 12/31/2026 |  | No | 5/31/2019 | 11/19/2019 | 5
s1921.1 | PJM MA | Build a four breaker 46 kV ring bus at Lilly substation | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Lilly | Bus | Build | EP |  | Operational Flexibility and Efficiency | 12/31/2026 |  | No | 5/31/2019 | 11/19/2019 | 2
s1921.2 | PJM MA | Replace line relaying, substation conductor, and disconnect switches on the Ampfire Mining 46 kV line exit at the Jackson Road station. | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Jackson Road | Conductor | Upgrade | EP |  | Operational Flexibility and Efficiency | 12/31/2026 |  | No | 5/31/2019 | 11/19/2019 | 2
s1921.3 | PJM MA | Replace line relaying on the Kokomo Road 46 kV line exit at the Summit station. | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Summit | Relay | Upgrade | EP |  | Operational Flexibility and Efficiency | 12/31/2026 |  | No | 5/31/2019 | 11/19/2019 | 2
s1921.4 | PJM MA | Replace line relaying and substation conductor on the Lilly 46 kV line exit at the Bethlehem 33 substation. | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Bethlehem 33 | Relay | Upgrade | EP |  | Operational Flexibility and Efficiency | 12/31/2026 |  | No | 5/31/2019 | 11/19/2019 | 2
s1921.5 | PJM MA | Operate normally open switch as normally closed on Portage - Lilly 46 kV line exit at the Portage station. | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Portage | Disconnect Switch | Modify | EP |  | Operational Flexibility and Efficiency | 12/31/2026 |  | No | 5/31/2019 | 11/19/2019 | 2
s1923.10 | PJM MA | Rebuild ~0.5 miles of Williamsburg - Williamsburg REC 46 kV line | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Williamsburg, Williamsburg REC | Transmission Line | Reconductor | EP |  | Operational Flexibility and Efficiency | 3/28/2025 |  | No | 5/31/2019 | 11/19/2019 | 2
s1923.11 | PJM MA | Eliminate ABW Tap, via a line loop and rebuild ~7.5 miles of Williamsburg REC - Warrior Ridge 46 kV line. | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Williamsburg REC, Warrior Ridge | Transmission Line | Reconductor | EP |  | Operational Flexibility and Efficiency | 11/7/2025 |  | No | 5/31/2019 | 11/19/2019 | 2
s1923.12 | PJM MA | Rebuild the Alexandria - Warrior Ridge 46 kV line from ABW tap | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Alexandria, Warrior Ridge | Transmission Line | Reconductor | EP |  | Operational Flexibility and Efficiency | 11/7/2025 |  | No | 5/31/2019 | 11/19/2019 | 2
s1923.13 | PJM MA | Replace disconnect switch on the Warrior Ridge 46 kV line exit with motor operated disconnect switch with whip at the Alexandria substation | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Alexandria | Disconnect Switch | Upgrade | EP |  | Operational Flexibility and Efficiency | 2/28/2026 |  | No | 5/31/2019 | 11/19/2019 | 20
s1923.14 | PJM MA | Replace disconnect switches with motor operated disconnect switches with vacuum bottles on Pemberton and Alexandria 46 kV line exits at the Water Street substation. | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Water Street,Pemberton, Alexandria | Disconnect Switch | Upgrade | EP |  | Operational Flexibility and Efficiency | 2/28/2026 |  | No | 5/31/2019 | 11/19/2019 | 1
s1923.2 | PJM MA | Replace disconnect switch on Warrior Ridge 46 kV line exit with motor operated disconnect switch with whip at the Center Union substation. | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Center Union | Disconnect Switch | Upgrade | EP |  | Operational Flexibility and Efficiency | 12/20/2025 |  | No | 5/31/2019 | 11/19/2019 | 2
s1923.3 | PJM MA | Replace disconnect switch on Center Union 46 kV line exit with motor operated disconnect switch with vacuum bottles at Belleville substation | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Belleville | Disconnect Switch | Upgrade | EP |  | Operational Flexibility and Efficiency | 4/30/2027 |  | No | 5/31/2019 | 11/19/2019 | 2
s1923.4 | PJM MA | Replace disconnect switch on Belleville 46 kV line exit with motor operated disconnect switch with vacuum bottles at the New Holland station | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | New Holland | Disconnect Switch | Upgrade | EP |  | Operational Flexibility and Efficiency | 4/30/2027 |  | No | 5/31/2019 | 11/19/2019 | 2
s1923.5 | PJM MA | Replace line relaying, substation conductor, disconnect switches on the Warrior Ridge 46 kV line exit at the Huntingdon substation. | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Huntingdon | Conductor | Upgrade | EP |  | Operational Flexibility and Efficiency | 12/20/2025 |  | No | 5/31/2019 | 11/19/2019 | 2
s1923.8 | PJM MA | Replace line relaying, disconnect switches, and substation conductor on the Altoona 46 kV line exit at the Williamsburg substation. | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Williamsburg | Conductor | Upgrade | EP |  | Operational Flexibility and Efficiency | 12/20/2025 |  | No | 5/31/2019 | 11/19/2019 | 2
s1923.9 | PJM MA | Replace disconnect switches with motor operated disconnect switches with whips on the Williamsburg 46 kV line exit at the Williamsburg REC substatin. | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Williamsburg REC | Disconnect Switch | Upgrade | EP |  | Operational Flexibility and Efficiency | 3/28/2025 |  | No | 5/31/2019 | 11/19/2019 | 2
s1924 | PJM MA | Construct a 115 kV ring bus at the Buffalo Road substation. | Supplemental | 115 | 12.8 |  | PENELEC |  |  |  |  | PA | Buffalo Road | Bus | Modify | EP | 9 | Operational Flexibility and Efficiency | 6/1/2027 |  | No | 5/31/2019 | 11/19/2019 | 3
s1924.1 | PJM MA | Expand the bus configuration to a six breaker ring bus by installing three (3) new 115 kV breakers at Buffalo Road. | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA | Buffalo Road | Bus | Modify | EP |  | Operational Flexibility and Efficiency | 7/15/2026 |  | No | 5/31/2019 | 11/19/2019 | 2
s1924.2 | PJM MA | Replace limiting substation conductor on the Four Mile No.2 115 kV line exit at the Buffalo Road station. | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA | Buffalo Road | Conductor | Upgrade | EP |  | Operational Flexibility and Efficiency | 7/15/2026 |  | No | 5/31/2019 | 11/19/2019 | 2
s2028 | PJM MA | Expand and reconfigure the existing Long Pond substation to a higher capacity design and build a second line from Long Pond to the existing Acahela-Jackson No.2 69 kV line | Supplemental | 69 | 0.75 |  | PPL |  |  |  |  | PA | Long Pond | Transmission Line | Build | EP | 0.75 | Customer Service | 11/30/2030 |  | No | 4/26/2019 | 11/14/2019 | 10
s2031 | PJM MA | Build a new distribution substation (Zeta) near the location of the requested load additions. Interconnect the distribution substation with lines from the existing Wescosville-Breinigsville No.1&2 69 kV lines. | Supplemental | 69 | 1.2 |  | PPL |  |  |  |  | PA | Zeta, Wescosville, Breinigsville | Substation | Build | EP | 1.2 | Customer Service | 12/31/2028 |  | No | 4/26/2019 | 11/14/2019 | 10
s2032 | PJM MA | Build a new distribution substation (Eta) near the location of the requested load additions. Interconnect the distribution substation with lines from the existing Allentown-Siegfried No.1&2 138 kV lines lines. | Supplemental | 138 | 1.5 |  | PPL |  |  |  |  | PA | Eta, Allentown, Siegfried | Substation | Build | EP | 1.5 | Customer Service | 11/1/2028 |  | No | 4/26/2019 | 11/14/2019 | 10
s2033 | PJM MA | Convert Glendon 115 kV to a six (6) breaker ring bus | Supplemental | 115 | 11 |  | ME |  |  |  |  | PA | Glendon | Bus | Modify | EP | 9.9 | Operational Flexibility and Efficiency | 12/31/2026 |  | No | 7/31/2019 | 11/19/2019 | 15
s2034 | PJM MA | Convert Lincoln 115 kV to a six (6) breaker ring bus | Supplemental | 115 | 6.9 |  | ME |  |  |  |  | PA | Lincoln | Bus | Modify | EP | 6.9 | Operational Flexibility and Efficiency | 6/1/2027 |  | No | 7/31/2019 | 11/19/2019 | 5
s2037 | PJM MA | Expand Pleasureville 115 kV substation into a breaker-and-a-half configuration (8 breakers). | Supplemental | 115 | 10 |  | ME |  |  |  |  | PA | Pleasureville | Bus | Modify | EP | 10 | Operational Flexibility and Efficiency | 4/14/2028 |  | No | 7/31/2019 | 11/19/2019 | 4
s2054 | PJM MA | Rebuild and reconductor approximately 33.0 miles of the Armstrong – Homer City 345 kV Line, of wood pole construction | Supplemental | 345 | 138 |  | PENELEC |  |  |  |  | PA | Armstrong, Homer City | Transmission Line | Rebuild | EP | 138 | Equipment Material Condition, Performance and Risk | 6/1/2029 |  | No | 8/8/2019 | 11/19/2019 | 4
s2076 | PJM MA | Construct new 230/13kv substation in a Ring configuration. Install two 230kV–13kV 62MVA Distribution Transformers to support new distribution load in the area. | Supplemental | 230/13 | 82 |  | PECO |  |  |  |  | PA | Navy Yard | Substation | Build | EP | 82 | Customer Service | 10/31/2029 |  | No | 10/21/2019 | 10/21/2019 | 10
s2128 | PJM WEST | On the Crossland – Shenango No.2 138 kV line, replace line relaying on Crossland-Shenango terminal ends; replace disconnect switches and substation conductors at Shenango and Crossland, replace one air break switch and terminal end breakers at Shenango (B14 and B18) due to existing condition. | Supplemental | 138 | 1 |  | ATSI |  |  |  |  | PA | Crossland, Shenango | Relay | Replace | EP | 1 | Equipment Material Condition, Performance and Risk | 3/1/2030 |  | No | 11/22/2019 | 11/22/2019 | 0
s2168 | PJM MA | Build a tap from the Frackville – Shenandoah 69 kV line to connect the new 69/12 kV distribution substation, "Ringtown" | Supplemental | 69/12 | 0.9 |  | PPL |  |  |  |  | PA | Frackville, Shenandoah, Ringtown | Transmission Line | Build | EP | 0.9 | Customer Service | 11/30/2033 |  | No | 11/18/2019 | 11/18/2019 | 0
s2170.3 | PJM MA | Replace 69 kV substation conductor at Mill Street substation | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | Mill Street | Conductor | Upgrade | EP |  | Equipment Material Condition, Performance and Risk | 12/15/2025 |  | No | 11/18/2019 | 11/18/2019 | 1
s2291 | PJM WEST | Charleroi 138 kV Substation – Replace line relaying, substation conductors, and line trap Mitchell 138 kV Substation – Replace line relaying, substation conductors, and line trap, Peters 138 kV Substation – Replace line relaying, substation conductors, and line trap | Supplemental | 138 | 2.04 |  | APS |  |  |  |  | PA | Charleroi | Relay | Replace | EP | 1.6 | Equipment Material Condition, Performance and Risk | 11/14/2022 |  | No | 5/22/2020 | 7/17/2020 | 20
s2292 | PJM WEST | Gordon 138 kV Substation – Replace line relaying, substation conductors, and line trap, Windsor 138 kV Substation – Replace line relaying, breaker, substation conductors, and line trap | Supplemental | 138 | 1.4 |  | APS |  |  |  |  | PA | Gordon | Relay | Replace | EP | 1.4 | Equipment Material Condition, Performance and Risk | 6/1/2022 |  | No | 5/22/2020 | 7/17/2020 | 1
s2310.1 | PJM MA | Rebuild and reconductor Carsonia – Lyons – North Boyertown 69 kV line | Supplemental | 69 | 26.4 |  | ME |  |  |  |  | PA | Carsonia/Lyons/ North Boyertown | Transmission Line | Rebuild | EP | 26.4 | Equipment Material Condition, Performance and Risk | 6/1/2029 |  | No | 7/16/2020 | 7/16/2020 | 3
s2310.2 | PJM MA | Replace disconnect switches, substation conductor, and line relaying at Carsonia 69 kV Substation | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | Carsonia |  | Replace | EP |  | Equipment Material Condition, Performance and Risk | 6/1/2026 |  | No | 7/16/2020 | 7/16/2020 | 4
s2310.3 | PJM MA | Replace disconnect switches and substation conductor at Friedensburg 69 kV Substation | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | Friedensburg |  | Replace | EP |  | Equipment Material Condition, Performance and Risk | 4/1/2026 |  | No | 7/16/2020 | 7/16/2020 | 4
s2310.4 | PJM MA | Replace circuit breaker and disconnect switches at North Boyertown 69 kV Substation | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | North Boyertown |  | Replace | EP |  | Equipment Material Condition, Performance and Risk | 12/4/2026 |  | No | 7/16/2020 | 7/16/2020 | 4
s2312 | PJM MA | Hooversville 115 kV Substation – Replace line trap, line relaying, and substation conductor, Tower 51 115 kV Substation – Replace line trap line relaying, substation conductor, disconnect switches, circuit breaker, and CTs | Supplemental | 115 | 1.1 |  | PENELEC |  |  |  |  | PA | Hooversville/Tower |  | Replace | EP | 1.1 | Equipment Material Condition, Performance and Risk | 6/1/2023 |  | No | 7/16/2020 | 7/16/2020 | 4
s2370 | PJM MA | Rebuild the 6.2-mile Corten tower section of the Montour-Saegers 1 & 2 230kV lines with steel monopoles and new conductor. | Supplemental | 230 | 17.5 |  | PPL |  |  |  |  | PA | Montour-Saegers | Transmission Structures | Rebuild | EP | 17.5 | Equipment Material Condition, Performance and Risk | 12/18/2026 |  | No | 10/6/2020 | 10/6/2020 | 10
s2371 | PJM MA | Rebuild the 8.5-mile Corten tower section of the Jenkins-Stanton & Mountain-Stanton 230kV lines with steel monopoles and new conductor. | Supplemental | 230 | 22.8 |  | PPL |  |  |  |  | PA | Jenkins/Stanton/Mountain | Transmission Structures | Rebuild | EP | 22.8 | Equipment Material Condition, Performance and Risk | 4/23/2027 |  | No | 10/6/2020 | 10/6/2020 | 0
s2372 | PJM MA | Rebuild the 9.8-mile Corten tower section of the Mountain-Stanton & Mountain-Jenkins 230kV lines with steel monopoles and new conductor | Supplemental | 230 | 27 |  | PPL |  |  |  |  | PA | Mountain/Stanton/Jenkins | Transmission Structures | Rebuild | EP | 27 | Equipment Material Condition, Performance and Risk | 7/3/2026 |  | No | 10/6/2020 | 10/6/2020 | 10
s2373 | PJM MA | Rebuild the 21.9 miles of Corten tower sections of the Montour-Susquehanna & Montour-Susquehanna T10 230kV lines with steel monopoles and new conductor. | Supplemental | 230 | 69.6 |  | PPL |  |  |  |  | PA | Montour-Susquehanna | Transmission Structures | Rebuild | EP | 69.6 | Equipment Material Condition, Performance and Risk | 12/31/2029 |  | No | 10/6/2020 | 10/6/2020 | 0
s2375 | PJM MA | Rebuild the 9.25-mile Corten tower section of the Montour-Columbia 230kV line with steel monopoles and new conductor. | Supplemental | 230 | 28.2 |  | PPL |  |  |  |  | PA | Montour-Columbia | Transmission Structures | Rebuild | EP | 28.2 | Equipment Material Condition, Performance and Risk | 1/31/2029 |  | No | 10/6/2020 | 10/6/2020 | 0
s2376 | PJM MA | Rebuild the 25.9-mile Corten tower section of the Frackville-Columbia 230kV line with steel monopoles and new conductor. | Supplemental | 230 | 91.9 |  | PPL |  |  |  |  | PA | Frackville-Columbia | Transmission Structures | Rebuild | EP | 91.9 | Equipment Material Condition, Performance and Risk | 1/25/2029 |  | No | 10/6/2020 | 10/6/2020 | 10
s2411 | PJM MA | Replace terminal equipment on the Erie South - Gore Junction - Green Garden 115 kV line | Supplemental | 115 | 2.1 |  | PENELEC |  |  |  |  | PA | Erie South - Gore Junction - Green Garden | Transmission Line | Replace | EP | 2.1 | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 12/31/2028 |  | No | 11/18/2020 | 11/18/2020 | 0
s2411.1 | PJM MA | Erie South 115 kV Substation –Replace line relaying (Erie South –GESG Tap 115 kV Line) | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA | Erie South | Relay | Replace | EP |  | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 12/31/2028 |  | No | 11/18/2020 | 11/18/2020 | 0
s2411.2 | PJM MA | Gore Junction 115 kV Substation –Replace line relaying and disconnect switch (GESG Tap – Gore Junction 115 kV Line) | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA | Gore Junction | Relay | Replace | EP |  | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 12/31/2028 |  | No | 11/18/2020 | 11/18/2020 | 0
s2411.3 | PJM MA | Green Garden 115 kV Substation –Replace line relaying (GESG Tap – Green Garden 115 kV Line) | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA | Green Garden | Relay | Replace | EP |  | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 12/31/2028 |  | No | 11/18/2020 | 11/18/2020 | 0
s2412 | PJM MA | Nanty Glo 46 kV Substation work | Supplemental | 46 | 7.9 |  | PENELEC |  |  |  |  | PA | Nanty Glo | Substation | Construct | EP | 7.9 | Operational Flexibility and Efficiency | 12/31/2027 |  | No | 11/18/2020 | 11/18/2020 | 1
s2412.1 | PJM MA | Construct Nanty Glo 46 kV station to six breaker ring bus | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Nanty Glo | Ring Bus | Construct | EP |  | Operational Flexibility and Efficiency | 12/31/2025 |  | No | 11/18/2020 | 11/18/2020 | 1
s2412.2 | PJM MA | Replace line relaying at Bethlehem 33 46 kV Substation on the Nanty Glo - Bethlehem 46kV circuit | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Bethlehem | Relay | Replace | EP |  | Operational Flexibility and Efficiency | 12/31/2025 |  | No | 11/18/2020 | 11/18/2020 | 1
s2412.3 | PJM MA | Replace line relaying at Jackson Road 46 kV Substation on the Nanty Glo - Jackson 46kV circuit | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Jackson Road | Relay | Replace | EP |  | Operational Flexibility and Efficiency | 12/31/2025 |  | No | 11/18/2020 | 11/18/2020 | 1
s2412.4 | PJM MA | Adjust line relaying at Spangler 46 kV Substation on the Nanty Glo - Spangler 46 kV circuit | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Spangler | Relay | Modify | EP |  | Operational Flexibility and Efficiency | 12/31/2025 |  | No | 11/18/2020 | 11/18/2020 | 1
s2481.1 | PJM MA | At Jackson – Replace line trap, and line relaying (on the Jackson – Menges Mills 115 kV Line) | Supplemental | 115 | 1 |  | ME |  |  |  |  | PA | Jackson | Relay | Replace | EP | 1 | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 12/31/2025 |  | No | 1/14/2021 | 1/14/2021 | 30
s2481.2 | PJM MA | At PH Glatfelter – Replace substation conductor, line trap, disconnect switches, circuit breaker, and line relaying (on the Menges Mills – PH Glatfelter 115 kV Line) | Supplemental | 115 | 0 |  | ME |  |  |  |  | PA | Menges Mills | Conductor | Replace | EP |  | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 5/9/2025 |  | No | 1/14/2021 | 1/14/2021 | 20
s2535.1 | PJM MA | Replace in-line switch on the Allegheny Hydro Tap – Allegheny Hydro 46 kV Line | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Raystown/ McConnellstown | Disconnect Switch | Replace | EP |  | Operational Flexibility and Efficiency | 12/31/2023 |  | No | 4/14/2021 | 4/14/2021 | 0
s2536.1 | PJM MA | Replace in-line switch on the Allegheny Hydro Tap – Allegheny Hydro 46 kV Line | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Raystown/ McConnellstown | Disconnect Switch | Replace | EP |  | Operational Flexibility and Efficiency | 12/31/2022 |  | No | 4/14/2021 | 4/14/2021 | 0
s2536.2 | PJM MA | Replace in-line switch on the Allegheny Hydro Tap – RAM Junction 46 kV Line | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Raystown/ McConnellstown | Disconnect Switch | Replace | EP |  | Operational Flexibility and Efficiency | 12/31/2022 |  | No | 4/14/2021 | 4/14/2021 | 0
s2536.3 | PJM MA | Replace in-line switch on the RAM Junction – Piney Ridge 46 kV Line | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Raystown/ McConnellstown | Disconnect Switch | Replace | EP |  | Operational Flexibility and Efficiency | 12/31/2022 |  | No | 4/14/2021 | 4/14/2021 | 0
s2591 | PJM MA | Extend a second circuit to Freeland substation from the HARW-EHAZ #1 69kV line (0.75 Miles) | Supplemental | 69 | 0.6 |  | PPL |  |  |  |  | PA | Freeland | Transmission Line | Build | EP | 0.6 | Customer Service | 10/30/2033 |  | No | 8/13/2021 | 8/13/2021 | 0
s2592 | PJM MA | Extend a second circuit to Gowen City substation from the SUNB-ELDR #2 69kV line (0.05 Miles) | Supplemental | 69 | 0.5 |  | PPL |  |  |  |  | PA | Gowen City | Transmission Line | Build | EP | 0.5 | Customer Service | 10/30/2033 |  | No | 8/13/2021 | 8/13/2021 | 0
s2645.1 | PJM MA | At Carpenter Technology – Replace circuit breaker, and line relaying (Carpenter Technology - West Shore Tap - West Reading 25 69 kV Line) | Supplemental | 69 | 1.05 |  | ME |  |  |  |  | PA | Carpenter Technology | Relay | Replace | EP | 1.05 | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 6/8/2021 |  | No | 9/14/2021 | 9/14/2021 | 0
s2645.2 | PJM MA | At West Reading – Replace circuit breaker, and line relaying (Carpenter Technology - West Shore Tap - West Reading 25 69 kV Line) | Supplemental | 69 | 1.05 |  | ME |  |  |  |  | PA | West Reading | Relay | Replace | EP | 1.05 | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 6/8/2021 |  | No | 9/14/2021 | 9/14/2021 | 0
s2672 | PJM MA | Tap the North Lebanon Tap - Frystown 69 kV line, Install 69 kV switches and Construct ~2 span of 69 kV to customer substation | Supplemental | 69 | 0.8 |  | ME |  |  |  |  | PA | North Lebanon Tap - Frystown | Transmission Line | Construct | EP | 0.8 | Customer Service | 11/1/2021 |  | No | 10/14/2021 | 10/14/2021 | 0
s2713.1 | PJM MA | Baldy 69 kV Substation – Replace line relaying, disconnect switches, substation conductor, and circuit breaker on the Baldy – Kutztown Tap 69 kV Line | Supplemental | 69 | 1.65 |  | ME |  |  |  |  | PA | Baldy | Station Equipment | Replace | EP | 1.65 | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 4/15/2022 |  | No | 3/17/2022 | 3/17/2022 | 0
s2713.2 | PJM MA | Lyons 69 kV Substation – Replace line relaying, and circuit breaker on the Kutztown Tap - Lyons | Supplemental | 69 | 1.65 |  | ME |  |  |  |  | PA | Lyons | Station Equipment | Replace | EP | 1.65 | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 4/15/2022 |  | No | 3/17/2022 | 3/17/2022 | 0
s2750.1 | PJM MA | Baldy 69 kV Substation – Replace line relaying, and substation conductor on the Baldy – Kutztown Tap 69 kV Line | Supplemental | 69 | 0.95 |  | ME |  |  |  |  | PA |  | Relay | Replace | EP | 0.95 | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 5/27/2022 |  | No | 5/16/2022 | 5/16/2022 | 0
s2750.2 | PJM MA | East Topton 69 kV Substation – Replace line relaying, substation conductor and circuit breaker on Kutztown Tap – East Topton | Supplemental | 69 | 0.95 |  | ME |  |  |  |  | PA |  | Relay | Replace | EP | 0.95 | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 5/27/2022 |  | No | 5/16/2022 | 5/16/2022 | 0
s2764 | PJM MA | Rebuild the Piney – Grandview – Titusville – Union City – Erie South 115 kV line using double circuit 115 kV construction adjacent to the existing 115 kV corridor (~82 miles). Energize the line in a six-wire configuration. Rebuild the Piney – Grandview – Titusville – Union City – Erie South 115 kV line using double circuit 115 kV construction adjacent to the existing 115 kV corridor (~82 miles). Energize the line in a six-wire configuration. Upgrade all substation terminals such that the new transmission line is the most limiting element. | Supplemental | 115 | 443 |  | PENELEC |  |  |  |  | PA |  | Transmission Line | Rebuild | EP | 443 | Equipment Material Condition, Performance and Risk | 6/1/2034 |  | No | 7/21/2022 | 7/21/2022 | 0
s2764.1 | PJM MA | Rebuild the Piney – Haynie 115 kV line using double circuit 115 kV construction adjacent to the existing 115 kV | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA |  | Transmission Line | Rebuild | EP |  | Equipment Material Condition, Performance and Risk | 6/1/2034 |  | No | 7/21/2022 | 7/21/2022 | 0
s2764.2 | PJM MA | Rebuild the Haynie – Grandview115 kV line using double circuit 115 kV construction adjacent to the existing 115 kV | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA |  | Transmission Line | Rebuild | EP |  | Equipment Material Condition, Performance and Risk | 6/1/2034 |  | No | 7/21/2022 | 7/21/2022 | 0
s2764.3 | PJM MA | Rebuild the Grandview – Titusville 115 kV line using double circuit 115 kV construction adjacent to the existing 115 kV | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA |  | Transmission Line | Rebuild | EP |  | Equipment Material Condition, Performance and Risk | 6/1/2034 |  | No | 7/21/2022 | 7/21/2022 | 0
s2764.4 | PJM MA | Rebuild the Titusville – Union City 115 kV line using double circuit 115 kV construction adjacent to the existing 115 kV | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA |  | Transmission Line | Rebuild | EP |  | Equipment Material Condition, Performance and Risk | 6/1/2034 |  | No | 7/21/2022 | 7/21/2022 | 0
s2764.5 | PJM MA | Rebuild the Union City – Erie South 115 kV line using double circuit 115 kV construction adjacent to the existing 115 kV | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA |  | Transmission Line | Rebuild | EP |  | Equipment Material Condition, Performance and Risk | 6/1/2034 |  | No | 7/21/2022 | 7/21/2022 | 0
s2803 | PJM MA | Tap the Baldy – Weisenberg 69 kV line. Install 69 kV switches and Construct ~1 span of 69 kV to customer substation | Supplemental | 69 | 0.8 |  | ME |  |  |  |  | PA |  | Substation | Install | EP | 0.8 | Customer Service | 8/3/2023 |  | No | 7/21/2022 | 7/21/2022 | 0
s2805 | PJM MA | Install 3rd Bryn Mawr 138/13 kV 62 MVA transformer with high side breaker. Install two 3000A 63kA 138 kV breakers on the Bryn Mawr straight bus to create two double breaker bus ties. Install two 3000A 63kA 138 kV line breakers on 130-35 (Bryn Mawr-Plymouth) & 130-36 (Bryn Mawr - Llanerch) lines at Bryn Mawr end | Supplemental | 138 | 7 |  | PECO |  |  |  |  | PA | Bryn Mawr | Circuit Breaker | Install | EP | 3 | Customer Service | 12/31/2027 |  | No | 4/19/2022 | 4/19/2022 | 15
s2837 | PJM MA | Extend a new single 69kV tap from the existing Engleside - Greenland #1 69kV line to interconnect a new customer’s 69-12.47kV substation. Build 0.15 miles of new 69kV single circuit line using 556 ACSR conductor | Supplemental | 69 | 1 |  | PPL |  |  |  |  | PA | Engleside/Greenland | Transmission Line | Construct | EP | 1 | Equipment Material Condition, Performance and Risk,Customer Service | 12/31/2028 |  | No | 9/15/2022 | 9/15/2022 | 10
s2890.1 | PJM MA | Install in-line breakers on the Wescosville – Allentown #1 & #2 138kV lines at the existing Sumner substation | Supplemental | 138 | 4 |  | PPL |  |  |  |  | PA | Sumner | Circuit Breaker | Install | EP | 4 | Operational Flexibility and Efficiency | 12/31/2027 |  | No | 1/17/2023 | 1/17/2023 | 10
s2890.2 | PJM MA | Acquire new site and install in-line breaker yard on the Siegfried – Wescosville #1 & #2 138kV | Supplemental | 138 | 4 |  | PPL |  |  |  |  | PA | Siegfried – Wescosville | Circuit Breaker | Install | EP | 4 | Operational Flexibility and Efficiency | 12/31/2027 |  | No | 1/17/2023 | 1/17/2023 | 10
s2894 | PJM MA | Rebuild 11.3 miles of the 12.5 miles of the South Akron – Dillerville #1 & #2 138kV lines with steel poles and 556 ACSR conductor. 1.2 miles of the line was rebuilt in 2013. If possible, any existing recently installed steel monopoles will be incorporated into the design | Supplemental | 138 | 31.5 |  | PPL |  |  |  |  | PA | South Akron – Dillerville | Transmission Line | Rebuild | EP | 31.5 | Equipment Material Condition, Performance and Risk | 12/31/2029 |  | No | 3/16/2023 | 3/16/2023 | 10
s2895 | PJM MA | Rebuild 11 miles of the South Akron – Prince #1 & #2 138kV lines with steel poles and 556 ACSR conductor. If possible, any existing recently installed steel monopoles will be incorporated into the design | Supplemental | 138 | 36 |  | PPL |  |  |  |  | PA | South Akron – Prince | Transmission Line | Rebuild | EP | 36 | Equipment Material Condition, Performance and Risk | 12/31/2029 |  | No | 3/16/2023 | 3/16/2023 | 10
s2896 | PJM MA | Install in-line breakers on the Monroe – Jackson #1 & #2 138kV lines at the existing North Stroudsburg substation. Install in-line breakers on the Siegfried – Jackson #1 & #2 138kV lines at the existing Gilbert substation | Supplemental | 138 | 8 |  | PPL |  |  |  |  | PA | Monroe – Jackson | Circuit Breaker | Install | EP | 8 | Operational Flexibility and Efficiency | 12/31/2026 |  | No | 3/16/2023 | 3/16/2023 | 10
s2902 | PJM MA | Rebuild the 0.66 miles of the Laurel Pumping Tap to Laurel Pumping 69kV with steel poles and 556 ACSR conductor | Supplemental | 69 | 1.1 |  | PPL |  |  |  |  | PA | Laurel Pumping | Transmission Line | Rebuild | EP | 1.1 | Equipment Material Condition, Performance and Risk | 12/31/2025 |  | No | 3/16/2023 | 3/16/2023 | 20
s2936 | PJM WEST | Remove switches A118 and A119 on the Maysville-Sharon Y-301 69 kV Line De-energize roughly 3.6 miles of the Maysville-Sharon 69 kV line from Maysville to the Camp Reynolds tap location. Remove switches A2153, A23, A2151, A260, A261 and A2152 at Greenville Build approximately 3.0 mi of 69 kV line connecting the Camp Reynolds (near TY19) tap to the Canal Tap (near TY104) Add 69 kV line switches with SCADA at Camp Reynolds tap, Greenville Metal tap, and Canal tap Add one 69 kV line switch with SCADA at Trinity tap | Supplemental | 69 | 12.2 |  | ATSI |  |  |  |  | PA | Maysville 69 kV | Substation | Replace | EP | 12.2 | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 6/1/2030 |  | No | 4/21/2023 | 4/21/2023 | 2
s2946.1 | PJM MA | Rebuild and reconductor North Boyertown – West Boyertown 69 kV Line | Supplemental | 69 | 10.3 |  | ME |  |  |  |  | PA | North Boyertown | Transmission Line | Rebuild | EP | 10.3 | Equipment Material Condition, Performance and Risk | 12/31/2027 |  | No | 4/20/2023 | 4/20/2023 | 0
s2946.2 | PJM MA | North Boyertown 69 kV Substation Replace substation conductor | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | North Boyertown | Conductor | Replace | EP | 0 | Equipment Material Condition, Performance and Risk | 12/31/2027 |  | No | 4/20/2023 | 4/20/2023 | 0
s2946.3 | PJM MA | West Boyertown 69 kV Substation Replace substation conductor | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | West Boyertown | Conductor | Replace | EP | 0 | Equipment Material Condition, Performance and Risk | 12/31/2027 |  | No | 4/20/2023 | 4/20/2023 | 0
s2948 | PJM MA | Rebuild McKnights Gap 69-13.2 kV Substation and Install new 69 kV switches | Supplemental | 69 | 0.8 |  | ME |  |  |  |  | PA | McKnights Gap | Substation | Rebuild | EP | 0.8 | Customer Service | 8/1/2025 |  | No | 4/20/2023 | 4/20/2023 | 0
s2949 | PJM MA | Tap the Saxton – Shade Gap 115 kV Line (Saxton – Three Springs 115 kV Line segment) and Construct ~8.64 miles of 115 kV line towards the customer. Install one 115 kV revenue metering package nd three 1200 A SCADA controlled disconnect switches. | Supplemental | 115 | 23.96 |  | PENELEC |  |  |  |  | PA | Saxton | Transmission Line | Tap | EP | 23.96 | Customer Service | 12/1/2025 |  | No | 4/20/2023 | 4/20/2023 | 1
s2963 | PJM MA | Remove 16.5 miles of the existing Lycoming – Lewisburg 69kV line. Remaining 2 miles will be rebuilt as part of s0968.4 and will become part of the Milton – Lewisburg line. | Supplemental | 69 | 3.5 |  | PPL |  |  |  |  | PA | Lycoming | Transmission Line | Upgrade | EP | 3.5 | Equipment Material Condition, Performance and Risk | 6/1/2027 |  | No | 5/18/2023 | 5/18/2023 | 10
s2997 | PJM WEST | Create the Vankirk Substation, Construct a new 10 breaker 138 kV breaker-and-a-half substation, Loop in the Dutch Fork, Washington 138 kV Line, Loop in the Gordon, Lagonda 138 kV Line, Loop in the Gordon, Charleroi 138 kV Line, At Washington: Replace limiting substation conductor and wave trap, At Dutch Fork: Replace limiting substation conductor, At Gordon: Replace limiting substation conductor, relaying, and wave trap, At Claysville: Replace limiting substation conductor, At Charleroi: Replace limiting substation conductor and wave trap | Supplemental | 138 | 31.7 |  | APS |  |  |  |  | PA | Vankirk Substation | Relay | Construct | EP | 31.7 | Operational Flexibility and Efficiency | 3/31/2027 |  | No | 6/16/2023 | 6/16/2023 | 4
s3017 | PJM MA | Install three SCADA controlled transmission line switches.Construct approximately 0.2 miles of transmission line using 556 ACSR 26/7 from tap point to customer substation. Install one 115 kV revenue metering package at customer substation. Modify relay settings at Middletown Junction and Smith Street substations | Supplemental | 115 | 4.9 |  | ME |  |  |  |  | PA | Middletown | Transmission Line | Construct | EP | 4.9 | Customer Service | 7/3/2026 |  | No | 7/20/2023 | 7/20/2023 | 0
s3082.1 | PJM MA | Extend a new double circuit 69kV tap from the existing Harwood – East Hazelton 1 & 2 69kV lines line to interconnect a PPL Distribution owned 69-12.47kV substation (McAdoo). | Supplemental | 69 | 2 |  | PPL |  |  |  |  | PA | Harwood | Transmission Line | Install | EP | 2 | Customer Service | 2/28/2026 |  | No | 7/20/2023 | 7/20/2023 | 10
s3082.2 | PJM MA | Harwood – Freeland #1 & #2: Add a second circuit from Harwood substation to Cando tap (1.3 miles), reconfigure existing circuits from Cando and Harleigh, and install 3.6 miles of new double circuit 69kV from Harleigh to East Hazelton. | Supplemental | 69 | 16.2 |  | PPL |  |  |  |  | PA | Harwood | Transmission Line | Install | EP | 16.1 | Customer Service | 12/31/2027 |  | No | 7/20/2023 | 7/20/2023 | 0
s3083.1 | PJM MA | Rebuild the Sunbury – Lock Haven 69kV line (~39 miles) to double circuit 69kV operation with 795 ACSR conductor. Install new line terminals at Sunbury and Lock Haven substations to accommodate the new circuit. | Supplemental | 69 | 103 |  | PPL |  |  |  |  | PA | Lock Haven | Transmission Line | Rebuild | EP | 103 | Equipment Material Condition, Performance and Risk | 12/30/2027 |  | No | 7/20/2023 | 7/20/2023 | 0
s3084.1 | PJM MA | Rebuild the Buxmont 2 - Upper Hanover Tap 69kV line (~9.14 miles) to single circuit, future double circuit 69kV operation with 556 ACSR conductor. | Supplemental | 69 | 18 |  | PPL |  |  |  |  | PA | Buxmont | Transmission Line | Rebuild | EP | 18 | Equipment Material Condition, Performance and Risk | 5/31/2026 |  | No | 9/14/2023 | 9/14/2023 | 0
s3085.1 | PJM MA | Rebuild the Lycoming – Williamsport #2 69kV line (2.1 miles) to double circuit 69kV operation with 556 ACSR conductor. Remove 1.2 miles of the Lycoming – Williamsport #1 69kV line. | Supplemental | 69 | 6 |  | PPL |  |  |  |  | PA | Lycoming | Transmission Line | Rebuild | EP | 6 | Equipment Material Condition, Performance and Risk | 12/30/2027 |  | No | 10/19/2023 | 10/19/2023 | 10
s3087.1 | PJM MA | Rebuild the PPL section of the Hunlock-Glen Brook 69kV line (3.5 miles) to single circuit 69kV operation with 556 ACSR conductor. | Supplemental | 69 | 7 |  | PPL |  |  |  |  | PA | Hunlock | Transmission Line | Rebuild | EP | 7 | Equipment Material Condition, Performance and Risk | 9/30/2027 |  | No | 10/19/2023 | 10/19/2023 | 10
s3096.1 | PJM WEST | Construct a new 8-mile 138 kV line between Ethel Springs and Bethlen substations using 954 ACSR conductor. The following work will be performed at neighboring substations: At Social Hall: Replace substation conductor, wave trap, and circuit breaker At Vasco:Construct a 4-breaker 138 kV ring bus, At Edgewater Tap: Install (3) SCADA controlled switches, At Loyalhanna: Replace substation conductor on the Bethlen 138 kV line terminal, At Ethel Springs: Convert the 138 kV yard into a 4-breaker ring bus, At Bethlen: Convert the 138 kV yard into a 3-breaker ring bus New line ratings: Vasco Tap – Social Hall 138 kV: 297 / 365 MVA (SN / SE), Bethlen – Loyalhanna 138 kV: 309 / 376 MVA (SN / SE), Bethlen – Ethel Springs: 308 / 376 MVA (SN / SE) | Supplemental | 138 | 59.6 |  | APS |  |  |  |  | PA | Ethel Springs – Bethlen | Transmission Line | Construct | EP | 59.6 | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 12/15/2028 |  | No | 10/20/2023 | 10/20/2023 | 0
s3107.1 | PJM WEST | At Franklin Substation, replace circuit breaker, disconnect switches, line trap, substation conductor and relaying. At Pursely Substation, replace substation conductor and relaying | Supplemental | 138 | 2.2 |  | APS |  |  |  |  | PA | Franklin – Pursley | Circuit Breaker | Replace | EP | 2.2 | Equipment Material Condition, Performance and Risk | 6/13/2026 |  | No | 11/17/2023 | 11/17/2023 | 4
s3161.1 | PJM WEST | At Fawn Substation, replace circuit breaker, disconnect switches, line trap, substation conductor and relaying. At Gobain Substation, replace circuit breaker, disconnect switches, line trap, substation conductor and relaying. | Supplemental | 138 | 3.5 |  | APS |  |  |  |  | PA | Fawn-Gobain | Relay | Replace | EP | 3.5 | Equipment Material Condition, Performance and Risk | 11/21/2025 |  | No | 12/15/2023 | 12/15/2023 | 15
s3186.1 | PJM MA | Rebuild approx. 4.5 miles with new dual circuit, weathering steel monopole structures and 959.6 kcmil ACSS conductor. Replace various substation equipment at Plymouth Meeting and Upper Merion substations to make the conductor the limiting element. | Supplemental | 230 | 50.2 |  | PECO |  |  |  |  | PA | Plymouth Meeting | Transmission Structures | Rebuild | EP | 29.2 | Equipment Material Condition, Performance and Risk | 11/30/2027 |  | No | 10/31/2023 | 10/31/2023 | 25
s3210.1 | PJM MA | Extend a second circuit to Lavino substation from the Berks – Lavino #2 69kV line (0.05 Miles) | Supplemental | 69 | 0.9 |  | PPL |  |  |  |  | PA | Lavino | Transmission Line | Upgrade | EP | 0.9 | Customer Service | 12/1/2026 |  | No | 1/18/2024 | 1/18/2024 | 10
s3264.1 | PJM MA | Rebuild North Lebanon – Fredericksburg 73 69 kV Line as double circuit. At North Lebanon Substation Add 69 kV breaker Replace limiting terminal equipment At Fredericksburg Substation | Supplemental | 69 | 13.6 |  | ME |  |  |  |  | PA | North Lebanon | Transmission Line | Rebuild | EP | 13.6 | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 12/31/2027 |  | No | 11/16/2023 | 11/16/2023 | 20
s3269.1 | PJM MA | At Yeagertown Substation: Replace the Yeagertown No. 1 230-46 kV Transformer. Replace transformer relaying. | Supplemental | 230 | 3.5 |  | PENELEC |  |  |  |  | PA | Yeagertown | Substation | Replace | EP | 3.5 | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 10/17/2025 |  | No | 3/5/2024 | 3/5/2024 | 0
s3271.1 | PJM MA | Replace relaying at Altoona and Hollidaysburg substations Replace disconnect switches and substation conductor at Altoona and Hollidaysburg substations | Supplemental | 46 | 1.5 |  | PENELEC |  |  |  |  | PA | Altoona | Relay | Replace | EP | 1.5 | Equipment Material Condition, Performance and Risk | 6/1/2027 |  | No | 3/14/2024 | 3/14/2024 | 5
s3287.1 | PJM MA | Convert Campbelltown into a five breaker 69 kV ring bus At Campbelltown Substation: Replace two 69 kV circuit breakers and associated disconnect switches.Install two new 69 kV circuit breakers and associated disconnect switches. Relocate one existing 69 kV circuit breaker and associated disconnect switches. Install new bus conductor. Install four standard transmission line relay panels. Replace substation conductor. At North Lebanon Substation: Replace one 69 kV circuit breaker. Replace one 69 kV disconnect switch. Install one standard transmission line relay panel. Replace substation conductor At Middletown Substation: Replace one 69 kV circuit breaker. Replace one 69 kV disconnect switch. Install one standard transmission line relay panel § Replace substation conductor | Supplemental | 69 | 10 |  | ME |  |  |  |  | PA | Campbelltown | Circuit Breaker | Upgrade | EP | 10 | Equipment Material Condition, Performance and Risk | 12/21/2026 |  | No | 2/15/2024 | 2/15/2024 | 10
s3288.1 | PJM MA | Rebuild approximately 5.9 miles of the Carpenter Technology – South Reading 69 kV Line. At South Reading Substation: Replace 69 kV breaker, line-side disconnect and line relaying. Install surge arresters At Carpenter Technology Substation: Replace 69 kV line-side disconnect and line relaying At Glenside Substation: Replace 69 kV motor-operated airbreak switches, disconnects and CCVTs | Supplemental | 69 | 15.2 |  | ME |  |  |  |  | PA | Car Tech - Glenside - S. Reading | Substation | Rebuild | EP | 15.2 | Equipment Material Condition, Performance and Risk | 6/9/2028 |  | No | 2/15/2024 | 2/15/2024 | 1
s3290.1 | PJM MA | At Niles Valley Substation: Construct a 115 kV, six breaker ring bus. Remove Niles Valley No. 1 115-34.5 kV Transformer. Remove the 115 kV bypass switch between the Wellsboro and Mansfield line exits (s2835) upon ring bus completion. Adjust relay settings | Supplemental | 115 | 16 |  | PENELEC |  |  |  |  | PA | Niles Valley | Substation | Upgrade | EP | 16 | Operational Flexibility and Efficiency | 6/1/2028 |  | No | 2/15/2024 | 2/15/2024 | 3
s3291.1 | PJM MA | Provide 115 kV service from the Warren – Falconer 115 kV Line: Tap the Warren –Falconer 115 kV Line, install switches and build approximately 190 ft of transmission line from the tap point to customer substation. Construct new 115 kV switching station near the Warren - Falconer 115 kV Line Install two SCADA controlled transmission line disconnect switches with full load break interrupters Install one 115 kV circuit breaker (Normally Open) Install one 115 kV revenue metering package at customer substation Adjust relay settings at Warren Substation solution component removed on 5/15/2025 - Operate disconnect switch towards Falconer Substation as normally open) | Supplemental | 115 | 1.5 |  | PENELEC |  |  |  |  | PA | Warren | Transmission Line | Construct | EP | 8.45 | Customer Service | 4/28/2028 |  | No | 2/15/2024 | 2/15/2024 | 3 |  | 4/28/2028
s3292.1 | PJM MA | Provide 115 kV service from the East Sayre – East Towanda 115 kV Line: Tap the East Sayre – East Towanda 115 kV Line, install switches and build approximately 250 feet of transmission line to the customer substation. Install three 115 kV motor-operated disconnects with SCADA. Install one wave trap | Supplemental | 115 | 1.67 |  | PENELEC |  |  |  |  | PA | East Towanda | Substation | Upgrade | EP | 1.67 | Customer Service | 6/1/2027 |  | No | 2/15/2024 | 2/15/2024 | 15
s3293.1 | PJM MA | Provide 115 kV service from the Carlisle Pike – Roxbury 115 kV Line: Tap the Carlisle Pike – Roxbury 115 kV Line, install switches and build approximately 1.76 miles of transmission line to the customer substation. Install one new 115 kV breaker at Carlisle Pike Substation. Install one new 115 kV revenue metering package at the customer substation Adjust relaying at Carlisle Pike Substation and Roxbury Substation | Supplemental | 115 | 8 |  | PENELEC |  |  |  |  | PA | Roxbury - Carlisle Pike | Substation | Upgrade | EP | 8 | Customer Service | 12/31/2027 |  | No | 2/15/2024 | 2/15/2024 | 4
s3300.1 | PJM MA | Construct new 69 kV line from Structure #37 on the S. Lebanon –Frystown/Rehrersburg 83 69 kV Line to the Northkill Substation (Approximately 8.9 miles). | Supplemental | 69 | 19.6 |  | ME |  |  |  |  | PA | Lebanon | Transmission Line | Construct | EP | 19.6 | Equipment Material Condition, Performance and Risk | 12/31/2027 |  | No | 11/16/2023 | 11/16/2023 | 1
s3300.2 | PJM MA | Create a new line terminal and add a fourth 69 kV breaker at Northkill Substation. Install two (2) sets of 69 kV disconnect switches with SCADA control and Auto-Transfer Scheme. Install 1 set of 69 kV disconnect switches with SCADA control on the tap to Rehrersburg Substation. | Supplemental | 69 | 0.8 |  | ME |  |  |  |  | PA | Northkill | Transmission Line | Upgrade | EP | 0.8 | Equipment Material Condition, Performance and Risk | 12/31/2027 |  | No | 11/16/2023 | 11/16/2023 | 1
s3300.3 | PJM MA | Rebuild the Bernville-Northkill 845 69 kV Line (0.84 mi) to double circuit construction. New line will share ~0.94 miles of common structure with newly rebuilt 825 line Tranmission Line Ratings: | Supplemental | 69 | 3.73 |  | ME |  |  |  |  | PA | Bernville | Transmission Line | Rebuild | EP | 3.73 | Equipment Material Condition, Performance and Risk | 12/31/2027 |  | No | 11/16/2023 | 11/16/2023 | 1
s3311.1 | PJM MA | Break the existing Juniata (JUNI)-Three Mile Island (TMIS) 500kV line and extend the lines 0.1 miles into a new four bay Bernheisel (BERN) 500kV breaker-and-a-half yard. | Supplemental | 500 | 40 |  | PPL |  |  |  |  | PA | Three Mile Island | Transmission Line | Modify | EP | 40 | Customer Service | 6/30/2027 |  | No | 4/2/2024 | 4/2/2024 | 10
s3311.2 | PJM MA | Rebuild the existing JUNI-TMIS 500kV line to double circuit for 13.3 miles from Juniata substation to Bernheisel substation. PPL’s standard is to have three sources into a BES substation. | Supplemental | 500 | 117 |  | PPL |  |  |  |  | PA | Three Mile Island | Transmission Line | Rebuild | EP | 117 | Customer Service | 6/30/2027 |  | No | 4/2/2024 | 4/2/2024 | 10
s3311.3 | PJM MA | Install four 500-138kV transformers. | Supplemental | 500 | 62 |  | PPL |  |  |  |  | PA | Three Mile Island | Transformer | Install | EP | 62 | Customer Service | 6/30/2027 |  | No | 4/2/2024 | 4/2/2024 | 10
s3311.4 | PJM MA | Install a six bay 138kV yard. | Supplemental | 138 | 15 |  | PPL |  |  |  |  | PA | Three Mile Island | Substation | Install | EP | 15 | Customer Service | 6/30/2027 |  | No | 4/2/2024 | 4/2/2024 | 10
s3311.5 | PJM MA | Install two 138kV capacitor banks | Supplemental | 138 | 7 |  | PPL |  |  |  |  | PA | Three Mile Island | Capacitor | Install | EP | 7 | Customer Service | 6/30/2027 |  | No | 4/2/2024 | 4/2/2024 | 10
s3311.6 | PJM MA | Extend six 138kV lines to customer facility | Supplemental | 138 | 3 |  | PPL |  |  |  |  | PA | Three Mile Island | Substation | Modify | EP | 3 | Customer Service | 6/30/2027 |  | No | 4/2/2024 | 4/2/2024 | 10
s3349.1 | PJM MA | Rebuild 2.6 miles of the existing Harwood – East Hazelton 1 & 2 69kV lines from Harwood Substation to the MCCI tap with 795 ACSR conductor | Supplemental | 69 | 6 |  | PPL |  |  |  |  | PA | Harwood | Substation | Rebuild | EP | 6 | Equipment Material Condition, Performance and Risk | 12/1/2026 |  | No | 12/13/2023 | 12/13/2023 | 0
s3350.1 | PJM MA | Rebuild the 0.1-mile Cass tap from the FRACAUBU 69kV line. Remove 69kV tap from FRACFISH #3. | Supplemental | 69 | 0.9 |  | PPL |  |  |  |  | PA | Cass | Transmission Line | Rebuild | EP | 0.9 | Customer Service | 5/31/2026 |  | No | 12/13/2023 | 12/13/2023 | 0
s3383.1 | PJM MA | Rebuild Tacony 69kV substation to 230kV standards by cutting into the 220-56 Eddington/Holmesburg/Richmond 230kV line in and out of the substation | Supplemental | 230 | 11 |  | PECO |  |  |  |  | PA | Tacony | Substation | Rebuild | EP | 11 | Equipment Material Condition, Performance and Risk | 12/31/2028 |  | No | 6/4/2024 | 6/4/2024 | 12
s3383.2 | PJM MA | Replace the existing 69-13kV 40MVA transformers with two new 230-13kV 62MVA units | Supplemental | 230 | 6 |  | PECO |  |  |  |  | PA | Tacony | Transformer | Replace | EP | 6 | Equipment Material Condition, Performance and Risk | 12/31/2028 |  | No | 6/4/2024 | 6/4/2024 | 15
s3384.1 | PJM MA | Rebuild approx. 6.24 miles of the 220-31 Planebrook – Bradford 230kV line with new dual circuit, weathering steel monopole structures and 959.6 kcmil ACSS/TW conductor. Replace various substation equipment at Planebrook and Bradford substations | Supplemental | 230 | 36 |  | PECO |  |  |  |  | PA | Planebrook | Substation | Rebuild | EP | 36 | Equipment Material Condition, Performance and Risk | 12/31/2028 |  | No | 6/4/2024 | 6/4/2024 | 5
s3385.1 | PJM MA | Rebuild approx. 4.5 miles of the 220-02 Planebrook – Bradford 230kV line with new dual circuit, weathering steel monopole structures and 959.6 kcmil ACSS/TW conductor. Replace various substation equipment at Planebrook and Bradford substations | Supplemental | 230 | 36 |  | PECO |  |  |  |  | PA | Planebrook | Substation | Rebuild | EP | 36 | Equipment Material Condition, Performance and Risk | 12/31/2029 |  | No | 6/4/2024 | 6/4/2024 | 5
s3391.1 | PJM MA | Extend a new double circuit 69kV tap from the existing Cumberland - Carlisle #1 & #2 69kV lines to interconnect the new Stonehouse 69-12.47kV substation. Build 0.1 miles of new 69kV double circuit line using 556 ACSR conductor. Initial loading of ~18MVA. | Supplemental | 69 | 1.4 |  | PPL |  |  |  |  | PA | Stonehouse 69kV Taps,Carlisle | Transmission Line | Tap | EP |  | Equipment Material Condition, Performance and Risk | 3/1/2027 |  | No | 7/18/2024 | 7/18/2024 | 0
s3397.1 | PJM MA | Install two main line and one tap line SCADA controlled switches • Construct one span of 34.5 kV line between tap point and customer substation • Review/modify relay settings on the Eaton Crest – Woodbine (R226) 34.5 kV line | Supplemental | 34.5 | 1.4 |  | JCPL |  |  |  |  | PA | Eaton Crest | Transmission Line | Tap | EP | 1.4 | Customer Service | 4/14/2026 |  | No | 10/19/2023 | 10/19/2023 | 0
s3399.1 | PJM MA | At Taylor Lane Substation, replace relaying | Supplemental | 34.5 | 0.64 |  | JCPL |  |  |  |  | PA | Taylor Lane | Relay | Replace | EP | 0.64 | Equipment Material Condition, Performance and Risk | 12/31/2026 |  | No | 10/19/2023 | 10/19/2023 | 30
s3400.1 | PJM MA | At Bradley Beach Substation, replace relaying | Supplemental | 34.5 | 0.64 |  | JCPL |  |  |  |  | PA | Bradley Beach | Relay | Replace | EP | 0.64 | Equipment Material Condition, Performance and Risk | 6/1/2026 |  | No | 10/19/2023 | 10/19/2023 | 20
s3401.1 | PJM MA | At East Flemington Substation, replace relaying | Supplemental | 34.5 | 0.64 |  | JCPL |  |  |  |  | PA | East Flemington | Relay | Replace | EP | 0.64 | Equipment Material Condition, Performance and Risk | 12/31/2025 |  | No | 10/19/2023 | 10/19/2023 | 0
s3403.1 | PJM MA | At McGuire Substation, replace relaying | Supplemental | 34.5 | 0.64 |  | JCPL |  |  |  |  | PA | McGuire | Relay | Replace | EP | 0.64 | Equipment Material Condition, Performance and Risk | 3/1/2026 |  | No | 10/19/2023 | 10/19/2023 | 30
s3404.1 | PJM MA | At Smithburg Substation, replace relaying | Supplemental | 34.5 | 0.64 |  | JCPL |  |  |  |  | PA | Smithburg | Relay | Replace | EP | 0.64 | Equipment Material Condition, Performance and Risk | 12/31/2027 |  | No | 10/19/2023 | 10/19/2023 | 0
s3405.1 | PJM MA | At Lebanon Substation, replace relaying | Supplemental | 34.5 | 1.28 |  | JCPL |  |  |  |  | PA | Lebanon | Relay | Replace | EP | 1.28 | Equipment Material Condition, Performance and Risk | 5/31/2028 |  | No | 10/19/2023 | 10/19/2023 | 0
s3406.1 | PJM MA | At Washington Substation, replace relaying | Supplemental | 34.5 | 1.28 |  | JCPL |  |  |  |  | PA | Washington | Relay | Replace | EP | 1.28 | Equipment Material Condition, Performance and Risk | 6/1/2028 |  | No | 10/19/2023 | 10/19/2023 | 0
s3407.1 | PJM MA | At Whitesville Substation, replace relaying | Supplemental | 34.5 | 1.92 |  | JCPL |  |  |  |  | PA | Whitesviille | Relay | Replace | EP | 1.92 | Equipment Material Condition, Performance and Risk | 6/1/2028 |  | No | 10/19/2023 | 10/19/2023 | 0
s3408.1 | PJM MA | At Portage Substation, replace the 46 kV structure, including 46 kV line switches. | Supplemental | 46 | 3.7 |  | PENELEC |  |  |  |  | PA | Portage | Substation | Replace | EP | 3.7 | Equipment Material Condition, Performance and Risk | 10/30/2026 |  | No | 10/19/2023 | 10/19/2023 | 4
s3411.1 | PJM MA | Replace relaying and limiting substation conductor at Atlantic and Red Bank 230 kV Substations | Supplemental | 230 | 2 |  | JCPL |  |  |  |  | PA | Atlantic | Substation | Replace | EP | 2 | Operational Flexibility and Efficiency,Equipment Material Condition, Performance and Risk | 12/31/2027 |  | No | 10/31/2023 | 10/31/2023 | 4
s3412.1 | PJM MA | Replace limiting substation conductor at Eaton Crest 230 kV ? Replace relaying at Atlantic and Red Bank 230 kV substations | Supplemental | 230 | 2 |  | JCPL |  |  |  |  | PA | Atlantic | Substation | Replace | EP | 2 | Operational Flexibility and Efficiency,Equipment Material Condition, Performance and Risk | 12/31/2028 |  | No | 10/31/2023 | 10/31/2023 | 4
s3422.2 | PJM MA | At Erie West, replace relaying & line trap (Erie South – Erie West 345 kV) | Supplemental | 345 | 10.7 |  | PENELEC |  |  |  |  | PA | Erie West | Substation | Replace | EP | 10.7 | Equipment Material Condition, Performance and Risk | 6/3/2028 |  | No | 12/5/2023 | 12/5/2023 | 0
s3423.1 | PJM MA | At Erie South, replace relaying & line trap (Erie South – Warren 230 kV) | Supplemental | 230 | 10.7 |  | PENELEC |  |  |  |  | PA | Erie South | Substation | Replace | EP | 10.7 | Equipment Material Condition, Performance and Risk | 6/3/2028 |  | No | 12/5/2023 | 12/5/2023 | 0
s3432.1 | PJM MA | Replace the Kittatinny No. 4 230-34.5 kV Transformer with a 125 MVA unit. Replace the transformer relaying. | Supplemental | 230/34.5 | 5 |  | JCPL |  |  |  |  | PA | Kittatinny | Transformer | Replace | EP | 5 | Equipment Material Condition, Performance and Risk | 5/31/2028 |  | No | 6/4/2024 | 6/4/2024 | 4
s3433.1 | PJM MA | Replace the Lakewood Gen No. 6 230-34.5 kV Transformer with a 125 MVA unit. Replace the transformer relaying | Supplemental | 230/34.5 | 6 |  | JCPL |  |  |  |  | PA | Lakewood | Transformer | Replace | EP | 6 | Equipment Material Condition, Performance and Risk | 6/30/2028 |  | No | 6/4/2024 | 6/4/2024 | 20
s3434.1 | PJM MA | North Temple – Allentown Cement 69 kV Line. Install three SCADA controlled transmission line switches. Construct approximately 1-2 spans of transmission line from tap point to customer substation. Install one 69 kV revenue metering package at customer substation. Modify relay settings at North Temple and Allentown Cement substations | Supplemental | 69 | 0.7 |  | ME |  |  |  |  | PA | North Temple – Allentown Cement | Transmission Line | Build | EP | 0.7 | Customer Service | 6/1/2025 |  | No | 6/13/2024 | 6/13/2024 | 0
s3435.1 | PJM MA | Hunterstown – North Hanover 115 kV Line. Install three SCADA controlled transmission line switches. Construct approximately 1-2 spans of transmission line from tap point to customer substation. Install one 115 kV revenue metering package at customer substation. Modify relay settings at North Hanover and Hunterstown substations | Supplemental | 115 | 1.7 |  | ME |  |  |  |  | PA | Hunterstown – North Hanover | Transmission Line | Build | EP | 1.7 | Customer Service | 12/1/2027 |  | No | 6/13/2024 | 6/13/2024 | 2
s3438.1 | PJM MA | Replace Washington 34.5 kV C705, P718, Q719, W23A, W23B, U723A and U723B circuit breakers. Replace bus and line disconnect switches, Install line disconnect switches for C705 and Q719 breakers | Supplemental | 34.5 | 5.4 |  | JCPL |  |  |  |  | PA | Washington | Circuit Breaker | Replace | EP | 5.4 | Equipment Material Condition, Performance and Risk | 6/30/2027 |  | No | 7/18/2024 | 7/18/2024 | 20
s3439.1 | PJM MA | Build new Galloping Hill 230/69 kV sunstation. Cut and loop Springfield Rd. – Aldene 230kV circuit into new 230/69kV station. Install one (1) 230/69kV transformer. Construct a 69/13kV substation. Cut and loop Springfield Rd. – Roselle 69kV circuit into the new substation. nstall two (2) 69/13kV transformers. | Supplemental | 230/69 | 72.4 |  | PSEG |  |  |  |  | PA | Galloping Hill | Substation | Build | EP | 72.4 | Customer Service | 12/30/2029 |  | No | 7/9/2024 | 7/9/2024 | 0
s3439.2 | PJM MA | Construct a 69/13kV substation. Cut and loop Springfield Rd. – Roselle 69kV circuit into the new substation | Supplemental | 230/69 | 51.4 |  | PSEG |  |  |  |  | PA | Galloping Hill | Substation | Build | EP | 51.4 | Customer Service | 12/30/2029 |  | No | 7/9/2024 | 7/9/2024 | 0
s3439.3 | PJM MA | Install one (1) 230/69kV transformer. Install two (2) 69/13kV transformers. | Supplemental | 230/69 | 45.2 |  | PSEG |  |  |  |  | PA | Galloping Hill | Substation | Build | EP | 45.2 | Customer Service | 12/30/2029 |  | No | 7/9/2024 | 7/9/2024 | 0
s3528.1 | PJM MA | Tomhicken 230kV Switchyard: Install a six bay BAAH 230kV switchyard with a 125MVAR Capacitor bank | Supplemental | 230 | 45 |  | PPL |  |  |  |  | PA | Tomhicken | Substation | Install | EP | 45 | Customer Service | 12/31/2026 |  | No | 8/6/2024 | 8/6/2024 | 10
s3528.10 | PJM MA | Extend a double circuit 230kV (built for 500kV) for ~9 miles from Nescopeck to Tomhicken on existing PPL ROW. Extend single circuit 230kV (built for 500kV DlbCir) for 2.7 miles from Tomhicken to Harwood and terminate at Harwood. This will create the Nescopeck - Tomhicken 230kV and Nescopeck - Harwood 230kV lines. | Supplemental | 230 | 80.5 |  | PPL |  |  |  |  | PA | Nescopeck | Transmission Line | Rebuild | EP | 80.5 | Customer Service | 2/29/2028 |  | No | 8/6/2024 | 8/6/2024 | 10
s3528.11 | PJM MA | Tomhicken Customer Taps 230kV lines: Install four 230kV lead lines for approximately 0.1 miles from Tomhicken 230kV switchyard to the customer facility. | Supplemental | 230 | 3.8 |  | PPL |  |  |  |  | PA | Tomhicken | Transmission Line | Rebuild | EP | 3.8 | Customer Service | 12/31/2026 |  | No | 8/6/2024 | 8/6/2024 | 10
s3528.2 | PJM MA | Nescopeck 230kV Switchyard: Install a new three bay BAAH 230kV switchyard. | Supplemental | 230 | 29.5 |  | PPL |  |  |  |  | PA | Nescopeck | Substation | Install | EP | 29.5 | Customer Service | 2/29/2028 |  | No | 8/6/2024 | 8/6/2024 | 10
s3528.3 | PJM MA | Susquehanna 230kV Switchyard: Install a new line terminal at Susquehanna 230kV yard by installing new dead-end, 230kV breaker, and associated equipment. | Supplemental | 230 | 2 |  | PPL |  |  |  |  | PA | Susquehanna | Substation | Install | EP | 2 | Customer Service | 2/29/2028 |  | No | 8/6/2024 | 8/6/2024 | 10
s3528.4 | PJM MA | Susquehanna T10 230kV Switchyard: Install a new BAAH bay at the Susquehanna T10 230kV yard. Install two dead-ends, three 230kV breakers and associated equipment. | Supplemental | 230 | 6 |  | PPL |  |  |  |  | PA | Susquehanna | Substation | Install | EP | 6 | Customer Service | 6/1/2027 |  | No | 8/6/2024 | 8/6/2024 | 10
s3528.5 | PJM MA | Harwood 230kV Substation: Install new line terminal in the Harwood 230kV switchyard, install one dead-end, two breakers, and associated equipment. New bay to be DBDB initial and future BAAH. | Supplemental | 230 | 4 |  | PPL |  |  |  |  | PA | Harwood | Substation | Install | EP | 4 | Customer Service | 12/31/2026 |  | No | 8/6/2024 | 8/6/2024 | 10
s3528.6 | PJM MA | SUSQ-HARW #1 & #2 230kV Lines: Bifurcate the Susquehanna – Harwood #1 & #2 230kV and terminate at the new Tomhicken 230kV switchyard. Extend lines approximately 0.25 into the new Tomhicken 230kV switchyard. | Supplemental | 230 | 3.7 |  | PPL |  |  |  |  | PA | Susquehanna | Transmission Line | Rebuild | EP | 3.7 | Customer Service | 12/31/2026 |  | No | 8/6/2024 | 8/6/2024 | 10
s3528.7 | PJM MA | Sunbury - Susquehanna # 1 230kV Line: Bifurcate the Sunbury – Susquehanna #1 230kV into the new Nescopeck 230kV switchyard. Extend lines approximately 0.2 into the new Nescopeck 230kV switchyard. | Supplemental | 230 | 1.85 |  | PPL |  |  |  |  | PA | Sunbury | Transmission Line | Rebuild | EP | 1.85 | Customer Service | 2/29/2028 |  | No | 8/6/2024 | 8/6/2024 | 10
s3528.8 | PJM MA | Sunbury - Susquehanna # 1 230kV Line Partial Rebuild: Rebuild the Sunbury - Susquehanna # 1 230kV Line to double circuit 230kV for 3.9 miles from the Susquehanna 230kV yard to the new Nescopeck 230kV switchyard. | Supplemental | 230 | 17.2 |  | PPL |  |  |  |  | PA | Sunbury | Transmission Line | Rebuild | EP | 17.2 | Customer Service | 2/29/2028 |  | No | 8/6/2024 | 8/6/2024 | 10
s3528.9 | PJM MA | Glen Brook - Susquehanna 230kV Line: Bifurcate the Glen Brook – Susquehanna 230kV line into the Susquehanna T10 yard. Extend lines approximately 0.25 into the existing Susquehanna T10 230kV switchyard. | Supplemental | 230 | 3 |  | PPL |  |  |  |  | PA | Glen Brook | Transmission Line | Rebuild | EP | 3 | Customer Service | 6/1/2027 |  | No | 8/6/2024 | 8/6/2024 | 10
s3547.1 | Not Specified | Construct a new five bay BAAH 138kV switchyard near the customer's facility. | Supplemental | 138 | 34 |  | PPL |  |  |  |  | PA | Pitney | Switching station | Build | EP |  | Customer Service | 6/1/2027 |  | No | 11/6/2024 | 11/6/2024 | 0
s3547.2 | Not Specified | Bifurcate the South Akron - Prince #1 & #2 138kV and terminate at the new Pitney 138kV switchyard. Extend the 138kV lines approximately 0.2 miles into the new Pitney 138kV switchyard. | Supplemental | 138 | 3 |  | PPL |  |  |  |  | PA,OH | Pitney,South Akron,Pitney^South Akron | Transmission Line | Install | EP |  | Customer Service | 6/1/2027 |  | No | 11/6/2024 | 11/6/2024 | 0
s3547.3 | Not Specified | Extend three 138kV circuits for approximately 0.1 miles from the Pitney 138kV switchyard to the customer's facility. | Supplemental | 138 | 3.5 |  | PPL |  |  |  |  | PA | Donnelley Gravure,Pitney,Donnelley Gravure^Pitney | Transmission Line | Build | EP |  | Customer Service | 6/1/2027 |  | No | 11/6/2024 | 11/6/2024 | 0
s3547.4 | Not Specified | Install a new 230-138kV Substation. Install a two bay 230kV BAAH yard, two 230-138kV 330MVA transformers, and a two bay BAAH 138kV yard. | Supplemental | 230 | 47.3 |  | PPL |  |  |  |  | PA | Lampeter | Substation | Build | EP |  | Customer Service | 6/1/2028 |  | No | 11/6/2024 | 11/6/2024 | 0
s3547.5 | Not Specified | Bifurcate the Millwood - South Akron 230kV line and terminate at the new Lampeter 230-138kV Substation. | Supplemental | 230 | 4 |  | PPL |  |  |  |  | PA | S. Akron,Lampeter,Millwood,S. Akron^Lampeter^Millwood | Transmission Line | Build | EP |  | Customer Service | 6/1/2028 |  | No | 11/6/2024 | 11/6/2024 | 0
s3547.6 | Not Specified | Rebuild 3.1 miles the Strasburg #1 #2 69kV taps to double circuit 138kV operation from outside Lampeter to Strasburg substation. Extend two 138 kV circuits from the Lampeter 138kV yard and tie into the rebuilt Strasburg 138kV lines. Rebuild 3.3 miles of the Engleside – Greenland #1 & #2 69kV line to double circuit 138kV operation from Strasburg Tap to the Greenland sub. Extend a new double circuit 138kV line for ~1.5 miles from the Engleside – Greenland #1 & #2 138kV lines to Pitney 138kV switchyard. Remove a 3.6 mile section of the Engleside – Greenland #1 & #2 69kV line that will no longer be utilized. | Supplemental | 69,138,230 | 26 |  | PPL |  |  |  |  | PA | Greenland,Pitney,Lampeter^Strasburg^Greenland^Pitney,Lampeter,Strasburg | Transmission Line | Build | EP |  | Customer Service | 6/1/2028 |  | No | 11/6/2024 | 11/6/2024 | 0
s3548.1 | Not Specified | Construct a new five bay BAAH 138kV switchyard near the customer's facility. | Supplemental | 138 | 34 |  | PPL |  |  |  |  | PA | North Lancaster | Substation | Build | EP |  | Customer Service | 6/1/2027 |  | No | 11/6/2024 | 11/6/2024 | 0
s3548.2 | Not Specified | Bifurcate the West Hempfield- Prince #1 & #2 138kV and terminate at the new North Lancaster 138kV switchyard. Extend the 138kV lines approximately 0.2 miles into the new North Lancaster 138kV switchyard. | Supplemental | 138,230 | 3 |  | PPL |  |  |  |  | PA | North Lancaster,W. Hempfield,North Lancaster^W. Hempfield | Transmission Line | Build | EP |  | Customer Service | 6/1/2027 |  | No | 11/6/2024 | 11/6/2024 | 0
s3548.3 | Not Specified | Bifurcate the South Akron - Dillerville #1 & #2 138kV and terminate at the new North Lancaster 138kV switchyard. Extend the 138kV lines approximately 0.2 miles into the new North Lancaster 138kV switchyard. | Supplemental | 230,138 | 3 |  | PPL |  |  |  |  | PA | S. Akron,North Lancaster,S. Akron^North Lancaster | Transmission Line | Build | EP |  | Customer Service | 6/1/2027 |  | No | 11/6/2024 | 11/6/2024 | 0
s3548.4 | Not Specified | Extend three 138kV circuits for approximately 0.1 miles from the North Lancaster 138kV switchyard to the customer's facility. | Supplemental | 138 | 3.5 |  | PPL |  |  |  |  | PA | Donnelley,North Lancaster,Donnelley^North Lancaster | Transmission Line | Build | EP |  | Customer Service | 6/1/2027 |  | No | 11/6/2024 | 11/6/2024 | 0
s3548.5 | Not Specified | Rebuild 8.1 miles the West Hempfield – Prince (NLAN) #1 &#2 138kV lines from West Hempfield to new North Lancaster Switchyard. | Supplemental | 230,138 | 24 |  | PPL |  |  |  |  | PA | W. Hempfield,North Lancaster,W. Hempfield^North Lancaster | Transmission Line | Rebuild | EP |  | Customer Service | 6/1/2028 |  | No | 11/6/2024 | 11/6/2024 | 0
s3549.1 | Not Specified | Bifurcate the Harwood - Tresckow #1 & #2 230kV lines and terminate at the new Slykerville 230kV switchyard. Extend lines approximately .2 miles into the new Slykerville 230kV switchyard. | Supplemental | 230 | 4 |  | PPL |  |  |  |  | PA | Slykerville,Harwood,Slykerville^Harwood | Transmission Line | Build | EP |  | Customer Service | 5/30/2027 |  | No | 11/6/2024 | 11/6/2024 | 0
s3549.2 | Not Specified | Install a four bay BAAH 230kV switchyard with a 125MVAR Capacitor bank. | Supplemental | 230 | 45 |  | PPL |  |  |  |  | PA | Slykerville | Switching station | Build | EP |  | Customer Service | 5/30/2027 |  | No | 11/6/2024 | 11/6/2024 | 0
s3549.3 | Not Specified | Install three 230kV lead lines for approximately 0.1 miles from Slykerville 230kV switchyard to the customer facility. | Supplemental | 230 | 4 |  | PPL |  |  |  |  | PA | Slykerville,Beltway,Slykerville^Beltway | Transmission Line | Build | EP |  | Customer Service | 5/30/2027 |  | No | 11/6/2024 | 11/6/2024 | 0
s3549.4 | Not Specified | Install 15 ohm series reactors on the Susquehanna - Harwood #1 and #2 230kV line at Susquehanna 230kV switchyard | Supplemental | 230 | 8 |  | PPL |  |  |  |  | PA | Susquehanna 230 | Series Reactor | Build | EP |  | Customer Service | 5/1/2028 |  | No | 11/6/2024 | 11/6/2024 | 0
s3549.5 | Not Specified | Reconductor the 2.7 miles of the Susquehanna T10 - Susquehanna #1 & #2 230kV lines. Replace 3 MODS at Susquehanna | Supplemental | 230 | 8.1 |  | PPL |  |  |  |  | PA | Susquehanna T10 Yard,Susquehanna 230,Susquehanna T10 Yard^Susquehanna 230 | Transmission Line | Reconductor | EP |  | Customer Service | 5/30/2028 |  | No | 11/6/2024 | 11/6/2024 | 0
s3549.6 | Not Specified | Replace four MODs on each of the Harwood - Slykerville #1 & #2 230kV lines (eight total) at Harwood 230kV yard. | Supplemental | 230 | 4.2 |  | PPL |  |  |  |  | PA | Harwood | Switch | Replace | EP |  | Customer Service | 5/30/2028 |  | No | 11/6/2024 | 11/6/2024 | 0
s3550.1 | Not Specified | Install new 250MVA 500/230kV transformers as an in-kind replacement for each of the three units of the current 500/230kV Alburtis Transformer 1 (750MVA Total). | Supplemental | 500 | 19.9 |  | PPL |  |  |  |  | PA | Alburtis | Transformer | Replace | EP |  | Equipment Material Condition, Performance and Risk | 12/31/2026 |  | No | 11/6/2024 | 11/6/2024 | 0
s3551.1 | Not Specified | Install a new 340MVA, 500-138kV transformer as an in-kind replacement of the existing 500-138kV Wescosville Transformer 3. | Supplemental | 500 | 15.5 |  | PPL |  |  |  |  | PA | Wescosville | Transformer | Replace | EP |  | Equipment Material Condition, Performance and Risk | 12/31/2026 |  | No | 11/6/2024 | 11/6/2024 | 0
s3552.1 | Not Specified | Install a new 170MVA, 230-69kV transformer as an in-kind replacement of the existing 230-69kV Lackawanna Transformer 2. | Supplemental | 500 | 6.3 |  | PPL |  |  |  |  | PA | Lackawanna | Transformer | Replace | EP |  | Equipment Material Condition, Performance and Risk | 12/31/2026 |  | No | 11/6/2024 | 11/6/2024 | 0
s3553.1 | Not Specified | Install a new 170MVA, 230-69kV transformer as an in-kind replacement of the existing 230-69kV Blooming Grove Transformer 1. | Supplemental | 230 | 6.3 |  | PPL |  |  |  |  | PA | Blooming Grove | Transformer | Replace | EP |  | Equipment Material Condition, Performance and Risk | 12/31/2027 |  | No | 11/6/2024 | 11/6/2024 | 0
s3554.1 | PJM MA | Add second 69kV circuit (556ACSR) on the existing single circuit, built for double circuit SUNB-MIDD 69kV line for ~6.4 miles. | Supplemental | 69 | 6.5 |  | PPL |  |  |  |  | PA | Middleburg,Penns,Middleburg^Penns | Conductor | Install | EP | 6.5 | Equipment Material Condition, Performance and Risk,Customer Service | 5/31/2028 |  | No | 11/14/2024 | 11/14/2024 | 0
s3554.2 | PJM MA | Rebuild the existing 9.1-mile single circuit Beavertown 69kV tap to double circuit 69kV. Conductor to be 556 ACSR. | Supplemental | 69 | 26.5 |  | PPL |  |  |  |  | PA | Middleburg,Beavertown,Middleburg^Beavertown | Transmission Line | Rebuild | EP | 26.5 | Equipment Material Condition, Performance and Risk,Customer Service | 5/31/2028 |  | No | 11/14/2024 | 11/14/2024 | 0
s3555.1 | Not Specified | Bifurcate the Harwood - Siegfried 230kV and the Harwood - East Palmerton 230kV lines and terminate at the new Tresckow 230kV switchyard. Extend lines approximately 1 mile into the new Tresckow 230kV switchyard. | Supplemental | 230 | 8 |  | PPL |  |  |  |  | PA | Tresckow 230,East Palmerton,Siegfried,Harwood^Tresckow 230^East Palmerton^Siegfried,Harwood | Transmission Line | Install | EP |  | Customer Service | 5/31/2027 |  | No | 10/8/2024 | 10/8/2024 | 0
s3555.2 | Not Specified | Install a four bay BAAH 230kV switchyard with a 125MVAR Capacitor bank. | Supplemental | 230 | 45 |  | PPL |  |  |  |  | PA | Tresckow 230 | Substation equipment | Build | EP |  | Customer Service | 5/31/2027 |  | No | 10/8/2024 | 10/8/2024 | 0
s3555.3 | Not Specified | Install three 230kV lead lines for approximately 4 miles from Tresckow 230kV switchyard to the customer facility. | Supplemental | 230 | 28 |  | PPL |  |  |  |  | PA | Tresckow 230,Lofty,Tresckow 230^Lofty | Transmission Line | Build | EP |  | Customer Service | 5/31/2027 |  | No | 10/8/2024 | 10/8/2024 | 0
s3556.1 | PJM MA | Extend a new double circuit 69/138kV tap from the existing Breinigsville - ATTR 69/138kV line to interconnect the new Tek Park 69-13.8kV substation. Build 0.4 miles of new 69/138kV double circuit line using 795 ACSR conductor. | Supplemental | 69 | 1.5 |  | PPL |  |  |  |  | PA | ATTR 69-13.8kV Substation,Tek Park 69-13.8kV Substation,ATTR 69-13.8kV Substation^Tek Park 69-13.8kV Substation | Transmission Line | Build | EP |  | Customer Service | 6/1/2026 |  | No | 9/19/2024 | 9/19/2024 | 0
s3556.2 | PJM MA | Extend a new double circuit 69/138kV tap from the existing Breinigsville 500-138-69kV Substation to the new Tek Park 69/138kV tap. Build 0.75 miles of new 69/138kV double circuit line using 795 ACSR conductor. | Supplemental | 500,69 | 4 |  | PPL |  |  |  |  | PA | Breinigsville,Tek Park 69-13.8kV Substation,Breinigsville^Tek Park 69-13.8kV Substation | Transmission Line | Build | EP |  | Customer Service | 6/1/2027 |  | No | 9/19/2024 | 9/19/2024 | 0
s3556.3 | PJM MA | Install two new line terminals in the Breinigsville 69/138kV Yard. Install two bays in initial DBDB future BAAH Arrangement. | Supplemental | 500 | 3.5 |  | PPL |  |  |  |  | PA | Breinigsville | Substation equipment | Install | EP |  | Customer Service | 6/1/2027 |  | No | 9/19/2024 | 9/19/2024 | 0
s3557.1 | PJM MA | Rebuild ~7 miles of the double circuit Stanton - Summit #1 & #2 69kV lines to double circuit 69kV with 556 ACSR conductor. | Supplemental | 230 | 17.5 |  | PPL |  |  |  |  | PA | Stanton,Summit (PL),Stanton^Summit (PL) | Transmission Line | Rebuild | EP |  | Equipment Material Condition, Performance and Risk | 12/1/2027 |  | No | 9/19/2024 | 9/19/2024 | 0
s3558.1 | PJM MA | Rebuild 2 miles of the existing single circuit Old Forge – Avoca 69kV tie line as single circuit 69kV with 556ACSR conductor. | Supplemental | 69 | 5.5 |  | PPL |  |  |  |  | PA | Avoca,Old Forge,Avoca^Old Forge | Transmission Line | Rebuild | EP |  | Equipment Material Condition, Performance and Risk | 12/1/2027 |  | No | 9/19/2024 | 9/19/2024 | 0
s3559.1 | PJM MA | Rebuild ~6 miles of the double circuit Stanton-Swoyersville/Exeter 69kV lines to double circuit 69kV. Rebuild ~1 mile of single circuit 69kV taps. All rebuilt sections to be 556 ACSR conductor. | Supplemental | 69,230 | 17.5 |  | PPL |  |  |  |  | PA | Exeter,Stanton,Exeter^Stanton | Transmission Line | Rebuild | EP |  | Equipment Material Condition, Performance and Risk | 12/1/2027 |  | No | 9/19/2024 | 9/19/2024 | 0
s3571.1 | Not Specified | Install a new 500-138kV substation with a four bay BAAH 500kV yard, four 500-138kV XFMRs, six bay BAAH 138kV yard, and one 138kV capacitor bank. | Supplemental | 500 | 148 |  | PPL |  |  |  |  | PA | New Buffalo | Substation | Build | EP |  | Customer Service | 6/30/2027 |  | No | 1/7/2025 | 1/7/2025 | 0
s3571.2 | Not Specified | Bifurcate the Juniata - Alburtis 500kV line and terminate into the New Buffalo substation. Extend lines approximately 0.6 miles. | Supplemental | 500 | 8 |  | PPL |  |  |  |  | PA | New Buffalo,Alburtis,Juniata,Juniata^New Buffalo^Alburtis | Transmission Line | Build | EP |  | Customer Service | 6/30/2027 |  | No | 1/7/2025 | 1/7/2025 | 0
s3571.3 | Not Specified | Rebuild the existing JUNI-ALBU 500kV line to double circuit for 9.6 miles from Juniata substation to New Buffalo substation. | Supplemental | 500 | 83 |  | PPL |  |  |  |  | PA | Juniata,New Buffalo,Juniata^New Buffalo | Transmission Line | Rebuild | EP |  | Customer Service | 5/30/2028 |  | No | 1/7/2025 | 1/7/2025 | 0
s3571.4 | Not Specified | Extend six 138kV lines to the customer facility. | Supplemental | 500,138 | 3 |  | PPL |  |  |  |  | PA | New Buffalo,Susquehanna Crossings,New Buffalo^Susquehanna Crossings | Transmission Line | Build | EP |  | Customer Service | 6/30/2027 |  | No | 1/7/2025 | 1/7/2025 | 0
s3605.1 | PJM MA | Convert Mountain Substation into a six-breaker ring bus | Supplemental | 115 | 11 |  | ME |  |  |  |  | PA | Mt Holly Springs | Substation | Rebuild | EP | 11 | Operational Flexibility and Efficiency | 12/31/2026 |  | No | 8/15/2024 | 8/15/2024 | 5
s3605.2 | PJM MA | At PPGI Substation, replace Mountain circuit breaker | Supplemental | 115 | 0.4 |  | ME |  |  |  |  | PA | Carlisle | Circuit Breaker | Replace | EP | 0.4 | Operational Flexibility and Efficiency | 12/31/2026 |  | No | 8/15/2024 | 8/15/2024 | 0
s3622.1 | PJM MA | Middletown Junction – Swatara Hill – Campbelltown 69 kV Line: Rebuild approximately 9 miles of Campbelltown – Middletown Junction 69 kV Line. At Middletown Junction, review and revise relaying. At Campbelltown Substation, review and revise relaying. | Supplemental | 69 | 25.4 |  | ME |  |  |  |  | PA | Middletown, Campbelltown, PA | Transmission Line | Rebuild | EP | 25.4 | Equipment Material Condition, Performance and Risk | 12/21/2026 |  | No | 3/13/2025 | 3/13/2025 | 0
s3623.1 | PJM MA | Raintree Substation: Construct a four-breaker 115 kV ring bus at Raintree Substation. Remove existing temporary configuration connection at Raintree. Loop the Middletown Junction – Smith Street 115 kV 978 Line into Raintree Substation. Install one control house. Install four 115 kV circuit breakers and associated disconnect switches. Install two standard transmission line relay panels. At Middletown Junction Substation, replace existing line relay panels. At Smith Street Substation, replace one 115 kV circuit breaker and associated disconnect switches, and existing line relay panels | Supplemental | 115 | 12.5 |  | ME |  |  |  |  | PA | York, PA | Circuit Breaker | Reconfigure | EP | 12.5 | Customer Service | 12/31/2026 |  | No | 12/12/2024 | 12/12/2024 | 0
s3624.1 | PJM MA | North Hershey Substation: Convert the 69 kV bus at North Hershey Substation into a four-breaker ring bus. Install four 69 kV, 3000 A circuit breakers and associated equipment. Install a 2nd 230-69 kV transformer at North Hershey Substation. Install one 230 kV, 3000 A circuit breaker and associated equipment. | Supplemental | 230/69 | 16.31 |  | ME |  |  |  |  | PA | Palmyra, PA | Transformer & CB | Reconfigure | EP | 16.31 | Operational Flexibility and Efficiency | 12/17/2027 |  | No | 11/6/2024 | 11/6/2024 | 0
s3625.1 | PJM MA | Cleona Substation: Construct a three breaker 69 kV ring bus by installing three 69 kV circuit breakers and associated disconnect switches. Install three standard transmission line relay panels. Re-terminate the North Lebanon – West Lebanon 69 kV 94 Line into Cleona. | Supplemental | 69 | 9.5 |  | ME |  |  |  |  | PA | LebaFALSEn, PA | Circuit Breaker | Reconfigure | EP | 9.5 | Operational Flexibility and Efficiency | 6/8/2026 |  | No | 12/12/2024 | 12/12/2024 | 0
s3626.1 | PJM MA | Belfast Substation: Construct a four breaker 115 kV ring bus. Install four 115 kV circuit breakers, disconnect switches, line traps, and relaying. Update relaying at North Bangor and Glendon substations. Re-terminate the North Bangor and Northwood 115 kV terminals at Belfast Substation. | Supplemental | 115 | 14.3 |  | ME |  |  |  |  | PA | Easton, PA | Circuit Breaker | Reconfigure | EP | 14.3 | Operational Flexibility and Efficiency | 6/1/2028 |  | No | 1/16/2025 | 1/16/2025 | 0
s3628.1 | PJM MA | Piney Substation: On the Burma Line Terminal, replace the circuit breaker, line trap, substation conductor, relays and associated disconnect switches. On the Grandview/Haynie Line Terminal, replace the circuit breaker, line trap, substation conductor, relays and associated disconnect switches. On the Timblin Line Terminal, replace circuit breaker and associated disconnect switches. On the Eclipse Line Terminal, replace line trap, substation conductor, disconnect switches and relays. Replace 115 kV bus tie breaker, 115 kV No. 3 Transformer Breaker, 115 kV No. 4 Transformer Breaker, relays and associated disconnect switches. Construct a new control building to house new equipment. At Grandview Substation, on the Piney/Haynie Line Terminal, replace the line trap, substation conductor, relays and associated disconnect switches. At Eclipse Substation, on the Piney Line Terminal, replace line trap, substation conductor and relays. | Supplemental | 115 | 11.4 |  | PENELEC |  |  |  |  | PA | Clarion, Oil City, Franklin, PA | Substation | Upgrade | EP | 11.4 | Equipment Material Condition, Performance and Risk | 1/12/2026 |  | No | 8/15/2024 | 8/15/2024 | 0
s3629.1 | PJM MA | SGC Tap - Summit 46 kV Line: Rebuild approximately 1.36 miles of existing line. | Supplemental | 46 | 3.54 |  | PENELEC |  |  |  |  | PA | Cresson, Gallitzin, PA | Transmission Line | Rebuild | EP | 3.54 | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 5/29/2026 |  | No | 3/13/2025 | 3/13/2025 | 0
s3631.1 | PJM MA | Glade Substation: Replace Glade Substation control building with a new package control enclosure. Install new cable trench, replace four disconnect switches, and two 230 kV breakers. Replace substation conductor and line trap on the Lewis Run and Warren line terminals at Glade Substation. Replace substation conductor on the Forest line terminal at Glade Substation - Install new relaying and control equipment. At Lewis Run Substation, on the Glade line terminal, replace line trap. Install new relaying and control equipment. At Warren Substation, on the Glade line terminal, replace substation conductor. Install new relaying and control equipment. At Forest Substation, on the Glade line terminal, install new relaying and control equipment. | Supplemental | 230 | 12 |  | PENELEC |  |  |  |  | PA | Warren, Ridgway Twp, Lewis Run , PA | Substation | Upgrade | EP | 12 | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 12/17/2027 |  | No | 3/4/2025 | 3/4/2025 | 0
s3633.1 | PJM MA | Strongstown - Belsano Replace line switch A119: Relocate and replace obsolete and non-repairable line switch Strongstown - Belsano A119. Upgrade switch to include SCADA controlled motor operators. Remove 4-pole wood structure and replace with appropriate tap structure. | Supplemental | 115 | 0.93 |  | PENELEC |  |  |  |  | PA | Glory,Spangler,Glory^Spangler | Transmission Line | Upgrade | EP | 0.93 | Equipment Material Condition, Performance and Risk | 11/13/2026 |  | No | 2/13/2025 | 2/13/2025 | 0
s3633.2 | PJM MA | Strongstown - Twin Rock Replace line switch A120: Relocate and replace obsolete and non-repairable line switch Strongstown - Twin Rock A120. Upgrade switches to include SCADA controlled motor operators. Remove 4-pole wood structure and replace with appropriate tap structure. | Supplemental | 115 | 0.93 |  | PENELEC |  |  |  |  | PA | Glory,Spangler,Glory^Spangler | Transmission Line | Upgrade | EP | 0.93 | Equipment Material Condition, Performance and Risk | 11/13/2026 |  | No | 2/13/2025 | 2/13/2025 | 0
s3634.1 | PJM MA | Altoona - Hollidaysburg 46 kV AH Line Terminal Upgrades: Replace line relaying at Altoona and Hollidaysburg substations | Supplemental | 230 | 2.21 |  | PENELEC |  |  |  |  | PA | Altoona | Relay | Upgrade | EP | 2.21 | Equipment Material Condition, Performance and Risk | 12/1/2027 |  | No | 4/10/2025 | 4/10/2025 | 0
s3635.1 | PJM MA | Tyrone North - Tipton 46 kV Line: Upgrade line relaying and limiting substation conductor at Tyrone North Substation. Upgrade protection and terminal equipment at Tipton Substation. | Supplemental | 115 | 2.92 |  | PENELEC |  |  |  |  | PA | Tyrone North | Relay | Upgrade | EP | 2.92 | Equipment Material Condition, Performance and Risk | 12/31/2027 |  | No | 4/10/2025 | 4/10/2025 | 0
s3640.1 | PJM MA | Extend the Wright #1 & #2 69kV taps ~0.5 miles to the connect the customer substation. | Supplemental | 69 | 1.75 |  | PPL |  |  |  |  | PA | Wright 69-12kV^Grand Landmark,Wright 69-12kV,Grand Landmark | Transmission Line | Build | EP |  | Customer Service | 8/1/2025 |  | No | 10/17/2024 | 10/17/2024 | 0
s3640.2 | PJM MA | Extend a new double circuit 69kV line from the existing Palooka 230-69kV Substation to the new Grand Landmark 69kV taps. Build ~5 miles of new 69kV double circuit line using 795 ACSR conductor. | Supplemental | 230,69 | 12.5 |  | PPL |  |  |  |  | PA | Palooka,Grand Landmark,Palooka^Grand Landmark | Transmission Line | Build | EP |  | Customer Service | 5/1/2028 |  | No | 10/17/2024 | 10/17/2024 | 0
s3640.3 | PJM MA | Install two new line terminals in the Palooka 69kV Yard. Install two bays in initial DBDB, future BAAH Arrangement. | Supplemental | 230 | 3.5 |  | PPL |  |  |  |  | PA | Palooka | Substation equipment | Build | EP |  | Customer Service | 5/1/2028 |  | No | 10/17/2024 | 10/17/2024 | 0
s3649.1 | PJM WEST | Replace one aged 138kV breaker with a modern breaker. | Supplemental | 138 | 0.8 |  | DL |  |  |  |  | PA | Neville | Circuit Breaker | Replace | EP |  | Equipment Material Condition, Performance and Risk | 12/31/2025 |  | No | 3/14/2025 | 3/14/2025 | 0
s3650.1 | PJM WEST | Replace two aged 138kV oil breakers with modern breakers. | Supplemental | 345 | 1.6 |  | DL |  |  |  |  | PA | Carson | Circuit Breaker | Replace | EP |  | Equipment Material Condition, Performance and Risk | 12/31/2025 |  | No | 3/14/2025 | 3/14/2025 | 0
s3651.1 | PJM WEST | Replace one aged 138kV breaker with a modern breaker. | Supplemental | 138 | 0.8 |  | DL |  |  |  |  | PA | Dravosburg | Circuit Breaker | Replace | EP |  | Equipment Material Condition, Performance and Risk | 12/31/2025 |  | No | 3/14/2025 | 3/14/2025 | 0
s3652.1 | PJM WEST | Replace one aged 138kV breaker with a modern breaker. | Supplemental | 138 | 0.8 |  | DL |  |  |  |  | PA | Findlay | Circuit Breaker | Replace | EP |  | Equipment Material Condition, Performance and Risk | 12/31/2025 |  | No | 3/14/2025 | 3/14/2025 | 0
s3657.1 | PJM WEST | At Charleroi Substation, replace substation conductor, line trap, surge arresters, CVT and line relaying. | Supplemental | 138 | 2.06 |  | APS |  |  |  |  | PA | Charleroi | Substation equipment | Upgrade | EP |  | Equipment Material Condition, Performance and Risk | 7/2/2029 |  | No | 4/11/2025 | 4/11/2025 | 0
s3657.2 | PJM WEST | At Emerald Substation, replace circuit switcher towards Brownsville Junction with a circuit breaker, replace bus tie circuit breaker, disconnect switches, substation conductor, line trap, CVTs and line relaying. | Supplemental | 138 | 2.06 |  | APS |  |  |  |  | PA | Emerald | Substation equipment | Upgrade | EP |  | Equipment Material Condition, Performance and Risk | 7/2/2029 |  | No | 4/11/2025 | 4/11/2025 | 0
s3657.3 | PJM WEST | At Gates Hill Substation, replace circuit switcher with circuit breaker, disconnect switches, line trap, line turner, COAX and line relaying. | Supplemental | 138 | 2.06 |  | APS |  |  |  |  | PA | Gates Hill | Substation equipment | Upgrade | EP |  | Equipment Material Condition, Performance and Risk | 7/2/2029 |  | No | 4/11/2025 | 4/11/2025 | 0
s3658.1 | PJM WEST | Replace the switch 1027 at Blacksville No. 1 Tap with a motor-operated, SCADA-controlled switch. | Supplemental | 138 | 1.3 |  | APS |  |  |  |  | PA | Whiteley,Fairview | Switch | Replace | EP |  | Equipment Material Condition, Performance and Risk | 8/21/2026 |  | No | 4/11/2025 | 4/11/2025 | 0
s3661.1 | PJM MA | Install 6th Byberry 138/13 kV 62 MVA transformer with high side breaker | Supplemental | 138 | 0.85 |  | PECO |  |  |  |  | PA | Byberry | Transformer | Install | EP | 0.85 | Customer Service,Equipment Material Condition, Performance and Risk | 6/1/2028 |  | No | 10/17/2024 | 10/17/2024 | 0
s3662.1 | PJM MA | Replace Byberry circuit breaker #150. Existing rating: 1600A, 42kA. Proposed rating: 3000A, 63kA | Supplemental | 138 | 0.55 |  | PECO |  |  |  |  | PA | Byberry | Circuit Breaker | Replace | EP | 0.55 | Equipment Material Condition, Performance and Risk | 6/1/2028 |  | No | 10/17/2024 | 10/17/2024 | 0
s3663.1 | PJM MA | Rebuild Neshaminy 138kV straight bus to a 7 breaker AIS ring bus configuration. Install two new 138kV circuit breakers #705 and #905 with associated buses, switches, and protection equipment. Remove the #175 138kV circuit breaker and associated relay equipment. Remove specialized protection scheme upon completion of new ring bus | Supplemental | 138 | 4.2 |  | PECO |  |  |  |  | PA | Neshaminy | Bus | Rebuild | EP | 4.2 | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 12/31/2027 |  | No | 10/17/2024 | 10/17/2024 | 0
s3666.1 | Not Specified | At Huntingdon Substation, replace circuit breaker, disconnect switches, substation conductor, line trap, surge arresters, CVTs, and relaying. At Springdale Substation, replace disconnect switches, substation conductor, line trap, surge arresters, CVTs, and relaying. | Supplemental | 138 | 4.71 |  | APS |  |  |  |  | PA | Huntingdon – Springdale | Circuit Breaker | Replace | EP | 4.71 | Equipment Material Condition, Performance and Risk | 5/1/2028 |  | No | 5/16/2025 | 5/16/2025 | 1
s3702.1 | PJM MA | Ashtabula – Erie West 345 kV Line: Rebuild the 7.2 mile, Penelec section of the line. At Erie West, replace disconnect switches. At Ashtabula, revise relay settings | Supplemental | 345 | 52.4 |  | PENELEC |  |  |  |  | PA | West Springfield, Girard, PA | Transmission Line | Rebuild | EP | 52.4 | Equipment Material Condition, Performance and Risk | 5/31/2027 |  | No | 8/6/2024 | 8/6/2024 | 0
s3706.1 | Not Specified | Install one new 230kV breaker, 230kV dead-end, and ancillary equipment in Bay 0 at Susquehanna 230kV. | Supplemental | 230 | 1.5 |  | PPL |  |  |  |  | PA | Susquehanna 230 | Circuit Breaker | Install | EP |  | Customer Service | 4/30/2026 |  | No | 5/6/2025 | 5/6/2025 | 0
s3706.2 | Not Specified | Re-terminate the Sunbury – Susquehanna #1 230kV line from Bay #1 to Bay #0 at Susquehanna 230kV. | Supplemental | 500,230 | 0.4 |  | PPL |  |  |  |  | PA | Sunbury^Susquehanna 230,Sunbury,Susquehanna 230 | Transmission Line | Reconfigure | EP |  | Customer Service | 4/30/2026 |  | No | 5/6/2025 | 5/6/2025 | 0
s3706.3 | Not Specified | Extend a new 230kV line (1590 ACSS) from Bay #1 at Susquehanna 230kV yard to the customer substation dead-end (Customer Yard 1). | Supplemental | 230 | 6.05 |  | PPL |  |  |  |  | PA | Susquehanna 230,SS01,Susquehanna 230^SS01 | Transmission Line | Build | EP |  | Customer Service | 4/30/2026 |  | No | 5/6/2025 | 5/6/2025 | 0
s3706.4 | Not Specified | Install one new 500kV breaker, 500kV dead-end, and ancillary equipment in Bay 2 at Susquehanna 500kV. | Supplemental | 500 | 3.5 |  | PPL |  |  |  |  | PA | Susquehanna | Circuit Breaker | Install | EP |  | Customer Service | 4/30/2027 |  | No | 5/6/2025 | 5/6/2025 | 0
s3706.5 | Not Specified | Extend a new 500kV line from Bay #2 at Susquehanna 500kV yard to the customer substation dead-end (Customer Yard 2). | Supplemental | 500 | 1.8 |  | PPL |  |  |  |  | PA | Susquehanna,SS02,Susquehanna^SS02 | Transmission Line | Build | EP |  | Customer Service | 4/30/2027 |  | No | 5/6/2025 | 5/6/2025 | 0
s3706.6 | Not Specified | Install one new 230kV breaker, 230kV dead-end, and ancillary equipment in both Bay #1 and #3 at Susquehanna T10 230kV Yard. | Supplemental | 230 | 3 |  | PPL |  |  |  |  | PA | Susquehanna T10 Yard | Circuit Breaker | Install | EP |  | Customer Service | 5/30/2028 |  | No | 5/6/2025 | 5/6/2025 | 0
s3706.7 | Not Specified | Extend two new 230kV lines (1590 ACSS) from Bay #1 and Bay #3 at Susquehanna T10 230kV yard to the customer substation dead-end (Customer Yard 3). | Supplemental | 230 | 3.15 |  | PPL |  |  |  |  | PA | Susquehanna T10 Yard,SS0X,Susquehanna T10 Yard^SS0X | Transmission Line | Build | EP |  | Customer Service | 5/30/2028 |  | No | 5/6/2025 | 5/6/2025 | 0
s3707.1 | PJM WEST | At Bethel Park Substation: replace circuit breaker, disconnect switches, line turner and coax, CCVT, substation conductor, metering, line trap and relaying At St Clair Substation: replace circuit breaker, disconnect switches, line turner and coax, CCVT, substation and bus conductors, line trap and relaying | Supplemental | 138 | 4.5 |  | APS |  |  |  |  | PA | Bethel Park – St Clair | Substation equipment | Replace | EP | 4.5 | Equipment Material Condition, Performance and Risk | 7/27/2029 |  | No | 6/13/2025 | 6/13/2025 | 0
s3709.1 | PJM WEST | At Harwick Substation: replace circuit breaker, disconnect switches, line trap, line turner and coax, substation and bus conductors and relaying At Houseville Substation: replace disconnect switches, line trap, line turner and coax, CVT, substation conductor and relaying | Supplemental | 138 | 3.4 |  | APS |  |  |  |  | PA | Harwick – Houseville | Substation equipment | Replace | EP | 3.4 | Equipment Material Condition, Performance and Risk | 12/31/2027 |  | No | 6/13/2025 | 6/13/2025 | 0
b3871.1 | PJM WEST | Replace two 138 kV disconnect switches with 3000 amp disconnect switches and replace a portion of the stranded conductor on the #2 138 kV Bus with aluminum pipe bus. | Baseline | 138 | 8 | 6/1/2029 | DL |  | Appendix A | DL:100 |  | PA | Brunot Island | Bus | Modify | PL | 8 | Baseline Load Growth Deliverability & Reliability | 12/31/2028 |  | No | 11/15/2024 | 11/15/2024 | 0
b3136 | PJM MA | Replace bus conductor at Smith 115 kV substation | Baseline | 115 | 0.24 | 6/1/2024 | ME |  | Appendix A | ME:100 |  | PA | Smith Tap - Smith St. | Bus | Upgrade | UC | 0.15 | Baseline Load Growth Deliverability & Reliability | 6/30/2027 |  | No | 9/24/2019 | 10/21/2019 | 40
b3245 | PJM MA | Construct a new breaker-and-a-half substation near Tiffany substation. All transmission assets and lines will be relocated to the new substation. The two distribution transformers will be fed via two dedication 115 kV feeds to the existing Tiffany substation. | Baseline | 115 | 23.2 | 6/1/2025 | PENELEC |  | Appendix A | PENELEC:100 |  | PA |  | Substation | Construct | UC | 23.2 | Baseline Load Growth Deliverability & Reliability | 6/5/2026 |  | No | 11/18/2020 | 11/18/2020 | 40
b3672 | PJM MA | East Towanda-North Meshoppen 115 kV line: Rebuild 2.5 miles of 636 ACSR with 1113 ACSS conductor using single circuit construction. Upgrade all terminal equipment to the rating of 1113 ACSS. | Baseline | 115 | 6.66 | 6/1/2026 | PENELEC |  | Appendix A | PENELEC:100 |  | PA | East Towanda/North Meshoppen |  | Rebuild | UC | 6.66 | Baseline Load Growth Deliverability & Reliability | 12/31/2025 |  | No | 11/18/2021 | 11/18/2021 | 40
b3715.1 | PJM MA | At the existing PPL Williams Grove substation, install a new 300 MVA 230/115 kV transformer. | Baseline | 230/115 | 6.3 | 6/1/2026 | PPL | 2021_1-99 | Appendix A | ME:100 |  | PA | Williams Grove | Transformer | Install | UC | 6.3 | Baseline Load Growth Deliverability & Reliability | 5/6/2026 |  | No | 5/10/2022 | 5/10/2022 | 50
b3715.2 | PJM MA | Construct a new ~3.4 mile 115 kV single circuit transmission line from Williams Grove to Allen substation. | Baseline | 115 | 5.11 | 6/1/2026 | PPL | 2021_1-99 | Appendix A | ME:100 |  | PA | Williams Grove-Allen | Transmission Line | Build | UC | 5.11 | Baseline Load Growth Deliverability & Reliability | 3/6/2026 |  | No | 5/10/2022 | 5/10/2022 | 50
b3730 | PJM MA | Reterminate the Lackawanna T3 and T4 500/230 kV transformers on the 230 kV side to remove them from the 230 kV buses and bring them into dedicated bay positions that are not adjacent to one another. | Baseline | 500/230 | 10.7 | 6/1/2027 | PPL | 2022_1-127 | Appendix A | PPL:100 |  | PA | Lackawanna | Transformer | Modify | UC | 10.7 | Baseline Load Growth Deliverability & Reliability | 12/19/2025 |  | No | 10/4/2022 | 11/1/2022 | 60
b3765 | PJM MA | Purchase one 80 MVAR 345 kV spare reactor, to be located at the Mainesburg station. | Baseline | 345 | 6.44 | 12/1/2022 | PENELEC |  | Appendix A | PENELEC:100 |  | PA | Mainesburg | Reactive Device | Provide | UC | 6.44 | Baseline Load Growth Deliverability & Reliability | 12/30/2026 |  | No | 11/4/2022 | 12/6/2022 | 50
b3783 | PJM MA | Cut and remove the 345 kV and 230 kV generator lead lines at Homer City. Install new station service supply, separate AC station service, separate protection and controls schemes, and review and adjust relay protection settings | Baseline | 345/230 | 2.25 | 6/1/2025 | PENELEC |  | Appendix A | PENELEC:100 |  | PA | Homer City | Substation | Modify | UC | 2.25 | Generator Deactivation | 10/1/2026 |  | Yes | 9/5/2023 | 9/5/2023 | 80
b3800.19 | PJM MA | Reconductor Lincoln-Orrtanna 115 kV line. | Baseline | 115 | 10.98 | 6/1/2027 | ME | 2022-W3-837 | Appendix A | ME:100 |  | PA |  | Transmission Line | Reconductor | UC | 10.98 | Baseline Load Growth Deliverability & Reliability | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 50
n6717 | Not Specified | Philipsburg 34. 5 kV Substation- Adjust remote relay and metering settings. | Network | 34.5 | 0.04 | 9/1/2021 | PENELEC |  |  |  |  | PA | Philipsburg | Relay | Modify | UC | 0.04 | AE2-131 |  |  | No | 11/1/2022 | 11/1/2022 | 0 | 9/1/2021 | 9/30/2021
n7088 | Not Specified | Lewistown: Install Hybrids and 1 DTT UPLC transmitter. Replace wave trap and line tuner. | Network | 115 | 0.36 | 11/2/2021 | PENELEC |  |  |  |  | PA | Lewistown | Relay | Replace | UC | 0.36 | AE1-071 | 9/15/2023 |  | No | 11/1/2022 | 11/1/2022 | 2 | 11/2/2021 | 9/30/2019
n7089 | Not Specified | Shade Gap: Install Hybrids and 1 DTT UPLC transmitter | Network | 115 | 0.3 | 11/2/2021 | PENELEC |  |  |  |  | PA | Shade Gap | Relay | Replace | UC | 0.3 | AE1-071 | 9/15/2023 |  | No | 11/1/2022 | 11/1/2022 | 2 | 11/2/2021 | 9/30/2019
n7274 | Not Specified | Tap the McConnellsburg – Mercersburg 34.5 kV Line, install two manual 1200A gang operated line switches on the existing McConnellsburg-Mercersburg 34.5kV Line, for the LSBP solar facility (AD1-061). @ McConnellsburg-Mercersburg 34.5kV Line Tap. | Network | 34.5 | 0.1 | 12/31/2021 | APS |  |  |  |  | PA | Line tap between McConnellsburg - Mercersburg | Relay | Modify | UC | 0.1 | AD1-061 |  |  | No | 11/1/2022 | 11/1/2022 | 0 | 12/31/2021 | 12/31/2022
n7275 | Not Specified | Estimated SCADA work at McConnellsburg & Mercersburg substations to support relay replacements and updated relay settings. | Network | 34.5 | 0.07 | 12/31/2021 | APS |  |  |  |  | PA | McConnellsburg - Mercersberg | Communication Equipment | Construct | UC | 0.07 | AD1-061 |  |  | No | 11/1/2022 | 11/1/2022 | 0 | 12/31/2021 | 12/31/2022
n7276 | Not Specified | Install new relaying on the Mercersburg 34.5kV line for the LSPB Solar interconnection (AD1-061). @ McConnellsburg | Network | 34.5 | 0.32 | 12/31/2021 | APS |  |  |  |  | PA | Mercersberg | Relay | Install | UC | 0.32 | AD1-061 |  |  | No | 11/1/2022 | 11/1/2022 | 0 | 12/31/2021 | 12/31/2022
n7277 | Not Specified | Review and revise relay settings @ Mercersburg | Network | 34.5 | 0.01 | 12/31/2021 | APS |  |  |  |  | PA | Mercersberg | Relay | Modify | UC | 0.01 | AD1-061 |  |  | No | 11/1/2022 | 11/1/2022 | 0 | 12/31/2021 | 12/31/2022
n7926 | Not Specified | Tap the Maysville-Sharon 69 kV (Y-301) line near structure 62 and install disconnect switches on either side of the tap at the new AE1-079 substation. Includes project management, environmental, forestry, real estate and right of way. | Network | 69 | 1.19 | 6/1/2020 | ATSI |  |  |  |  | PA | AE1-079 Tap | Transmission Line | Install | UC | 1.19 | AE1-079 |  |  | No | 10/8/2024 | 10/8/2024 | 0 | 6/1/2020 | 12/31/2023
n7927 | Not Specified | Update Relay Settings at Marysville 69 kV substation | Network | 69 | 0.09 | 6/1/2020 | ATSI |  |  |  |  | PA | Maysville | Relay | Modify | UC | 0.09 | AE1-079 |  |  | No | 10/8/2024 | 10/8/2024 | 0 | 6/1/2020 | 12/31/2023
n7928 | Not Specified | Update Relay Settings at Sharon 69 kV substation | Network | 69 | 0.09 | 6/1/2020 | ATSI |  |  |  |  | PA | Sharon | Relay | Modify | UC | 0.09 | AE1-079 |  |  | No | 10/8/2024 | 10/8/2024 | 0 | 6/1/2020 | 12/31/2023
n7930 | Not Specified | Update Relay Settings at Cedar street 69 kV substation | Network | 69 | 0.09 | 6/1/2020 | ATSI |  |  |  |  | PA | Cedar Street | Relay | Modify | UC | 0.09 | AE1-079 |  |  | No | 10/8/2024 | 10/8/2024 | 0 | 6/1/2020 | 12/31/2023
n7931 | Not Specified | Update Relay Settings at McDowell Street 69 kV substation | Network | 69 | 0.09 | 6/1/2020 | ATSI |  |  |  |  | PA | McDowell Street | Relay | Modify | UC | 0.09 | AE1-079 |  |  | No | 10/8/2024 | 10/8/2024 | 0 | 6/1/2020 | 12/31/2023
n7933 | Not Specified | SCADA/Fiber Communication: Estimated installation of 700 MHz radio system (70% penetration of FE territory) to support the SCADA switch replacements at the new AE1-079 substation | Network | 69 | 0.1 | 6/1/2020 | ATSI |  |  |  |  | PA | AE1-079 Tap | Communication Equipment | Install | UC | 0.1 | AE1-079 |  |  | No | 10/8/2024 | 10/8/2024 | 0 | 6/1/2020 | 12/31/2023
n7934 | Not Specified | Tap the Dilworth-Andover (Maysville) 69 kV (Y-78) line at structure 145 and install disconnect switches on either side of the tap. Includes project management, environmental, forestry, real estate and right of way. | Network | 69 | 0.88 | 6/1/2020 | ATSI |  |  |  |  | PA | AE1-237 Tap | Transmission Line | Install | UC | 0.88 | AE1-237 |  |  | No | 10/8/2024 | 10/8/2024 | 0 | 6/1/2020 | 12/31/2023
n7935 | Not Specified | Update Relay Settings at Marysville 69 kV substation | Network | 69 | 0.09 | 6/1/2020 | ATSI |  |  |  |  | PA | Maysville | Relay | Modify | UC | 0.09 | AE1-237 |  |  | No | 10/8/2024 | 10/8/2024 | 0 | 6/1/2020 | 12/31/2023
n7936 | Not Specified | Update Relay Settings at Sharon 69 kV substation | Network | 69 | 0.09 | 6/1/2020 | ATSI |  |  |  |  | PA | Sharon | Relay | Modify | UC | 0.09 | AE1-237 |  |  | No | 10/8/2024 | 10/8/2024 | 0 | 6/1/2020 | 12/31/2023
n7937 | Not Specified | SCADA/Fiber Communication: Estimated installation of 700 MHz radio system (70% penetration of FE territory) to support the SCADA switch replacements at AE1-237 substation. Assumed SCADA work is included in this cost. | Network | 69 | 0.05 | 6/1/2020 | ATSI |  |  |  |  | PA | AE1-237 Tap | Communication Equipment | Install | UC | 0.05 | AE1-237 |  |  | No | 10/8/2024 | 10/8/2024 | 0 | 6/1/2020 | 12/31/2023
n8187.1 | Not Specified | Farmers Valley – Ridgway 115 kV Line Loop: Construct a loop from the Farmers Valley – Ridgway 115 kV line to the new substation, approximately 14.4 miles from Farmers Valley substation. | Network | 115 | 1.69 | 12/31/2020 | PENELEC |  |  |  |  | PA | Farmers Valley, Ridgeway | Conductor | Build | UC | 1.69 | AE2-113 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 12/31/2020 | 11/1/2024
n8187.2 | Not Specified | Ridgway Substation: Line terminal upgrade | Network | 115 | 0.19 | 12/31/2020 | PENELEC |  |  |  |  | PA | Ridgeway | Relay | Upgrade | UC | 0.19 | AE2-113 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 12/31/2020 | 11/1/2024
n8187.3 | Not Specified | Farmers Substation: Line terminal upgrade | Network | 115 | 0.3 | 12/31/2020 | PENELEC |  |  |  |  | PA | Farmers | Relay | Upgrade | UC | 0.3 | AE2-113 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 12/31/2020 | 11/1/2024
n8187.4 | Not Specified | Pierce Brook Substation: Line terminal upgrade | Network | 115 | 0.06 | 12/31/2020 | PENELEC |  |  |  |  | PA | Pierce Brook | Relay | Upgrade | UC | 0.06 | AE2-113 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 12/31/2020 | 11/1/2024
n8314.1 | Not Specified | SCADA/Fiber Communication: Design, install, and test/commission MPLS Equipment for SCADA transport | Network | 115 | 0.21 | 9/20/2019 | PENELEC |  |  |  |  | PA | AF1-086 | Communication Equipment | Install | UC | 0.21 | AF1-086 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 9/20/2019 | 9/30/2026
n8314.2 | Not Specified | Fiber from AF1-086 interconnection substation to ADSS Backbone: Install fiber from AF1-086 interconnection substation to ADSS Backbone for communication transport | Network | 115 | 1.26 | 9/20/2019 | PENELEC |  |  |  |  | PA | AF1-086 | Communication Equipment | Install | UC | 1.26 | AF1-086 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 9/20/2019 | 9/30/2026
n8314.3 | Not Specified | Garman-Shawville 115 kV Line Loop: Loop existing Garman Shawville 115 kV Line into the new CPV Rogue’s Wind interconnection substation. | Network | 115 | 1.21 | 9/20/2019 | PENELEC |  |  |  |  | PA | AF1-086 | Transmission Line | Modify | UC | 1.21 | AF1-086 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 9/20/2019 | 9/30/2026
n8314.4 | Not Specified | Madera: Modify drawings and nameplates for line name change. | Network | 115 | 0.03 | 9/20/2019 | PENELEC |  |  |  |  | PA | Madera | Substation | Modify | UC | 0.03 | AF1-086 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 9/20/2019 | 9/30/2026
n8314.5 | Not Specified | Westover: Modify drawings and nameplates for line name change. | Network | 115 | 0.03 | 9/20/2019 | PENELEC |  |  |  |  | PA | Westover | Substation | Modify | UC | 0.03 | AF1-086 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 9/20/2019 | 9/30/2026
n8314.6 | Not Specified | Glory: Line Terminal upgrade | Network | 115 | 0.39 | 9/20/2019 | PENELEC |  |  |  |  | PA | Glory | Transmission Line | Upgrade | UC | 0.39 | AF1-086 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 9/20/2019 | 9/30/2026
n8314.7 | Not Specified | Shawville: Line Terminal upgrade | Network | 115 | 0.57 | 9/20/2019 | PENELEC |  |  |  |  | PA | Shawville | Transmission Line | Upgrade | UC | 0.57 | AF1-086 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 9/20/2019 | 9/30/2026
n8314.8 | Not Specified | Garman: Line Terminal upgrade | Network | 115 | 0.81 | 9/20/2019 | PENELEC |  |  |  |  | PA | Garman | Transmission Line | Upgrade | UC | 0.81 | AF1-086 |  |  | No | 10/3/2023 | 10/3/2023 | 0 | 9/20/2019 | 9/30/2026
s0320 | PJM WEST | Rebuild aging double circuit 138 kV tower line between Brunot Island and Crescent substations with 138 kV tower line. | Supplemental | 138 | 160 |  | DL |  |  |  |  | PA | Brunot Island - Crescent | Transmission Line | Rebuild | UC | 40 | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 6/1/2027 |  | No | 9/19/2011 | 2/9/2017 | 70
s0320.1 | PJM WEST | Reconfigure 138 kV circuits to create Brunot Island-Montour, Montour-Sewickley, and Crescent-Sewichley 138 kV circuits and establish new Brunot Island-Crescent 138 kV circuit | Supplemental | 345/138 | 0 |  | DL |  |  |  |  | PA |  | Transmission Line | Reconfigure | UC | 0 | Infrastructure Resilience | 6/1/2027 |  | No | 11/5/2015 | 11/5/2015 | 70
s0945.1 | PJM MA | Rebuild the Juniata 230/69 kV Substation | Supplemental | 230/69 | 36 |  | PPL |  |  |  |  | PA | Juniata | Substation | Rebuild | UC | 36 | Equipment Material Condition, Performance and Risk | 12/31/2025 |  | No | 7/29/2015 | 7/29/2015 | 70
s0945.2 | PJM MA | Rebuild the Juniata - Richfield/Newport 69 kV Lines (3.5 mi) | Supplemental | 69 | 42.6 |  | PPL |  |  |  |  | PA | Juniata - Richfield/Newport | Transmission Line | Rebuild | UC | 42.6 | Equipment Material Condition, Performance and Risk,Infrastructure Resilience | 11/30/2028 |  | No | 7/29/2015 | 7/29/2015 | 30
s0945.4 | PJM MA | Rebuild the Cumberland 230/69 kV substation | Supplemental | 230/69 | 27.2 |  | PPL |  |  |  |  | PA | Cumberland | Substation | Rebuild | UC | 27.2 | Equipment Material Condition, Performance and Risk,Infrastructure Resilience | 11/26/2026 |  | No | 7/29/2015 | 7/29/2015 | 60
s0945.5 | PJM MA | Rebuild the Cumberland - West Carlisle 1 & 2 69 kV (10.5 mi) | Supplemental | 69 | 27.2 |  | PPL |  |  |  |  | PA | Cumberland - West Carlisle | Transmission Line | Rebuild | UC | 27.2 | Equipment Material Condition, Performance and Risk,Infrastructure Resilience | 12/30/2025 |  | No | 7/29/2015 | 7/29/2015 | 75
s0945.6 | PJM MA | Rebuild the Cumberland - West Shore 1 & 2 69 kV (14 mi) | Supplemental | 69 | 27.4 |  | PPL |  |  |  |  | PA | Cumberland - West Shore | Transmission Line | Rebuild | UC | 27.4 | Equipment Material Condition, Performance and Risk,Infrastructure Resilience | 12/31/2025 |  | No | 7/29/2015 | 7/29/2015 | 90
s0947.1 | PJM MA | Rebuild Dauphin - Capital Park 1 & 2 69 kV lines (1 mi) | Supplemental | 69 | 1.5 |  | PPL |  |  |  |  | PA | Dauphin - Capital Park | Transmission Line | Rebuild | UC | 1.5 | Equipment Material Condition, Performance and Risk,Infrastructure Resilience | 7/31/2026 |  | No | 7/29/2015 | 7/29/2015 | 50
s0947.4 | PJM MA | Rebuild Harrisburg Substation to 230/69 kV GIS | Supplemental | 230/69 | 64 |  | PPL |  |  |  |  | PA | Harrisburg | Substation | Rebuild | UC | 64 | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 12/31/2027 |  | No | 7/29/2015 | 7/29/2015 | 70
s0948.6 | PJM MA | Rebuild West Hempfield-Hummelstown 69 kV line (10.6 mi) | Supplemental | 69 | 32.5 |  | PPL |  |  |  |  | PA | West Hempfield - Hummelstown | Transmission Line | Rebuild | UC | 32.5 | Equipment Material Condition, Performance and Risk | 2/19/2026 |  | No | 7/29/2015 | 7/29/2015 | 75
s0958.3 | PJM MA | Rebuild the Martins Creek - Nazareth #1 and #2 69 kV lines (13 mi) | Supplemental | 69 | 36.2 |  | PPL |  |  |  |  | PA | Martins Creek - Nazareth | Transmission Line | Rebuild | UC | 36.2 | Equipment Material Condition, Performance and Risk | 11/28/2025 |  | No | 7/29/2015 | 7/29/2015 | 90
s0961.1 | PJM MA | Rebuild the Lackawanna - East Carbondale 69 kV line (19 mi) | Supplemental | 69 | 39.4 |  | PPL |  |  |  |  | PA | Lackawanna - East Carbondale | Transmission Line | Rebuild | UC | 39.4 | Equipment Material Condition, Performance and Risk,Infrastructure Resilience | 9/28/2026 |  | No | 7/29/2015 | 7/29/2015 | 90
s0962.3 | PJM MA | Install second circuit on the Blooming Grove - West Damascus 69 kV line (2.3 mi), Install second circuit on Bohemia 69 kV Tap (3.9 mi) | Supplemental | 69 | 8 |  | PPL |  |  |  |  | PA | Blooming Grove - West Damascus, Bohemia | Transmission Line | Install | UC | 8 | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 12/31/2025 |  | No | 7/29/2015 | 7/29/2015 | 80
s0963.5 | PJM MA | Rebuild the Frackville - Fishbach 3 69 kV Line (8.5 mi) | Supplemental | 69 | 18.3 |  | PPL |  |  |  |  | PA | Frackville - Fishbach | Transmission Line | Rebuild | UC | 18.3 | Equipment Material Condition, Performance and Risk,Infrastructure Resilience | 7/19/2027 |  | No | 7/29/2015 | 7/29/2015 | 80
s0964.6 | PJM MA | Rebuild the Jenkins - Plymouth 69 kV line (3.4 mi) | Supplemental | 69 | 6 |  | PPL |  |  |  |  | PA | Jenkins - Plymouth | Transmission Line | Rebuild | UC | 6 | Equipment Material Condition, Performance and Risk,Infrastructure Resilience | 8/30/2027 |  | No | 7/29/2015 | 7/29/2015 | 60
s1101 | PJM MA | Rebuild the existing Shawnee-Bushkill 230 kV line (Approximately 2.2 Miles). | Supplemental | 230 | 6.8 |  | PPL |  |  |  |  | PA | Shawnee - Bushkill | Transmission Line | Rebuild | UC | 6.8 | Equipment Material Condition, Performance and Risk | 12/31/2025 |  | No | 1/7/2016 | 1/7/2016 | 50
s1152 | PJM MA | Remove the 230kV reactor and 230kV bypass circuit breaker on the Brunner Island-W.Hempfield 230kV line | Supplemental | 230 | 0.93 |  | PPL |  |  |  |  | PA | Brunner Island - W.Hempfield | Reactive Device | Remove | UC | 0.93 | Equipment Material Condition, Performance and Risk | 12/15/2033 |  | No | 7/26/2016 | 7/26/2016 | 10
s1640.2 | PJM MA | Replace Middletown Junction #2 (75 MVA) & #5 (75/84 MVA) 230/115 kV transformers with 180/240/300 MVA units | Supplemental | 230/115 | 0 |  | ME |  |  |  |  | PA | Middletown Junction#2 | Transformer | Replace | UC | 0 | Operational Flexibility and Efficiency | 6/15/2025 |  | No | 3/23/2018 | 5/25/2018 | 45
s1641 | PJM MA | Install new 115 kV circuit breakers at Tolna on the generator terminal and in the bus tie position. | Supplemental | 115 | 4.7 |  | ME |  |  |  |  | PA | Tolna | Circuit Breaker | Install | UC | 2.4 | Operational Flexibility and Efficiency | 12/31/2026 |  | No | 3/23/2018 | 5/25/2018 | 85
s1726 | PJM MA | Expand the existing South Reading 69 kV yard to a breaker-and-a-half configuration | Supplemental | 69 | 26.66 |  | ME |  |  |  |  | PA | South Reading | Bus | Rebuild | UC | 19.4 | Operational Flexibility and Efficiency | 12/31/2025 |  | No | 7/20/2018 | 8/24/2018 | 75
s1773.1 | PJM MA | Yeagertown - Construct a new five breaker 230 kV ring bus | Supplemental | 230 | 20.4 |  | PENELEC |  |  |  |  | PA | Yeagertown | Bus | Build | UC | 20.4 | Operational Flexibility and Efficiency | 12/19/2025 |  | No | 10/29/2018 | 10/29/2018 | 70
s1773.2 | PJM MA | Yeagertown - Construct a new five breaker 46 kV ring bus | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Yeagertown | Bus | Build | UC |  | Operational Flexibility and Efficiency | 12/19/2025 |  | No | 10/29/2018 | 10/29/2018 | 45
s1773.3 | PJM MA | Loop Lewistown – Logan 1LK line into the Yeagertown 46 kV ring bus | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Lewistown, Logan, Yeagertown | Transmission Line | Modify | UC |  | Operational Flexibility and Efficiency | 12/19/2025 |  | No | 10/29/2018 | 10/29/2018 | 45
s1773.4 | PJM MA | Tap the existing Yeagertown – Logan 1YL line and connect to the new Yeagertown 46 kV ring bus | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Yeagertown, Logan | Transmission Line | Modify | UC |  | Operational Flexibility and Efficiency | 12/19/2025 |  | No | 10/29/2018 | 10/29/2018 | 45
s1773.5 | PJM MA | Install a new Yeagertown 230/46 kV 60/80/100 MVA transformer | Supplemental | 230/46 | 0 |  | PENELEC |  |  |  |  | PA | Yeagertown | Transformer | Install | UC |  | Operational Flexibility and Efficiency | 12/19/2025 |  | No | 10/29/2018 | 10/29/2018 | 45
s1773.6 | PJM MA | Install a 46 kV bus tie breaker between the existing Yeagertown and the new ring bus to be operated as normally open | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Yeagertown | Circuit Breaker | Install | UC |  | Operational Flexibility and Efficiency | 12/19/2025 |  | No | 10/29/2018 | 10/29/2018 | 45
s1773.7 | PJM MA | Operate the Yeagertown 46-34.5 kV transformer high side circuit breaker as normally open | Supplemental | 46/34.5 | 0 |  | PENELEC |  |  |  |  | PA | Yeagertown | Circuit Breaker | Modify | UC |  | Operational Flexibility and Efficiency | 12/19/2025 |  | No | 10/29/2018 | 10/29/2018 | 45
s1774.3 | PJM MA | Replace the Seward #9 230/115 kV with a 230/115 kV 180/240/300 MVA transformer | Supplemental | 230/115 | 0 |  | PENELEC |  |  |  |  | PA | Seward | Transformer | Replace | UC |  | Operational Flexibility and Efficiency | 11/7/2025 |  | No | 10/29/2018 | 10/29/2018 | 50
s1775.1 | PJM MA | Summit - Construct a five breaker 115 kV ring bus | Supplemental | 115/46 | 26.3 |  | PENELEC |  |  |  |  | PA | Summit | Bus | Build | UC | 26.3 | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 11/24/2025 |  | No | 10/29/2018 | 10/29/2018 | 70
s1775.2 | PJM MA | Summit - Construct a 46 kV breaker-and-a-half station with eight breakers | Supplemental | 115/46 | 0 |  | PENELEC |  |  |  |  | PA | Summit | Bus | Build | UC |  | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 11/24/2025 |  | No | 10/29/2018 | 10/29/2018 | 50
s1775.3 | PJM MA | Replace the Summit #1 and #2 115/46 kV with 115/46 kV 45/60/75 MVA transformers | Supplemental | 115/46 | 0 |  | PENELEC |  |  |  |  | PA | Summit | Transformer | Replace | UC |  | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 11/24/2025 |  | No | 10/29/2018 | 10/29/2018 | 50
s1775.4 | PJM MA | Summit - Adjust relay settings at remote ends | Supplemental | 115/46 | 0 |  | PENELEC |  |  |  |  | PA | Summit | Relay | Modify | UC |  | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 11/24/2025 |  | No | 10/29/2018 | 10/29/2018 | 50
s1811 | PJM MA | Pleasureville – Harley Davidson – York Incinerator 115 kV Line Rehab | Supplemental | 115 | 3.9 |  | ME |  |  |  |  | PA | Pleasureville, Harley Davidson, York Incinerator | Transmission Line | Upgrade | UC |  | Equipment Material Condition, Performance and Risk | 12/12/2025 |  | No | 11/28/2018 | 11/28/2018 | 35
s1850.2 | PJM MA | Tap existing 69 kV Schuylkill to Angora, Schuylkill to Island Road, and Schuylkill to University lines to feed new Civic substation. Retire portions of the Schuylkill to Island Road and Schuylkill to University lines under the Schuylkill river | Supplemental | 69 | 10 |  | PECO |  |  |  |  | PA | Schuylkill, Angora, Island Road, University | Transmission Line | Modify | UC |  | Equipment Material Condition, Performance and Risk | 12/31/2025 |  | No | 4/26/2019 | 4/26/2019 | 90
s1886.1 | PJM MA | Replace line relaying and circuit breaker on the Whetstone 115 kV Line exit at the Ridgway substation. | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA | Ridgway | Conductor | Upgrade | UC |  | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 4/25/2025 |  | No | 3/25/2019 | 11/19/2019 | 95
s1886.2 | PJM MA | Replace line relaying on the Ridgway 115 kV line exit at the Whetstone Substation. | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA | Whetstone | Relay | Upgrade | UC |  | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 4/25/2025 |  | No | 3/25/2019 | 11/19/2019 | 95
s1890.1 | PJM MA | Replace line relaying and line trap on the Union City 115 kV line exit at the Erie South substation. | Supplemental | 115 | 0 |  | PENELEC |  |  |  |  | PA | Erie South | Conductor | Upgrade | UC |  | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 3/31/2025 |  | No | 3/25/2019 | 11/19/2019 | 75
s1891 | PJM MA | Construct a 115 kV ring bus at the Titusville. | Supplemental | 115 | 9.3 |  | PENELEC |  |  |  |  | PA | Titusville | Bus | Build | UC | 9.3 | Operational Flexibility and Efficiency | 12/31/2027 |  | No | 3/25/2019 | 11/19/2019 | 40
s1893.1 | PJM MA | Rehab/Rebuild Baldy - South Hamburg (~29.3 miles) 69 kV line | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | Baldy, South Hamburg | Transmission Line | Rebuild | UC |  | Equipment Material Condition, Performance and Risk | 5/30/2025 |  | No | 4/26/2019 | 11/19/2019 | 50
s1893.2 | PJM MA | Replace line relaying and substation conductoron the Weisenberg 69 kV line exit at the at Baldy substation. | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | Baldy | Conductor | Upgrade | UC |  | Equipment Material Condition, Performance and Risk | 5/30/2025 |  | No | 4/26/2019 | 11/19/2019 | 50
s1893.3 | PJM MA | Replace substation conductor on the Lynnville 69 kV line exit at the South Hamburg substation. | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | South Hamburg | Conductor | Upgrade | UC |  | Equipment Material Condition, Performance and Risk | 5/30/2025 |  | No | 4/26/2019 | 11/19/2019 | 50
s1898 | PJM MA | Rehab/Rebuild Bernville - State Street - South Hamburg 69 kV Line | Supplemental | 69 | 18.5 |  | ME |  |  |  |  | PA | Bernville, South Hamburg | Transmission Line | Rebuild | UC | 14.9 | Equipment Material Condition, Performance and Risk | 12/31/2025 |  | No | 4/26/2019 | 11/19/2019 | 70
s1903 | PJM MA | Rehab/Rebuild North Hershey - Grantville - Turf Club 69 kV line. Reconductor ~4.5 miles | Supplemental | 69 | 8.1 |  | ME |  |  |  |  | PA | North Hershey, Grantville, Turf Club | Transmission Line | Rebuild | UC | 6.4 | Equipment Material Condition, Performance and Risk | 5/22/2026 |  | No | 4/26/2019 | 11/19/2019 | 50
s1907.3 | PJM MA | Expand the South Lebanon 230 kV bus into a 5 breaker ring bus | Supplemental | 230 | 6.6 |  | ME |  |  |  |  | PA | South Lebanon | Bus | Modify | UC |  | Equipment Material Condition, Performance and Risk | 12/11/2025 |  | No | 4/26/2019 | 11/19/2019 | 60
s1909.1 | PJM MA | Rehab/Rebuild South Lebanon - Bayer Labs - Myerstown 69 kV line. Reconductor ~7 miles | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | South Lebanon, Bayer Labs, Myerstown | Transmission Line | Rebuild | UC |  | Equipment Material Condition, Performance and Risk | 12/31/2025 |  | No | 4/26/2019 | 11/19/2019 | 40
s1910.2 | PJM MA | Replace switches on the Fredericksburg Tap 69 kV line exit at North Lebanon substation. | Supplemental | 69 | 0 |  | ME |  |  |  |  | PA | North Lebanon | Disconnect Switch | Upgrade | UC |  | Equipment Material Condition, Performance and Risk | 12/31/2025 |  | No | 4/26/2019 | 11/19/2019 | 70
s1922 | PJM MA | Build a new 17th Street 46 kV substation. | Supplemental | 46 | 9 |  | PENELEC |  |  |  |  | PA | 17th Street | Substation | Build | UC | 9 | Operational Flexibility and Efficiency | 12/20/2025 |  | No | 5/31/2019 | 11/19/2019 | 40
s1922.1 | PJM MA | Build a new 17th Street 46 kV breaker-and-a-half substation to replace the existing Collinsville substation | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | 17th Street | Substation | Build | UC |  | Operational Flexibility and Efficiency | 12/20/2025 |  | No | 5/31/2019 | 11/19/2019 | 40
s1922.10 | PJM MA | Install a new terminal for 46 kV capacitor at the 17th Street substation. | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | 17th Street | Bus | Modify | UC |  | Operational Flexibility and Efficiency | 12/20/2025 |  | No | 5/31/2019 | 11/19/2019 | 40
s1922.2 | PJM MA | Install a new terminal for 20th Street 46 kV line exit at the 17th Street substation. | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | 17th Street | Bus | Modify | UC |  | Operational Flexibility and Efficiency | 12/20/2025 |  | No | 5/31/2019 | 11/19/2019 | 40
s1922.3 | PJM MA | Install a new terminal for Greenwood 46 kV line exit at the 17th Street substation. | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | 17th Street | Bus | Modify | UC |  | Operational Flexibility and Efficiency | 12/20/2025 |  | No | 5/31/2019 | 11/19/2019 | 40
s1922.4 | PJM MA | Install a new terminal for Pleasant Valley 46 kV line exit at the 17th Street substation. | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | 17th Street | Bus | Modify | UC |  | Operational Flexibility and Efficiency | 12/20/2025 |  | No | 5/31/2019 | 11/19/2019 | 40
s1922.5 | PJM MA | Install a new terminal for Altoona F 46 kV line exit at the 17th Street substation. | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | 17th Street | Bus | Modify | UC |  | Operational Flexibility and Efficiency | 12/20/2025 |  | No | 5/31/2019 | 11/19/2019 | 40
s1922.6 | PJM MA | Install a new terminal for Altoona AG 46 kV line exit at the 17th Street substation. | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | 17th Street | Bus | Modify | UC |  | Operational Flexibility and Efficiency | 12/20/2025 |  | No | 5/31/2019 | 11/19/2019 | 40
s1922.7 | PJM MA | Install a new terminal for Altoona G 46 kV line exit at the 17th Street substation. | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | 17th Street | Bus | Modify | UC |  | Operational Flexibility and Efficiency | 12/20/2025 |  | No | 5/31/2019 | 11/19/2019 | 40
s1922.8 | PJM MA | Install a new terminal for No.1 46/12.47 kV transformer at the 17th Street substation. | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | 17th Street | Bus | Modify | UC |  | Operational Flexibility and Efficiency | 12/20/2025 |  | No | 5/31/2019 | 11/19/2019 | 40
s1922.9 | PJM MA | Install a new terminal for No.2 46/12.47 kV transformer at the 17th Street substation. | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | 17th Street | Bus | Modify | UC |  | Operational Flexibility and Efficiency | 12/20/2025 |  | No | 5/31/2019 | 11/19/2019 | 40
s1923 | PJM MA | Warrior Ridge 46 kV project | Supplemental | 46 | 26.4 |  | PENELEC |  |  |  |  | PA | Warrior Ridge | Substation | Build | UC | 26.4 | Operational Flexibility and Efficiency | 12/20/2025 |  | No | 5/31/2019 | 11/19/2019 | 75
s1923.1 | PJM MA | Build a 46 kV breaker-and-a-half substation, Warrior Ridge. | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Warrior Ridge | Substation | Build | UC |  | Operational Flexibility and Efficiency | 12/20/2025 |  | No | 5/31/2019 | 11/19/2019 | 40
s1971 | PJM WEST | Cedar Street: Replace 138 kV Cedar Street - New castle Line relaying | Supplemental | 138 | 0.2 |  | ATSI |  |  |  |  | PA | Cedar St | Relay | Upgrade | UC | 0.2 | Operational Flexibility and Efficiency,Infrastructure Resilience | 6/3/2022 |  | No | 3/25/2019 | 3/25/2019 | 50
s2035 | PJM MA | Install a tie breaker at Westgate 115 kV | Supplemental | 115 | 0.6 |  | ME |  |  |  |  | PA | Westgate | Circuit Breaker | Install | UC | 0.6 | Operational Flexibility and Efficiency | 10/27/2025 |  | No | 7/31/2019 | 11/19/2019 | 50
s2039 | PJM MA | Convert Fredericksburg 69 kV to a four (4) breaker ring bus | Supplemental | 69 | 6 |  | ME |  |  |  |  | PA | Fredericksburg | Bus | Modify | UC | 6 | Operational Flexibility and Efficiency | 10/20/2026 |  | No | 7/31/2019 | 11/19/2019 | 50
s2049 | PJM MA | Shade Gap 115 kV Substation – Replace line relaying and substation conductor on the Hill Valley – Shade Gap 115 kV Line | Supplemental | 115 | 1.2 |  | PENELEC |  |  |  |  | PA | Shade Gap | Relay | Replace | UC | 0.8 | Equipment Material Condition, Performance and Risk,Operational Flexibility and Efficiency | 12/30/2025 |  | No | 7/31/2019 | 11/19/2019 | 40
s2303 | PJM MA | Retire the Jackson 230/115 kV #4 transformer and remove from service, plus retire the B10 230 kV breaker and replace it with bus conductors. | Supplemental | 230/115 | 0 |  | ME |  |  |  |  | PA | Jackson | Transformer | Modify | UC | 0 | Equipment Material Condition, Performance and Risk | 12/31/2029 |  | No | 7/7/2020 | 7/7/2020 | 50
s2374 | PJM MA | Rebuild the 38.0 miles of Corten tower sections of the Siegfried-Harwood & Harwood-East Palmerton/Siegfried-East Palmerton 230kV lines with steel monopoles and new conductor. | Supplemental | 230 | 136.8 |  | PPL |  |  |  |  | PA | Siegfried/Harwood/East Palmerton | Transmission Structures | Rebuild | UC | 136.8 | Equipment Material Condition, Performance and Risk | 10/23/2026 |  | No | 10/6/2020 | 10/6/2020 | 40
s2409 | PJM MA | Add a new 115 kV line terminal to the Germantown 115 kV substation and construct approximately 3.5 miles of 115 kV line to the customer substation. | Supplemental | 115 | 10.8 |  | ME |  |  |  |  | PA | Germantown | Substation | Install | UC | 10.8 | Customer Service | 12/19/2025 |  | No | 11/18/2020 | 11/18/2020 | 40
s2535.2 | PJM MA | Replace in-line switch on the Allegheny Hydro Tap – RAM Junction 46 kV Line | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Raystown/ McConnellstown | Disconnect Switch | Replace | UC |  | Operational Flexibility and Efficiency | 3/29/2026 |  | No | 4/14/2021 | 4/14/2021 | 90
s2535.3 | PJM MA | Replace in-line switch on the RAM Junction – Piney Ridge 46 kV Line | Supplemental | 46 | 0 |  | PENELEC |  |  |  |  | PA | Raystown/ McConnellstown | Disconnect Switch | Replace | UC |  | Operational Flexibility and Efficiency | 3/29/2026 |  | No | 4/14/2021 | 4/14/2021 | 90
s2826 | PJM WEST | Replace the two Brunot Island 138/69 kV transformers. | Supplemental | 138 | 3.25 |  | DL |  |  |  |  | PA | Brunot Island | Transformer | Replace | UC | 3.25 | Equipment Material Condition, Performance and Risk | 12/31/2025 |  | No | 8/19/2022 | 8/19/2022 | 60
s2869 | PJM WEST | Replace relaying & controls at Sharon substation for the following lines: Sharon – Maysville Y-299/Y-81 69 kV Line Sharon – McDowell Y-300 69 kV Line Sharon – Maysville Y-301 69 kV Line Sharon – Masury Y-188/Y-303 69 kV Line Install a new 69 kV control building at Sharon substation Adjust relay settings at Masury, Maysville, & McDowell substations Install a new standard large RTU panel and a new standard HMI Pane | Supplemental | 69 | 20.8 |  | ATSI |  |  |  |  | PA | Sharon 69 kV | Relay | Replace | UC | 20.8 | Equipment Material Condition, Performance and Risk,Infrastructure Resilience | 12/15/2025 |  | No | 11/18/2022 | 11/18/2022 | 65
s2968 | PJM MA | Install three SCADA controlled transmission line switches. Construct approximately 0.1 miles of transmission line using 556 ACSR 26/7 from tap point to customer substation. Install one 69 kV revenue metering package at customer substation. Modify relay settings at Bernville and South Hamburg substations | Supplemental | 69 | 1.6 |  | ME |  |  |  |  | PA | Bernville | Transmission Line | Tap | UC | 1.6 | Customer Service | 4/30/2026 |  | No | 6/15/2023 | 6/15/2023 | 60
s2998 | PJM WEST | Install three SCADA controlled transmission line switches, Construct 0.1 miles of 954 ACSR 48/7 transmission line, Adjust relay settings at Maple substation, Install tie line interchange revenue metering at Krendale | Supplemental | 138 | 1.7 |  | ATSI |  |  |  |  | PA | Krendale-Maple | Relay | Install | UC | 1.7 | Customer Service | 10/17/2025 |  | No | 5/19/2023 | 5/19/2023 | 40
s3123.1 | PJM WEST | Rebuild/rehab the Connellsville – Stoner Junction 138 kV Line. Replace existing transmission line conductor with larger size. Rebuild/rehab the Stoner Junction – King Farm 138 kV Line. Rebuild/rehab the Stoner Junction – Iron Bridge 138 kV Line. Replace existing transmission line conductor with larger size. | Supplemental | 138 | 31.5 |  | APS |  |  |  |  | PA | Stoner Junction | Transmission Line | Rebuild | UC | 31.5 | Equipment Material Condition, Performance and Risk | 6/15/2026 |  | No | 7/21/2023 | 7/21/2023 | 65
s3185.1 | PJM MA | Rebuild approx. 2.5 miles with new dual circuit, weathering steel monopole structures and 959.6 kcmil ACSS conductor. Replace various substation equipment at Plymouth Meeting and Flint substations to make the conductor the limiting element. | Supplemental | 230 | 25.9 |  | PECO |  |  |  |  | PA | Plymouth Meeting | Transmission Structures | Rebuild | UC | 18.2 | Equipment Material Condition, Performance and Risk | 11/30/2026 |  | No | 10/31/2023 | 10/31/2023 | 50
s3263.1 | PJM MA | Convert Hokes Substation into a six-breaker ring bus Upgrade terminal equipment to transmission line ratings and adjust relay settings Transmission Line Ratings: | Supplemental | 69 | 24.1 |  | ME |  |  |  |  | PA | Hokes | Circuit Breaker | Upgrade | UC | 24.1 | Operational Flexibility and Efficiency | 6/1/2026 |  | No | 11/16/2023 | 11/16/2023 | 45
s3268.1 | PJM MA | Westfall 115 kV Substation Replace the existing control building with a new Package Control Enclosure that can accommodate all relaying and equipment. | Supplemental | 115 | 6.7 |  | PENELEC |  |  |  |  | PA | Westfall | Relay | Replace | UC | 6.7 | Equipment Material Condition, Performance and Risk | 10/30/2026 |  | No | 12/13/2023 | 12/13/2023 | 40
s3289.1 | PJM MA | Rebuild and reconductor approximately 0.5 miles of the Birdsboro – Birdsboro Extrusions 69 kV Line At Birdsboro Substation: Replace 69 kV circuit breaker. Replace four 69 kV disconnect switches. Replace existing line drop and bus conductor. Replace existing line and breaker relaying. At South Reading Substation: Adjust relay settings | Supplemental | 69 | 2.1 |  | ME |  |  |  |  | PA | Birdsboro | Substation | Rebuild | UC | 2.1 | Equipment Material Condition, Performance and Risk | 6/1/2026 |  | No | 2/15/2024 | 2/15/2024 | 40
s3356.1 | PJM WEST | Establish a new substation, Veterans Bridge Substation, in the North Shore neighborhood of Pittsburgh by tapping the existing Brunot Island – Forbes 138 kV underground HPFF transmission line. Veterans Bridge Substation will supply the customer for the duration of the customer’s construction project. Veterans Bridge Substation will contain a single 138 kV breaker and 138/23 kV transformer to serve the customer’s load. Establishing Veterans Bridge Substation will require extending the Brunot Island – Forbes 138 kV 138 kV underground HPFF transmission line by approximately 50 ft. | Supplemental | 138 | 0 |  | DL |  |  |  |  | PA | Veterans Bridge | Substation | Build | UC | 0 | Customer Service | 1/31/2026 |  | No | 2/16/2024 | 2/16/2024 | 40
s3413.1 | PJM MA | Replace relaying and limiting substation conductor at Chester and West Wharton 230 kV Substations | Supplemental | 230 | 2 |  | JCPL |  |  |  |  | PA | Chester | Substation | Replace | UC | 2 | Equipment Material Condition, Performance and Risk | 12/23/2025 |  | No | 10/31/2023 | 10/31/2023 | 40
s3466.1 | PJM WEST | Eliminate the 69 kV voltage level from Dravosburg Substation by replacing the two aged 138-69 kV autotransformers and the station’s existing 69-23 kV transformers with two new 138-23 kV transformers. This elimination will require an extension of the 138 kV bus, the addition of 3 new 138 kV breakers, and the removal of the 69 kV bus and associated breakers. | Supplemental | 138 | 8.5 |  | DL |  |  |  |  | PA | Dravosburg | Transformer | Replace | UC | 8.5 | Customer Service,Equipment Material Condition, Performance and Risk | 12/1/2027 |  | No | 5/17/2024 | 5/17/2024 | 40
s3481.1 | PJM WEST | Tap the Grandpoint – Guilford 138 kV and install two SCADA controlled switches. Construct 500 ft of 138 kV line extension from the tap location to the Customer’s substation.Install one SCADA controlled switch at POI between FE and Customer. Install 138 kV revenue metering in Customer’s substation. Modify line relay settings in Grandpoint and Guilford substations. | Supplemental | 138 | 1.75 |  | APS |  |  |  |  | PA | Grand Point – Guilford | Switch | Install | UC | 1.75 | Customer Service | 11/2/2025 |  | No | 5/17/2024 | 5/17/2024 | 40
s3627.1 | PJM MA | Alcoa – Broad Street 69 kV Line Customer Connection: Install one SCADA controlled transmission line switch. Relocate SW 9206 at/near STR. 92-81. Construct approximately 1-2 spans of transmission line using from tap to customer. Install one 69 kV revenue metering package at customer substation. Modify relay settings at Alcoa and Broad St. substations. | Supplemental | 69 | 1.19 |  | ME |  |  |  |  | PA | LebaFALSEn, PA | Transmission Line | Tap | UC | 1.19 | Customer Service | 11/24/2025 |  | No | 8/15/2024 | 8/15/2024 | 0

## Definitions-Mapping
Column Name | Definition
Upgrade ID | PJM-assigned project identifier
Region | Region of the project (PJM West, PJM MAAC, PJM South, MISO)
Description | Description
Project Type | Identifies the policies and procedures governing the transmission project: baseline, supplemental or network type
Voltage (kv) | Operating voltage of the transmission asset
Cost Estimate | Cost Estimate
Required Date | Date when the criteria violation will impact the system
Transmission Owner | Owner of the transmission asset
Proposal IDs | List of proposal IDs
Schedule 12 Location | Tariff Schedule 12 Appendix
NLRS Cost Allocation (%) | Non-Load Ratio Share Cost Allocation Percentage
LRS Cost Allocation (%) | Load Ratio Share Cost Allocation Percentage
State | State in which the asset is located
Location | Electrical location of the transmission asset
Equipment | Type of transmission asset being worked on
Task | Type of work to be performed
Status | Current status of the project: Planning (active), Engineering and Procurement, Under Construction, In-Service, On Hold, Withdrawn or Canceled
TEAC Cost (Millions) | Estimated cost presented at the TEAC of performing the upgrade
Driver | Fundamental motivation for performing the upgrade
Projected In-Service Date | Date when the Transmission Owner expects the upgrade to be placed in service
Actual In Service Date | The date the upgrade is placed in service
Immediate Need | Immediate Need
Initial TEAC Date | Initial TEAC Date
Latest TEAC Date | Latest TEAC Date
Percent Complete | Percent Complete
ISA In-Service Date | ISA In-Service Date
Revised In-Service Date | Revised In-Service Date
TEAC Materials | Committee presentations of the projects as well as other projects in the area